Performance Indicator Reference Sheet

Instructions:  Goals, objectives, sub-objectives, and activities may have more than one indicator, or they may have none.  Add or delete sections as appropriate to match the Change Map.  For example, if there are multiple goals, each with one indicator, copy and paste the entire “Goal” section to match the number of goals with indicators, and change the goal numbering to match the Change Map.  If using multiple indicators for a goal, objective, or activity, repeat the information starting with “indicator name” under the associated Goal / Objective / Activity section header.

Notes:  For a project proposal, it is only necessary to complete three indicators, with at least one outcome indicator, using notional data if real data are not available.  The template will need to be fully completed (matching all indicators listed in the Change Map) as an early deliverable.  See Appendix A for definitions.  See Appendix B for the Indicator Work Aid.  See Appendix C for a quick reference on properties of a useful indicator.

- Project Information

Project Name:

Project Award Number:

INL POC:

Implementing Organization Name:

Implementing Organization POC:

Project Start Date:

Project End Date:

Project Location(s):

- Performance Periods and Reporting Due Dates

| Project Reporting Period Dates |  |  |  |
| --- | --- | --- | --- |
| Reporting Period | Period Start Date (MM/DD/YYYY) | Period End Date (MM/DD/YYYY) | Report Due (MM/DD/YYYY) |
| Quarter 1 |  |  |  |
| Quarter 2 |  |  |  |
| Quarter 3 |  |  |  |
| Etc. Add rows as needed. |  |  |  |

- Indicator Information – See Appendix A for detailed instructions

Vision Section (Optional)

Vision statement (from the Change Map):

Indicator name (short name for reference purposes):

Indicator use (what performance questions will this help you answer?):

Indicator definition (describe what data are to be collected, define all terms, be specific):

Indicator value type (count, percentage):

Indicator value unit (individuals, kilograms, etc.):

Indicator data source(s) (where the data comes from if collected by a third-party):

Data collection methodology (exactly how data will be collected, recommend an attachment if detailed):

Disaggregate category(ies) (all groups by which the overall number should be broken down):

Reporting frequency (quarterly, annually, end of project, etc.):

Known data limitations (any missingness, biases, or other problems):

Level of effort for collection and analysis (high, medium, or low):

Indicator Table:

Set reporting periods (top row) according to reporting schedule above and indicator reporting frequency.  If there are many reporting periods, create multiple tables.  Fill in disaggregation categories and values, adding or removing rows as necessary.  Fill in overall baseline value and overall targets for each reporting period.  Gray cells are to be completed when reporting begins. See Appendix A for an example.

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA |  |  |  |  |
|  | Overall Result |  |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-1 Result |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-2 Result |  |  |  |  |  |
| Disag. Category 2 | Disag. Value 2-1 Result |  |  |  |  |  |
| Add rows as needed… |  |  |  |  |  |  |

Main Project Section

Goal 1

Goal statement (from the Change Map):

Indicator name (short name for reference purposes):

Indicator use (what performance questions will this help you answer?):

Indicator definition (describe what data are to be collected, define all terms, be specific):

Indicator value type (count, percentage):

Indicator value unit (individuals, kilograms, etc.):

Indicator data source(s) (where the data comes from if collected by a third-party):

Data collection methodology (exactly how data will be collected, recommend an attachment if detailed):

Disaggregate category(ies) (any groups by which the overall number should be broken down):

Reporting frequency (quarterly, annually, end of project, etc.):

Known data limitations (any missingness, biases, or other problems):

Level of effort for collection and analysis (high, medium, or low):

Indicator Table:

Set reporting periods (top row) according to reporting schedule above and indicator reporting frequency.  If there are many reporting periods, create multiple tables.  Fill in disaggregation categories and values, adding or removing rows as necessary.  Fill in overall baseline value and overall targets for each reporting period.  Gray cells are to be completed when reporting begins.  See Appendix A for an example.

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA |  |  |  |  |
|  | Overall Result |  |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-1 Result |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-2 Result |  |  |  |  |  |
| Disag. Category 2 | Disag. Value 2-1 Result |  |  |  |  |  |
| Add rows as needed… |  |  |  |  |  |  |

Objective 1.1

Objective statement (from the Change Map):

Indicator name (short name for reference purposes):

Indicator use (what performance questions will this help you answer?):

Indicator definition (describe what data are to be collected, define all terms, be specific):

Indicator value type (count, percentage):

Indicator value unit (individuals, kilograms, etc.):

Indicator data source(s) (where the data comes from if collected by a third-party):

Data collection methodology (exactly how data will be collected, recommend an attachment if detailed):

Disaggregate category(ies) (any groups by which the overall number should be broken down):

Reporting frequency (quarterly, annually, end of project, etc.):

Known data limitations (any missingness, biases, or other problems):

Level of effort for collection and analysis (high, medium, or low):

Indicator Table:

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA |  |  |  |  |
|  | Overall Result |  |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-1 Result |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-2 Result |  |  |  |  |  |
| Disag. Category 2 | Disag. Value 2-1 Result |  |  |  |  |  |
| Add rows as needed… |  |  |  |  |  |  |

Sub-Objective 1.11

Sub-objective statement (from the Change Map):

Indicator name (short name for reference purposes):

Indicator use (what performance questions will this help you answer?):

Indicator definition (describe what data are to be collected, define all terms, be specific):

Indicator value type (count, percentage):

Indicator value unit (individuals, kilograms, etc.):

Indicator data source(s) (where the data comes from if collected by a third-party):

Data collection methodology (exactly how data will be collected, recommend an attachment if detailed):

Disaggregate category(ies) (any groups by which the overall number should be broken down):

Reporting frequency (quarterly, annually, end of project, etc.):

Known data limitations (any missingness, biases, or other problems):

Level of effort for collection and analysis (high, medium, or low):

Indicator Table:

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA |  |  |  |  |
|  | Overall Result |  |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-1 Result |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-2 Result |  |  |  |  |  |
| Disag. Category 2 | Disag. Value 2-1 Result |  |  |  |  |  |
| Add rows as needed… |  |  |  |  |  |  |

Activity 1.111

Activity statement (from the Change Map):

Indicator name (short name for reference purposes):

Indicator use (what performance questions will this help you answer?):

Indicator definition (describe what data are to be collected, define all terms, be specific):

Indicator value type (count, percentage):

Indicator value unit (individuals, kilograms, etc.):

Indicator data source(s) (where the data comes from if collected by a third-party):

Data collection methodology (exactly how data will be collected, recommend an attachment if detailed):

Disaggregate category(ies) (any groups by which the overall number should be broken down):

Reporting frequency (quarterly, annually, end of project, etc.):

Known data limitations (any missingness, biases, or other problems):

Level of effort for collection and analysis (high, medium, or low):

Indicator Table:

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA |  |  |  |  |
|  | Overall Result |  |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-1 Result |  |  |  |  |  |
| Disag. Category 1 | Disag. Value 1-2 Result |  |  |  |  |  |
| Disag. Category 2 | Disag. Value 2-1 Result |  |  |  |  |  |
| Add rows as needed… |  |  |  |  |  |  |

Repeat as needed for all indicators

APPENDIX A:  Terms and Definitions

Goal/Objective/Activity Statement: Should mirror the statement of the associated goal/objective/activity in the Change Map.  For FY22, the only requirements are that there be 1) at least one outcome indicator, associated with a main project goal; and 2) at least one outcome indicator for which progress is expected at least every six months.  These may be the same indicator.  Beyond that, collect data you will use and no more.

##### Indicator name: A short name used to refer to the indicator on documents or in conversation. May contain numbers.

##### Indicator use: A brief note about the purpose of collecting data for this indicator. In what way(s) will it contribute to your understanding of project performance?

##### Indicator definition:

- Describe what data are to be collected

- Define all potentially subjective terms in the indicator (e.g., what specifically counts as being “trained” or not for purposes of this indicator)

- Define all technical terms so non- subject matter experts can understand

- Clarify how frequently the subject of the indicator should be counted (e.g., count each person once even if they receive multiple interventions, or count each instance of the intervention)

- Clarify any minimum or maximum values or scales that are relevant for this indicator

##### Indicator value unit:  For counts, state what is being counted (people, hours, dollars, etc.).  For percentages, state what is in the numerator and the denominator.

##### Indicator data sources:  Specify whether data will be a) newly created primary data; or b) derived from third-party sources.  If data are derived from one or more third-party sources, specify the source(s).

Data collection tools should be easy to use for both the participant and the person responsible for analyzing the data.  Suggested primary data collection tools include, but are not limited to:

- Pre- and post-tests

- Community surveys

- Meeting minutes

- Attendance sheets

- Site visit checklists

- Key informant interviews

- Direct observation

- Focus groups

Examples of third-party data sources include, but are not limited to:

- Host country government reports/data

- UN, World Bank, and other relevant data

- Document review (reports, studies, evaluations of similar programs, etc.

- Official government records

- IResults (limited to Western Hemisphere region)

##### Data collection methodology:  Explain in detail how data will be collected (or was collected, in the case of third-party sources), and by whom.  If survey data, specify the question that will be asked, including response options. (You may wish to attach an appendix specifying overall survey methodology, including target population, sampling plan, interview mode, etc.) If a checklist will be used, include all items in the checklist.  Etc.

Disaggregate Category(ies): To disaggregate data means to break something down by subgroups. It is important to consider only the information that you need to know, as there are infinite ways to disaggregate information. Note that all people-level indicators must be disaggregated by gender. Bureaus, offices, and posts are encouraged to limit disaggregates to what is absolutely necessary for monitoring progress toward goals and objectives.

Known data limitations:  Describe any known or anticipated problems with the data in terms of feasibility of collection, completeness, bias, etc. Describe how the problems would affect the conclusions that could be drawn from the data, and the extent to which it is possible to mitigate the problems.

Level of effort for collection and analysis:  Specify whether the level of effort needed to collect, organize, clean, and analyze the data will be a) High; b) Medium; or c) Low

Indicator Table:

Set target periods according to reporting schedule defined on page one; disaggregate categories and values in the example below are illustrative.  Create more tables as needed to include all reporting periods.  Baseline and target values (I.e., the numbers) should be entered in the blank white cells.  Gray cells are to be completed when reporting begins.  Numbers and reporting periods included here for illustrative purposes.

Note: More disaggregates are not necessarily better.  Many are included here for demonstration purposes.

|  |  | Baseline Value | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA | 100 | 100 | 110 | 125 |
|  | Overall Result | 100 |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Gender | Men |  |  |  |  |  |
| Gender | Women |  |  |  |  |  |
| Age | 18-35 |  |  |  |  |  |
| Age | 36-50 |  |  |  |  |  |
| Age | 51-65 |  |  |  |  |  |
| Age | 66+ |  |  |  |  |  |
| State | Chiapas |  |  |  |  |  |
| State | Tamaulipas |  |  |  |  |  |
| State | Zacatecas |  |  |  |  |  |
| State | Oaxaca |  |  |  |  |  |
| State-Gender | Chiapas -Women |  |  |  |  |  |
| State-Gender | Tamaulipas -Women |  |  |  |  |  |
| State-Gender | Zacatecas -Women |  |  |  |  |  |
| State-Gender | Oaxaca-Women |  |  |  |  |  |
| State-Gender | Chiapas-Men |  |  |  |  |  |
| State-Gender | Tamaulipas-Men |  |  |  |  |  |
| State-Gender | Zacatecas-Men |  |  |  |  |  |
| State-Gender | Oaxaca-Men |  |  |  |  |  |

|  |  | Baseline Value | Q5 | Q6 | Q7 | Q8 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Overall Target | NA | 140 | 160 | 180 | 200 |
|  | Overall Result | 100 |  |  |  |  |
| Disaggregations (Results only) |  |  |  |  |  |  |
| Gender | Men |  |  |  |  |  |
| Gender | Women |  |  |  |  |  |
| Age | 18-35 |  |  |  |  |  |
| Age | 36-50 |  |  |  |  |  |
| Age | 51-65 |  |  |  |  |  |
| Age | 66+ |  |  |  |  |  |
| State | Chiapas |  |  |  |  |  |
| State | Tamaulipas |  |  |  |  |  |
| State | Zacatecas |  |  |  |  |  |
| State | Oaxaca |  |  |  |  |  |
| State-Gender | Chiapas -Women |  |  |  |  |  |
| State-Gender | Tamaulipas -Women |  |  |  |  |  |
| State-Gender | Zacatecas -Women |  |  |  |  |  |
| State-Gender | Oaxaca-Women |  |  |  |  |  |
| State-Gender | Chiapas-Men |  |  |  |  |  |
| State-Gender | Tamaulipas-Men |  |  |  |  |  |
| State-Gender | Zacatecas-Men |  |  |  |  |  |
| State-Gender | Oaxaca-Men |  |  |  |  |  |

APPENDIX B:  Indicator Work Aid

Introduction:

In FY 22, INL will focus our monitoring efforts on ensuring that all new projects have at least one valid outcome indicator corresponding to a project goal or objective.  An outcome indicator measures whether the expected change described in the associated goal statement occurred.  An indicator that is valid provides information that accurately measures what it claims to measure.

This document provides quick tips on how to design valid outcome indicators, examples of indicators that do and do not meet the outcome and validity criteria, and why valid outcome indicators are crucial for successful performance monitoring.

How to Design Outcome Indicators:

Outcome indicators measure progress toward the effects or changes a project is anticipated to create; they answer the question:  to what extent are we seeing the expected results?  Output indicators, on the other hand, measure a project’s activities and deliverables; they answer the question:  to what extent is the project being implemented according to plan?

In short, outcome indicators measure results while output indicators measure implementation.  Both are valuable for project monitoring, but because monitoring is a costly exercise, we begin by focusing on the types of indicators—outcome indicators—that allow us to answer the most important questions:  are our projects working; are they having the desired effects?

To be sure you have an outcome indicator, first write a project goal that meets the change standard.  That is, write a goal statement that describes what success looks like—an expected result or desired end state of the project.  Then ask:  how will we know if we have achieved the expected result?  What could someone objectively observe that would tell us the extent to which we have achieved the goal?  (Note that while only one outcome indicator associated with a main project goal is required, it is fine to measure progress toward multiple goals and/or objectives.  All are outcomes.)

How to Design Valid Indicators:

A valid indicator:  a) provides information that allows you to draw accurate conclusions—in other words, the thing that is being measured is a good approximation of the concept you want to measure; and b) provides accurate information about the thing it is supposed to measure—in other words, the data matches reality.

The first step in designing a valid indicator is figuring out exactly what you want to measure.  This is often the hardest part!  For designing valid outcome indicators, make sure that the goal you intend to measure meets the clarity standard, in that it defines all concepts in concrete terms.  For example, specify exactly what “improved capacity” should look like.

Once you know exactly what you’re looking for, you can think about how you might measure it.  For example, if “improved capacity” means prosecutors present forensic evidence in court, an indicator that captures the concept you are trying to measure might be the number of relevant cases in which the prosecutor presents forensic evidence.

Finally, consider whether the data that can be gathered for the indicator provides an accurate (or accurate enough) picture of reality.  For example, your country might provide official reports on violent incidents in prisons, but these reports might claim there are very few violent incidents, even though you know violence in prisons to be high.  In this case, an indicator that relied on this reported data would not be valid.    Make sure the plan for measuring the indicator is explicit and detailed so that you know how the data are gathered and what information might be missing or distorted.  If you don’t believe the numbers—or if you don’t know where they come from—then you don’t have a valid indicator.

Tip:  Working through a PIRS will help ensure your indicators meet the validity standard.  For other indicator standards (not required this year), see Appendix C for the Indicator Criteria Checklist.

Examples of Common Mistakes and How to Fix Them:

| Original | Explanation of the Problem | Improvement |
| --- | --- | --- |
| Goal: Increase the capacity of Freedonian corrections officers to confiscate contraband. Indicator: Number of corrections officers who complete the training course | The goal is not stated as an expected result, but instead as an activity of INL or its implementing partner. The indicator does measure an important aspect of training implementation, but because it does not measure an expected result, it is not an outcome indicator. | Solution: Re-write the goal to meet the change standard, then revise the indicator. Goal: Freedonian corrections officials have the knowledge and skills to confiscate contraband. Indicator: Among corrections officers who enroll in the training course, percentage who pass the end-of-course practical skills test, as assessed by the INL Advisor. |
| Goal: Freedonia has the capacity to prosecute multinational cybercrime networks. Indicator: ??? | The goal does not meet the clarity standard, so it is hard to know what to measure. What specifically would success look like? Who should be doing what if the expected results are achieved? Or what could an observer expect to see if the project is successful? | Solution: Clarify the goal, then try again to develop the indicator. Goal: Freedonian prosecutors bring criminal charges against individuals participating in transnational cybercrime networks when provided actionable evidence by U.S. law enforcement. Indicator: Of those for which actionable evidence of criminal conduct is provided by U.S. law enforcement, percentage who are formally charged by Freedonian prosecutors |
| Goal: Freedonian police have increased capacity to disrupt transnational criminal organizations. Indicator: Number of arrests for illicit activities related to transnational organized crime | This is a tricky one! One problem is that the indicator data probably does not provide an accurate reflection of reality because crimes are not generally recorded as “TOC-related.” For example, if a member of a drug cartel kills someone for refusing to pay protection fees, then that would be a clear case of TOC-related crime—but it would be recorded simply as an arrest for homicide, like any other arrest for homicide. The total number of arrests for homicide is not the same as the number of arrests for homicide committed for TOC-related reasons, and there is likely no way to distinguish between TOC-related homicides and other types of homicides, such as those resulting from domestic violence, bar fights, vigilante violence, etc. Another problem is that the goal is unclear. It does not specify what exactly police should have the capacity to do, so you cannot determine whether trends in the number of arrests are a good measure of project success. | Solution 1: Ensure you understand the data collection methodology. If you find that the methodology is a mess, revise the indicator. In this case, it would be helpful to more clearly define the goal as well. If you cannot measure the number of TOC-related arrests, what should you measure? The goal as written does not help answer this question. What would it look like for police to have increased capacity to disrupt TCOs? Given the scope and scale of the project, is the main goal to improve skills among a group of police trainees? To change how a local unit performs on the job? Or do we expect to see broader changes that reflect region- or nation-wide decreases in TCO activity? And if we expect to see decreased TCO activity, what exactly would that look like? Developing valid indicators requires first clarifying goals. For projects that seek to improve capacity through training, see the first example above. The second example provides an outcome and indicator related to decreasing TCO activity, though of course there are many other types of goals under this general umbrella topic. |

Why Valid Outcome Indicators Matter:

Developing valid outcome indicators (and then collecting and analyzing the data) allows for objective assessment of the extent to which a project is achieving its goals.  Where the data show that our projects are working well, we would have strong evidence of our success to share with colleagues and partner institutions; and with Congress and other oversight bodies.  Where the data show that our projects are not working well, we would be able to adjust course and provide strong evidence that we are good stewards of American taxpayer dollars and American national interests.  In both cases, having systematic and objective evidence about what works and what does not puts INL in a position to lead policy discussions in our areas of interest.

APPENDIX C:  Indicator Criteria Checklist

Adapted from USAID Learning Lab’s Selecting Performance Indicators. Available at: https://usaidlearninglab.org/library/selecting-performance-indicators

Specific

# The indicator has concrete and defined terms. # Ask: What does this indicator mean to you? Ensuring all indicators have definitions will help increase reliability.

Valid

# The indicator clearly and adequately measures the result it intends to measure. # Ask: Will the difference in the numbers over time tell me whether the goal, objective, or activity has been achieved?

Useful

# This indicator will be useful for project and/or management decision-making. # Ask: Will I use this data to help me course-correct programming and/or report it to leadership when they ask how my project/program is going?

Timely

# Frequency and timing of indicator data collection will be useful for management decision making. # Ask: When will the data be collected, and when will it be reported to me? Will decisions need to be made before the data arrive? Will the underlying conditions have changed so much by the time the data are reported that the data are no longer useful for understanding the situation on the ground and/or the impacts of the project?

# Reporting of indicator data is unlikely to be delayed. Note: Take the likelihood (and length) of delays into account when answering the questions above.

Measurable

# The data is collectable. # Ask: What is the data collection plan? Could I explain it to someone else? Given what I know about the world, does this seem feasible? Lack of a detailed data collection plan—even for indicators that seem simple—is a red flag.

Disaggregated

# The indicator includes appropriate disaggregates, such as gender, age, and location, that are important for monitoring. # Ask: What are the key groups that I would like to (or am required to) be able to report on? Make sure all these groups are included in the list of disaggregations.