Engineering Information

EDA is required to complete an engineering review for all construction and design projects before making an award.  Form ED-900 and required forms have several questions related to requirements for construction and design applications.  The following outline provides more detailed information on these requirements for the Preliminary Engineering Report (PER) in order to assist applicants in preparing their application.

Preliminary Engineering Report Requirements

A PER must include the following at a minimum to meet EDA’s requirements for an application:

  - Description of Project components –Provide a general description of all project components involved in the project.  Indicate where the project involves the construction of new facilities or the renovation or replacement of existing ones.  Describe each of the project components in terms of dimensions, quantities, capacities, square footage etc.

  - A statement verifying the project components described in the engineering report are consistent with the EDA investment project description that is provided in Section A.2 of Form ED-900.  Note: Engineering reports that describe project components that are inconsistent with the EDA investment project description in Section A.2 of Form ED-900 will not be considered to be valid.

  - Sketches of schematics showing the general layout and location of the existing site conditions and of the project components as well as location of project beneficiary(s) identified in Section B.5 of Form ED-900 that provide economic justification for the project, if any.   Rough dimensions and quantities for major project components should be shown and labeled on the drawings.  Drawings should clearly identify the project components that are being proposed.  Applicants are encouraged to clarify such drawings, for example, through color coding, labeling, and any other methods.

  - A feasibility analysis for the constructability of the project, including a review of the existing conditions and noting particular features, alignments, and events affecting construction of project components.

  - The proposed method of construction.  Indicate whether construction procurement shall be done through competitive bid or other method.  Indicate if any portion of the project is to be done by design/build, construction management at risk, by the applicant’s own forces, or whether a third party construction manager will be used.  If an alternate construction procurement method (other than traditional design/bid/build with sealed competitive bid process) is proposed, a construction services procurement plan must be provided to EDA for approval in accordance with EDA’s regulation at 13 CFR 305.6(a).

  - The number of construction contracts anticipated.  If multiple contracts are proposed, provide a description of the project components included in each contract.  If separate contracts are anticipated for demolition or site work, the budget information cost classification should reflect the estimated costs for these components.  If project phasing is proposed, a project phasing request must be provided to EDA for approval per EDA’s regulation at 13 CFR 305.9(a).

  - A current detailed construction cost estimate for each of the project components, showing quantities, unit prices, and total costs.  Provide a basis for the determination of construction contingencies.

  - If the budget includes costs for real property acquisition, the applicant should include a current fair market value appraisal completed by a certified appraiser for the property to be purchased.

  - A list of all permits required for the proposed project and their current status.  Identify all permits required; include the timeline to obtain the permits and discuss how the permitting relates to the overall project schedule.  If the project crosses a railroad right-of-way or is within a railroad right-of-way, provide an explanation of any permitting or approvals that may be required from the railroad or other authority and the timeframe for obtaining these permits or approvals.

  - An estimated project schedule, including the number of months for each of the following:  (i) design period, (ii) period of time to obtain required permits; (iii) period of time to obtain any required easements of rights-of-way; (iv) solicitation of bids and awarding of contracts, and (v) construction period.