Scope of Work (SOW) (Draft until finalized)

| Applicant Name/Recipient Name | Name of Applicant Organization/Name of Recipient Organization |
| --- | --- |
| NOFO Title/Project Title | U.S.-Armenia Professional Partnership in Journalism (PPJ) |
| Federal Assistance Listing Number | 19.900 |
| Period of Performance | 36 months |
| U.S. Embassy Program Strategic Goals and Objectives | The U.S. Department of State, U.S. Embassy Yerevan announces an open competition for organizations with expertise in journalism education and training to implement the “U.S. - Armenia Professional Partnership in Journalism” program. The goal of the program is to support the Armenian media sector’s overall resilience to disinformation, strengthen professional reporting skills and standards, and cultivate U.S.-Armenian professional partnerships in journalism by instituting an exchange program for Armenian professional journalists and media managers. The exchange program will incorporate a training institute and a fellowship placement for Armenian media professionals in a U.S. media outlet/institution for hands-on learning and relationship-building. The “U.S.-Armenia Professional Partnership in Journalism" program is expected to involve approximately 65-75 broadcast and print journalists, editors, and media managers from Armenia, in a program designed to improve journalism skills through exchanges, a training institute, and month-long fellowship placements. |
| U.S. Embassy Program Background and Description | In recent years, the Armenian media space has seen an increase in the level of disinformation. However, as disinformation and misinformation techniques become increasingly sophisticated, support for modernizing formal journalism education and professional development opportunities for working journalists and media managers has been limited. This initiative was informed by a comprehensive needs assessment of journalism education and training in Armenia, conducted by U.S. Embassy Yerevan via a wide-ranging media stakeholders survey. In this survey, journalists and media managers from Armenia identified the lack of quality training and professional development opportunities as the top challenge faced by them. The needs assessment further revealed exchange programs as the most desired and effective avenue for professional development as perceived by Armenian journalists, media managers, and ecosystem stakeholders. According to the needs assessment, the top requested training topics for professional journalists included combatting mis- and disinformation, fact-checking, conflict reporting, source verification, and media ethics. Furthermore, the top requested training topics for media managers included building sustainable financial models; marketing and digital advertising revenue streams; quality standards in managing media establishments; managing media websites/online platforms (including social media); and newsroom management and strategic planning. |
| Project Location | Armenia |
| Project Goals and Objectives | Projects should be designed to achieve the following: - Objective 1: 15-25 print/online journalists from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency will be required). - Objective 2: 15-25 broadcast journalists from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency will be required). - Objective 3: 8-12 editors from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency preferred, but not required—interpretation to be provided). - Objective 4: 8-12 media managers from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency preferred, but not required—interpretation to be provided). - Objective 5: 15-20 professional development fellowships are offered to the participating Armenian media professionals for month-long work placement/residency in U.S. media organizations/newsrooms (following the primary training program/institute), to study, identify, and design innovative methods for media management and quality content production for their local newsrooms. |
| Objective 1 | U.S. Embassy Policy Objective: 15-25 print/online journalists from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency will be required). Applicant Project Objective 1: Activities To achieve the goals and expected results, the program should include the following: (insert additional activities as needed) - Identify and select program host media outlets which should primarily include medium-market outlets and media institutions. - Develop the criteria for selecting program beneficiaries, including designing a merit-based mechanism for selecting participants for the additional month-long fellowship placements. - Organize pre-departure and on-arrival orientations for exchange program participants; arrange all visa-related and logistical matters for the purposes of the exchange visits (including arranging international travel in compliance with the Fly America Act). - Plan for a portion of the U.S. exchange to occur in Washington, D.C to allow exposure to U.S. government institutions and the American system for checks and balances. Expected Results Specific results could include the following: - XXX - XXX - XXX Performance Indicators: - Number of non-state news outlets assisted by United States Government. - Number of journalists trained and supported. - Percentage increase in key journalistic skills/competencies among beneficiaries upon the conclusion of the program. - Number of collaborative media projects initiated between U.S. and Armenian media institutions/journalists due to the program. - Number of innovative solutions localized by exchange program participants in their local newsrooms. Inputs (resource and time requirements): - XXX - XXX Outputs (actions completed and/or items produced): - XXX - XXX Data should be disaggregated as follows: - XXX - XXX Targets (measurable; quarterly and/or other milestones): - XXX - XXX - XXX Outcomes (results or changes caused by these activities): - XXX - XXX - XXX |
| Objective 2 | U.S. Embassy Policy Objective: 15-25 broadcast journalists from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency will be required). Applicant Project Objective 2: Activities To achieve the goals and expected results, the program should include the following: (insert additional activities as needed) - In collaboration with the Public Diplomacy Section (PDS) of U.S. Embassy Yerevan, design and implement substantive exchange programs of approximately two to three weeks for the above-mentioned beneficiary groups from Armenia. - Facilitate, design, and implement month-long individual fellowship placements in U.S. newsrooms/media institutions for a select cohort of Armenian participating journalists/media managers. - Identify and select program host media outlets which should primarily include medium-market outlets and media institutions. - Develop the criteria for selecting program beneficiaries, including designing a merit-based mechanism for selecting participants for the additional month-long fellowship placements. - Organize pre-departure and on-arrival orientations for exchange program participants; arrange all visa-related and logistical matters for the purposes of the exchange visits (including arranging international travel in compliance with the Fly America Act). - XXX Expected Results Specific results could include the following: - XXX - XXX Performance Indicators: - XXX Inputs (resource and time requirements): - XXX - XXX Outputs (actions completed and/or items produced): - XXX - XXX Data should be disaggregated as follows: - XXX - XXX Targets (measurable; quarterly and/or other milestones): - XXX - XXX Outcomes (results or changes caused by these activities): - XXX - XXX |
| Objective 3 | U.S. Embassy Policy Objective: 8-12 editors from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency preferred, but not required—interpretation to be provided). Applicant Project Objective 3: Activities To achieve the goals and expected results, the program should include the following: (insert additional activities as needed) - Identify and select program host media outlets which should primarily include medium-market outlets and media institutions. - Develop the criteria for selecting program beneficiaries, including designing a merit-based mechanism for selecting participants for the additional month-long fellowship placements. - Organize pre-departure and on-arrival orientations for exchange program participants; arrange all visa-related and logistical matters for the purposes of the exchange visits (including arranging international travel in compliance with the Fly America Act). - Organize simultaneous translation for the training programs designed for editors and media managers from Armenia. Expected Results Specific results could include the following: - XXX - XXX - XXX Performance Indicators: - XXX - XXX Inputs (resource and time requirements): - XXX - XXX Outputs (actions completed and/or items produced): - XXX - XXX Data should be disaggregated as follows: - XXX - XXX Targets (measurable; quarterly and/or other milestones): - XXX - XXX Outcomes (results or changes caused by these activities): - XXX - XXX |
| Objective 4 | U.S. Embassy Policy Objective: 8-12 media managers from Armenia undertake a training program/institute in the United States, with the duration of two to three weeks, to improve their professional skills. (English language proficiency preferred, but not required—interpretation to be provided). Applicant Project Objective 4: Activities To achieve the goals and expected results, the program should include the following: (insert additional activities as needed) - Identify and select program host institutions which should primarily include medium-market outlets and media institutions. - Develop the criteria for selecting program beneficiaries, including designing a merit-based mechanism for selecting participants for the additional month-long fellowship placements. - Organize pre-departure and on-arrival orientations for exchange program participants; arrange all visa-related and logistical matters for the purposes of the exchange visits (including arranging international travel in compliance with the Fly America Act). - Organize simultaneous translation for the training programs designed for editors and media managers from Armenia. - XXX Expected Results Specific results could include the following: - XXX - XXX - XXX Performance Indicators: - XXX - XXX Inputs (resource and time requirements): - XXX - XXX Outputs (actions completed and/or items produced): - XXX - XXX Data should be disaggregated as follows: - XXX - XXX Targets (measurable; quarterly and/or other milestones): - XXX - XXX Outcomes (results or changes caused by these activities): - XXX - XXX |
| Objective 5 | U.S. Embassy Policy Objective: 15-20 professional development fellowships are offered to the participating Armenian media professionals for month-long work placement/residency in U.S. media organizations/newsrooms (following the primary training program/institute), to study, identify, and design innovative methods for media management and quality content production for their local newsrooms. Applicant Project Objective 5: Activities To achieve the goals and expected results, the program should include the following: (insert additional activities as needed) - Identify and select program host media outlets which should primarily include medium-market outlets and media institutions. - Develop the criteria for selecting program beneficiaries, including designing a merit-based mechanism for selecting participants for the additional month-long fellowship placements. - Organize pre-departure and on-arrival orientations for exchange program participants; arrange all visa-related and logistical matters for the purposes of the exchange visits (including arranging international travel in compliance with the Fly America Act). - Provide limited support, including through targeted sub-grants, to enable the localization of the innovative methods developed by fellowship program participants. - XXX Expected Results Specific results could include the following: - XXX - XXX Performance Indicators: - XXX - XXX Inputs (resource and time requirements): - XXX - XXX Outputs (actions completed and/or items produced): - XXX - XXX Data should be disaggregated as follows: - XXX - XXX Targets (measurable; quarterly and/or other milestones): - XXX - XXX Outcomes (results or changes caused by these activities): - XXX - XXX |
| Sustainability | Applicant’s plan for continuing the program beyond the grant period, or the availability of other resources, if applicable. Include ways program activities will ensure sustainability. |