## Sheet1
Background A monitoring and evaluation plan (M&E plan) is a systematic and objective approach or process for monitoring project performance toward its objectives over time. In general, INL prefers M&E plans with a robust set of indicators that measure program progress and impact of the program activities. While it is not necessary to have indicators for every program activity, the indicators should measure the major program activities that will contribute to the advancement of the strategic objectives as laid out in the grant agreement. Each M&E plan should contain specific output- and outcome-based indicators with baselines and targets, data source, and frequency of data collection. However, there is not a standard template for the M&E plan that each DRL grantee must follow (e.g., each objective does not need to have 4 indicators with 2 of those indicators being outcome-focused). INL wants to afford grantees the flexibility to design an M&E plan that is customized to the specifics of the program. INL recognizes that sometimes it may be difficult for grantees to design truly results-oriented M&E plans, but we encourage grantees to develop an M&E plan that is as comprehensive, ambitious and creative as possible. The M&E plan is meant to detail how the outputs and outcomes of program activities will be measured quantitatively. Yet, sometimes the results and impact of a program are more easily conveyed qualitatively. Grantees can describe how program impact will be assessed qualitatively at the end of the M&E plan. INL encourages grantees to provide success stories and anecdotal or other qualitative evidence of program impact in the quarterly progress reports, as well as showing how well the program is meeting the targets set in the M&E plan. Below is one example of how the monitoring and evaluation plan can look.
Program Description Free Democrastan Institute (FDI) will build the capacity of the judicial sector to ensure that the Democrastan citizens, especially detainees and those accused of crimes, are aware of and know how to defend their legal rights. This program has two strategic objectives: (1) to increase capacity of judicial police units, magistrates and court and prison clerks to protect the rights of detainees and prisoners and (2) to ensure that target communities, especially detainees and prisoners, are better informed about their legal rights. The project’s key activities include comprehensive training to judicial police units, magistrates to enhance their skills and knowledge on existing criminal procedure code provisions; management training to court and prison clerks to improve the implementation of the current prison case management system; and planning meetings with and implementing a public awareness campaign to mobilize and sensitize communities on the rights of prisoners and detainees as well as develop and implement an effective prison monitoring system.
Strategic Objective 1: To increase capacity of judicial police units, magistrates and court and prison clerks to protect the rights of detainees and prisoners.
Activity | Indicator | Output/Outcome | Baseline | Target/Benchmark | Data Source | Data Disaggregation | Frequency
Intermediate Results 1: The judicial sector is better equip to protect the rights of detainees and prisoners.
| Ability of overall judicial sector personnel to show due process and protection of the rights of detainees and prisoners. | Outcome | Baseline from needs assessment | FY13: 25% increase above the baseline in judicial sector's ability to protect the rights of detainees and prisoners. FY14: 35% increase above the baseline in judicial sector's ability to protect the rights of detainees and prisoners. | Pre/post-program survey,focus groups and interviews with judicial police units, magistrates, court and prison clerks | By sex, type of judicial sector, and region | Bi-annual and final evaluation
| Detainees and prisoners' level of confidence about the justice system effectively protecting their rights during their detention. | Outcome | Baseline from needs assessment | FY13: 15% increase above the baseline in detainee and prisoners' overall confidence level with the judicial system FY14: 25% increase above the baseline in detainee and prisoners' overall confidence level with the judicial system | Pre/post-program survey, focus groups and interviews with detainees and prisoners | By sex and region | Bi-annual and final evaluation
Conduct training sessions for judicial police unit and magistrates on the rights of detainees and prisoners | Number of Judges and judicial personnel Trained with USG Assistance* | Output | 0 | FY13: 50 police and 10 magistrates trained (15 women) FY14: 50 police units and 30 magistrates (20 women) Cumulative: 100 police units and 40 magistrated trained (35 women) | Program monitoring and reports | By sex and region | Following training event
| Percentage of unlawful detentions made | Outcome | Baseline from needs assessment | FY13: 10% decrease in unlawful detentions from baseline FY14: 20% decrease from baseline | Interviews with participants | By region | Final evaluation
| Number of bail requests granted | Outcome | Baseline from needs assessment | FY13: At least 30% increase in bail request grants that are above the baseline FY14: At least 50% increase in bail request grants that are above the baseline | Interviews with participants | By institution | Final evaluation
Hold office management training to court & prison clerks on how to best practices of office management | Number of courts and prison clerks trained | Output | 0 | FY13: 20 clerks (8 women) trained FY14: 20 (same 20 clerks receives training in FY14) Cumulative: 20 clerks (8 women) trained | Program monitoring and reports | By sex and institution | Quarterly
| Number of USG-assisted courts with improved case management systems* | Output | 0 | FY13: 0 FY14: 6 courts Cumulative: 6 courts | Program monitoring and reports | By region | Quarterly
| Participants data entry skills | Outcome | Baseline from pre-test survey | FY13: Overall, participants show 60% improvement in data entry skills over the baseline FY14: N/A | Pre- and post-test surveys of participants | By institution | Following training event
| Level of knowledge on data management | Outcome | Baseline from pre-test survey | FY13: Overall, participants show 30% knowledge increase on data management above the baseline FY14: N/A | Pre- and post-test surveys of participants |  | Following training event
| Percentage of files available to public upon demand | Outcome | Baseline from needs assessment | FY13: 25% increase above baseline FY14: 40% increase above baseline | Interviews from detainees, court clients and court staff |  | Bi-annual and in final evaluation
Strategic Objective 2: To ensure that target communities, especially detainees and prisoners, are better informed about their legal rights.
Activity | Indicator | Output/Outcome | Baseline | Target/Benchmark | Data Source | Data Disaggregation | Frequency
Intermediate Results 2.1: Detainees and prisoners know their legal rights.
| Level of knowledge from the prisoners and detainees about their rights. | Outcome | Baseline from needs assessment | FY13: NA FY14: 50% increase above the baseline in the prisoners and detainees' knowledge on their rights. | Focus groups and interviews with prisoners and detainees | By sex and region | Project beginning and and final evaluation
| Ability of prisoners and detainees to advocate for their rights when detained. | Outcome | Baseline from needs assessment | FY13: NA FY14: 40% increase above the baseline in the prisoners and detainees' ability to advocate for their rights when detained. | Focus groups and interviews with prisoners and detainees | By sex and region | Project beginning and and final evaluation
Intermediate Results 2.2: The general public are more knowledgeable about the legal rights of detainees and prisoners.
| Level of knowledge from the public about the rights of detainees and prisoners. | Outcome | Baseline from needs assessment | FY13: NA FY14: 35% increase above the baseline in the public's knowledge on the rights of detainees and prisoners. | Public opinion survey at the beginning and the end of the project | By sex and region | Project beginning and and final evaluation
Conduct training sessions for mayors and municipal council members on the rights of detainees and prisoners | Percentage of municipalities represented | Output | 0% | FY13: NA FY14: At least 95% 0f municipalities represented | Program monitoring and reports | By municipality | Quarterly
| Number of participants trained in the rights of detainees and prisoners | Output | 0 | FY13: NA FY14: 50 participants trained (20 women) Cumulative: 50 participants (20 women) | Program monitoring and reports | By sex and municipality | Following training event
| Knowledge of participants on legal rights issues | Outcome | Baseline from pre-test survey | FY13: N/A FY14: Overall, participants show 50% increase in knowledge from the baseline | Pre- and post-test surveys of participants |  | Following training event
| No. of awareness initiatives implemented successfully | Outcome | 0 initiatives | FY13: 2 successful initiatives implemented FY14: 4 successful initiative implemented Cumulative: 6 | Interviews with participating mayors and council members | By municipality | Final evaluation
Convene awareness strategic planning meeting | Quality of strategic plan developed | Outcome | 0% | FY13: NA FY14: 80% of plan elements rated as "high " by community leaders | Interviews with mayors, council members, and community members |  | Following meeting report
| No. of recommendations implemented at the provincial level | Outcome | 0 | FY13: NA FY14: 45% of recommendations in the process of being implemented | Interviews with mayors, council members, and community members |  | Final evaluation
Train prison volunteers in criminal procedure | Number of prison volunteers trained in criminal procedures | Output | 0 | FY13: 60 participants trained (25 women) FY14: 80 participants trained (35 women) Cumulative: 140 participants (60 women) | Program monitoring and reports | By sex and municipality | Following training event
| Participants’ knowledge on criminal procedures | Outcome | Baseline from pre-test survey | FY13: Overall, participants show 50% increase in knowledge from the baseline FY14: Overall, participants show 50 increase in knowledge from the baseline | Pre- and post-test surveys of participants |  | Following training event
| Ability to protect detainees | Outcome | 0% | FY13: NA FY14: 65% of participants use training to provide helpful information to detainees | Interviews with participants and detainees |  | Final Evaluation
* Denotes a Governing Justly and Democratically (GJD) Standard Indicator.
Note on E6: chenky: Targets should be provided for each fiscal year, where relevant.
Note on B8: chenky: These indicators in light gray are higher-order indicators meant to meaure progress towards the program objectives.
Note on B30: chenky: Individuals evaluate terms, such as quality, differently. While in this M&E plan, the term "quality" was not defined, it is important to explain in the M&E plan how these terms will be defined and measured. The term "quality" was included to show just one example of an outcome indicator.