| Saving Mothers, Giving Life - Phase II Plan – Summary of Activities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Focus Areas | Luapula Province Mansa district |  | Luapula Province -Samfya District, Central Province - Kabwe District (Kabwe includes the district and selected health facilities in adjacent districts) | Districts in Southern and Eastern Provinces |  |
| DEMAND - Increased capacity of communities and individuals to reduce maternal and neonatal mortality |  |  |  |  |  |
| Train Safe Motherhood Action Groups on basic interventions to prevent maternal and newborn morbidity and mortality (including HIV, Malaria, birth spacing) | Consolidate |  | Expand in Samfya Start in Kabwe |  |  |
| Organize, monitor and motivate Safe Motherhood Action Groups to sensitize on good health practices, promote good health seeking behavior. | Continuing activity |  | New activity |  |  |
| Support radio messaging for health communication, in coordination with the USAID social behavior change project (IMPACT) | Continuing activity |  | New activity | Coordinate with other partners |  |
| Support community leader outreach activities, in coordination with IMPACT | Continuing activity |  | New activity | Coordinate |  |
| Develop, produce and distribute behavior change communication tools, in coordination with IMPACT | Continuing activity |  | New activity | Coordinate |  |
| ACCESS - Increased capacity of health services to undertake outreach activities, undertake referrals and communicate information |  |  |  |  |  |
| Provide support for vehicle functioning and maintenance | Continuing activity |  | New activity |  |  |
| Provide support for personnel undertaking outreach activities | Continuing activities |  | New activity |  |  |
| Provide talk time for health workers for referrals and mentoring | Continuing activity |  | New activity |  |  |
| Establish a referral network to assure appropriate care at the different health care levels. (In Kabwe this implies upgrading services of selected facilities in contiguous districts that used to refer to Kabwe hospitals) | Continuing activity |  | New activity |  |  |
| Train/mentor Community Health Workers and other health staff to promote safe health practices in the community, such as: the benefits of antenatal care, birth spacing, HIV prevention, malaria prevention, nutrition. birth planning, institutional delivery and post-partum care for the mother and newborn. | Continuing activity with more emphasis of FP, HIV, nutrition and malaria |  | New activity |  |  |
| QUALITY - Increased capacity of health services to provide quality health services |  |  |  |  |  |
| Train/mentor in Emergency Obstetrical and Neonatal care (EmONC - i.e. Comprehensive or Basic EMONC) | Train new personnel |  | Train all personnel |  |  |
| Train/mentor in neonatal resuscitation to reduce neonatal mortality to trainers-of-trainers, and health personnel. | Train new personnel |  | Train all personnel | Support other project training |  |
| Train/mentor in post-partum family planning for trainers and health personnel | Train new personnel |  | Train all personnel | Support other project training |  |
| Train/mentor health workers on integration of HIV –Maternal and Child Health and Family Planning Services | Train all personnel |  | Train all personnel | Support other project training |  |
| Train/mentor district mentors who will provide on-the-job- training at health facilities | Train new personnel |  | Train all personnel |  |  |
| Train/mentor in adequate management of health information systems | Support training of new personnel |  | Support training od new personnel |  |  |
| Coordinate with the USAID Supply Chain Management Project to ensure delivery of essential drugs | Continuing activity |  | New activity |  |  |
| Conduct provincial partners meetings to assure coordination and adequate program implementation | Continuing activity |  | New activity |  |  |
| Provide mentoring and supportive supervision to health workers | Continuing activity |  | New activity |  |  |
| Supervise and monitor | Continuing activity |  | New activity |  |  |
| Undertake field supervision activities and provide resources to support MOH and MCDMCH supervision | Continuing activity |  | New activity |  |  |
| Hire provincial coordinators ( these will be hired by the new health system strengthening project but will support MNCH project ) | (will support Mansa and Sanfya) |  | (will support Kabwe and adjacent District health services) |  |
| Hire provincial coordinators (none for these districts) | -- |  | --- |  |
| Hire data clerks to assure adequate SMGL data reporting and analysis | Continuing activity |  | New activity |  |
| Hire midwifes (3 per district) as mentors and ensure that they will then be absorbed by the MOH | Continuing activity |  | New activity |  |
| Integrate MNCH services to FP, HIV and malaria services particularly to assure post-partum family planning, FP counseling, HIV counseling and testing, PMTCT, early infant diagnosis of HIV, and malaria prevention | Continuing activity but more emphasis on FP, HIV and malaria |  | New activity |  |
| SYSTEM STRENGTHENING - Improved health infrastructure, equipment, drugs and support for community health groups |  |  |  |  |
| Provide equipment for appropriate deliveries and surgeries. Activity to be undertaken in coordination with Project CURE that sends donated equipment |  | Complete activity | New activity |  |
| Coordinate with National Blood Bank on safe blood supply |  | Continuing activity | New activity |  |
| Refurbish Health facilities and staff housing Activity to be promoted or undertaken by other projects or donors with community participaton |  | --- | --- |  |
| Construct or maternal waiting shelters. Activity to be undertaken in coordination with other projects or donors with community participation |  | Expand to other services | New activity |  |
| Provide basic equipment for Safe Motherhood Action Groups conforming to standards already set forth in other districts |  | Expand to other communities | New activity |  |
| System Strengthening - Adequate monitoring and evaluation |  |  |  |  |
| Undertake an end of project survey to measure project impact in four original districts- to be defined in year 2015 and depending on availability of funds |  | End or project activity |  |  |
| Conduct facility assessments (completed) and training needs assessment (as needed) |  | --- | --- |  |
| Conduct maternal and neonatal mortality reviews and active surveillance of pregnant women |  | Continuing activity | New activity |  |
| Conduct routine collection of health data through the regular health information system using manual and electronic SmartCare (where available) to evaluate project interventions and track indicators. (Work to be undertaken in coordination with other partners) |  | Continuing activity | New activity |  |
| Facility monitoring on specific HIV, maternal and newborn health indicators |  | Continuing activity | New activity |  |