Annex A

Logical framework

Maternal Newborn and Child Health Project

| Narrative Summary | Illustrative Indicators | Data Sources | Assumptions |
| --- | --- | --- | --- |
| Goal: Maternal Mortality and Newborn Mortality reduced by 50% (Overall SMGL Goal) | Maternal Mortality Ratio decreased by at least 35% Newborn Mortality Rate decreased by at least 35% | Baseline/Health facility Assessments Health facility delivery registers District HMIS | GRZ, Ministry of Health, MCDMCH remains committed to strengthening MNCH activities |
| Activity Purpose; Maternal Mortality and Newborn Mortality reduced by 35% | Maternal Mortality Ratio decreased by at least 35% Newborn Mortality Rate decreased by at least 35% | District HMIS Facility Reports Health facility delivery Registers | The different levels of the ministry; the province, the district and the facilities themselves are committed and have ownership of the programs |
| - Increase institutional deliveries | Institutional deliveries increased by 20% | Health facility delivery registers, Facility HMIS District HMIS | All necessary interventions are in place, are supported by the GOZ and are sustainable |
| Intermittent Result 1.1 Outputs Barriers for women to access institutional deliveries at the facility decreased Strengthened quality of care and services Strengthened Maternal Death surveillance Response activities | - Facility assessment using the standardized SMGL tool in all intervention districts to capture baseline data for each district conducted - Facility-based delivery increased by 35% - Access to Essential New Born Care increased by 20% - Maternal Death Surveillance Response activities in the districts strengthened | Health facility assessment reports Health facility delivery Registers HMIS MDSR reports Project reports | GRZ, Ministry of Health, MCDMCH remains committed to strengthening MNCH activities Other USG health projects and relevant Non - USG partners are willing to work in partnership to coordinate MNCH activities in the targeted districts |
| Intermittent Result 1.1 Inputs Project Work plans approved Health care providers available at the health facilities Health facility assessments conducted Relevant stakeholders trained in MDSR Transport and communication services strengthened | # of health facilities assessed # of health care providers available to provide services Proportion of health facilities refurbished increased by 50% # of MDSR meetings supported | HFA Report Training reports Project reports |  |
| Intermittent Result 1.2: Outputs Demand in communities for ANC, institutional delivery and PNC increased Access to quality maternal and child health services increased | - # of SMAGS providing sensitization on good health seeking behavior and promoting delivery in the health facility increased by 20% - # SMAG members trained in life saving skills increased by 20% | Facility reports Training reports | Community involvement established SMAG training curriculum standardized |
| Intermittent Result 1.2: Inputs Community structures and networks identified and engaged | #of community health workers available for training in SMAGS # community sensitization and community mobilization meetings held | Training reports Meeting minutes | District and facilities committed to supporting community involvement. Interventions supported by community and religious leaders Communities engaged on the interventions at the health facilities |
| - Improve Quality of care of mothers and newborns | Met need for EMONC services increased by 20% | Facility registers Project reports | MCDMCH continues to support scale up of EMONC services |
| Intermittent Result 2.1: Outputs Health systems providing quality institutional delivery services strengthened. | - # of facilities with at least one trained health provider in EMONC/BEMONC. - Proportion of facilities providing at least 4 EMONC signal functions - Proportion of designated basic and comprehensive EmONC facilities performing all signal functions EmONC services increased by 50% - Proportion of facilities providing Misoprostol for management of postpartum hemorrhage at community level increased by 20% - Proportion of facilities offering partum family planning services (PPIUD) increased by 20% - # of health facilities with SMAGs affiliated increased by 50% | Facility reports Project reports | MCDMCH commitment and ownership of the programs |
| Intermittent Result 2.1: Inputs Quality of antenatal, labor and delivery and postnatal care services improved. Scale up of EMONC services Necessary equipment and supplies procured Health care providers available Community health workers identified Technical support and supervision, mentorship provided by ministry, province, district and project staff | # of health facilities providing EMONC services # of facilities supplied with equipment and supplies # of health care providers available for training in the different intervention areas # of mentorship visits conducted #of health care facilities with community health workers | Facility reports Project reports Training reports Facility meeting minutes | MCDMCH technical staff and project technical staff available for provision of technical support and supervision |
| Intermittent Result 2.2 Outputs: Capacity of health care providers built. Provincial, district, health facility skills assessment conducted | - Provincial, district and facility managers oriented to provide supervision and mentorship in EMONC/HBB, Postpartum Family Planning (PPIUD), prevention of post-partum hemorrhage at community level and Maternal Death Response Surveillance increased by 50% - At least 1 health care provider in trained in EMONC/HBB per facility in the intervention districts - Health care providers trained in the prevention of Postpartum hemorrhage with the use of misoprostol at community level increased by 20% - Health care providers trained in Postpartum Family Planning increased by 20% | Training Reports Facility Reports Project reports | Training is supported by the MCDMCH The logistics management systems for maternal and child health commodities are working and commodities available in the facilities |
| Intermittent Result 2.2 Inputs: Training of health care workers in EMONC,HBB, Postpartum Family planning, Prevention of postpartum hemorrhage using misoprostol and MDSR | # of provincial, district, facility staff managers trained in the different intervention areas for training # of health care providers trained in EMONC/HBB # of health care providers trained in HBB # of health care providers trained in postpartum family planning # of health care providers trained in use of misoprostol at community level for prevention of postpartum hemorrhage # of health care providers trained in MDSR | Training Reports | Trainers are available to conduct trainings Guidelines available Curriculums for the trainings in the different intervention areas standardized |
| 3. Strengthen Health service integration | Proportion of facilities offering an integrated MNCH/HIV package of services increased by 20%. | Health facility reports Project reports | Government supporting and onboard in implementation of integration of activities |
| Result 3 outputs: MNCH/HIV continuum –of- care package strengthened. | # of facilities offering and integrated package of services increased by 50% | Health facility reports Project reports | USG and Non USG PARTNERS collaboration continues |
| Result 3: Inputs Integrated package of care offering a “one stop shop” for all services including PMTCT, HIV care, treatment and support | 90% of facilities offering and/or referring to PMTCT, HIV care, treatment and support services to mothers who deliver in the facility | ANC registers, Delivery registers, | The integrated package of care is standardized. PMTCT, HIV care, treatment and support services are offered at the same health facility |