Momavlis Taoba (Future Generation) Program

U.S. Agency for International Development

Cooperative Agreement AID-114-A-14-00006

AWARD PERIOD:  June 30, 2014 through December 15, 2020

MT extension Y1 Annual Report

Reporting Period: January 2018 – December 2018

Prepared for

USAID/Georgia

United States Agency for International Development

ATTN: Nino Buachidze, AOR

11 George Balanchine St.

Tbilisi 0131

Prepared by

PH International

Project Harmony, Inc.  
5197 Main Street, Unit #6

Waitsfield, VT, 05673

January 30, 2019

This report was produced for review by the United States Agency for International Development. It was prepared by PH International.

Table of Contents

List of Acronyms................................................................................................................................................iv

I.	Overview of the Momavlis Taoba Program	6

II.	Tasks Completed in the Reporting Period	7

1.	Identification of Partner Schools for MT Extension	7

1.1. Selection of partner schools for program activities	7

1.2. Start-up of the communication with partner schools	8

2. Revision and Printing of Supplemental Civic Education Materials	8

2.1. Revision and printing of civics supplemental textbooks	8

2.2. Introduction of toolboxes on civics classroom projects and school civics clubs	9

3. Monitoring the use of civics supplemental textbooks and toolboxes	10

3.1. Visits to schools to observe the use of textbooks and toolboxes	10

4. Teacher Training	11

4.1. Updates to the teacher training program, ToT, core training, additional training	11

5. Coordination with and capacity building of MESCS to play an expanded role in national civic education efforts	13

5.1. The work of the Project Advisory Committee	13

5.2. Support to government civic education policy-making and implementation	13

6. Coordination with, capacity building and activities of Civics Teachers Forum (CETF)	14

6.1. The role of the Civics Teachers Forum in the development of civic education in Georgia	14

6.2. Subgrant in support of relevant CETF programs	18

7. Applied Learning	20

7.1 NGO partners work to promote implementation of the MT program in regions	20

7.2. Equipment Contest for Schools	25

8. Mini-Grants for Students Activities	26

8.1. Education of students, teachers, and communities on mini-grants program	26

8.2. Identification of themes for mini-grants with inputs from schools and communities	26

8.3. Functioning and management of mini-grant program resulting in 60 grants to students and/or student-teacher groups	27

8.4. Monitoring and evaluation of mini-grant component	31

9. Interactive Website and Social Networking	32

9.1 Program websites and social networks	32

10. General/Administrative	32

10.1 Development of promotional materials of the program	32

10.2. Meeting with Media Representatives	32

10.3. Cooperation with Media	33

List of attachments:	35

List of Acronyms

MT – Momavlis Taoba (Future Generation Program)

PH – Project Harmony, Inc (PH International)

MESCS – Ministry of Education, Science, Culture and Sport of Georgia (name of the Ministry of Education and Science after the merger with the Ministry of Culture since July 14, 2018)

MES - Ministry of Education and Science of Georgia (former name of the Ministry before summer 2018)

CETF – Civic Education Teachers’ Forum

CDT – Curriculum Development Team

ToT – Training of Trainers

ERCs – Educational Resource Centers of the Ministry of Education, Science, Culture and Sport of Georgia

Partner NGOs – program’s partner non-Governmental organizations in Tbilisi and other regions

ACETT - Applied Civic Education and Teacher Training Program

MAC - McLain Association for Children

## Overview of the Momavlis Taoba Program

The Momavlis Taoba Program (MT), funded by the United States Agency for International Development (USAID), is implemented by PH International. The program is supported by the Ministry of Education, Science, Culture, and Sport of Georgia. The program aims to 1) promote greater civic engagement of young people; and 2) enhance civil society’s role in promoting transparent and accountable governance at the national and local levels by expanding and institutionalizing secondary school civic education curricula and its practical applications. The program was built on the progress made under ACETT, which worked with civics teachers and students in approximately 30% of schools in Georgia. Through the initial MT award, the program reached another 20% of secondary schools (480 schools) throughout the country. Now, in the MT 3-year extension period, the program works with an additional 10% of secondary schools (230 schools), improving the quality and scope of school-based civic education as a means to positively influencing the knowledge, attitudes, and behaviors of the youth (and, through their example, those of the broader community) as active participants in Georgia’s democratic society. MT introduced additional approaches or variations to promoting applied learning by students in school civics classes, seeking to find the best approach or combination of approaches for maximizing the translation of learning into action. The program included schools in all 11 regions of Georgia: Tbilisi, Adjara, Guria, Imereti, Kakheti, Kvemo Kartli, Mtskheta-Mtianeti, Racha-Lechkhumi, Samegrelo-Zemo Svaneti, Samtskhe-Javakheti and Shida Kartli. PH partnered with regional NGOs to take advantage of their knowledge of regional differences and approaches to mobilizing collaboration among young people, civil society, local authorities, and other stakeholders in ways that increase citizen engagement. PH International worked closely with its Georgian partner, the Center for Training and Consultancy (CTC), to accomplish the objectives of MT.

The MT extension, which is consistent with the scope of the initial MT award, further strengthens and consolidates its major activities and enables PH to accomplish MT results through an integrated set of program activities that include:

(1) selecting and working with 230 schools in Georgia to engage teachers, students and communities as partners in civic education and practice;

(2) updating (as needed) and delivering a modern teacher training course for civics teachers from project schools to assist them in better meeting civics curriculum goals for students;

(3) providing the new 230 schools with four high quality, interactive resources developed under ACETT and updated under MT to supplement and enhance existing, approved civic education textbooks and teaching resources. These resources (textbooks) are: “How Can I Become an Active Citizen”; “Cooperation for Community Benefit”; “Cooperation with Local Government and Media” and “Participation in School’s Self-Governance”;

(4) working with the Civics Teachers Forum and the Ministry of Education and Science (MES) to provide a sustainable system of supportive resources and incentives to civics teachers through an interactive website, peer skills development using professional learning community meetings and model lesson approaches, mentoring, and annual professional recognition awards;

(5) introducing of varied approaches that encourage and support students from participating schools in applying their civics lessons into practice in their schools and communities, as well as local NGO and mini-grant support for teacher and student-created projects;

(6) holding multiple local, regional, and national activities including competitions, civics club fairs and other programs that further stimulate and reward the civic engagement by youth people;

(7) working with MES to stimulate improvement of civic education in all secondary schools throughout the country and to prepare MES for implementing the best practices as demonstrated through USAID civic education programs; and

(8) raising public awareness about the importance of civic education through media and other channels (TV, radio, print media, online sources, and social media).

PH International works closely with its Georgian partner, the Civic Education Teachers Forum (CETF), and regional partner organizations to accomplish the program objectives of MT.  The program is managed from PH International’s Country Office in Tbilisi, with contractual relationships with USAID managed from PH International’s US based headquarters located in Waitsfield, Vermont.

## Tasks Completed in the Reporting Period

## Identification of Partner Schools for MT Extension

### 1.1. Selection of partner schools for program activities

This task is completed.

Based on the school list with student numbers received from MESCS, PH selected the list of new schools in which neither ACETT nor MT have already worked.

As agreed with MESCS, while selecting the schools PH made an emphasis on student numbers in 9th and 10th grades as civics is taught as a mandatory discipline in these grades. PH also took into account the number of students in 6th, 7th and 8th grades (as these students will become part of MT in the upcoming years when they move to grades 9 and 10). Other main criteria for the school selection included readiness from the school administration to cooperate with the program and schools with ethnic minority students.

During the selection process, PH’s partner NGOs contacted school principals in advance to confirm their interest about participating in the program.

As a result of a school selection process, a total of 230 schools, most of which had 15 or more students in both 9th and 10th grades together, were selected. Distribution of “new” schools per regions is as follows:

      - Adjara – 23 schools;

      - Guria – 7 schools;

      - Tbilisi – 38 schools;

      - Imereti – 30 schools;

      - Kakheti – 37 schools;

      - Mtskheta-Mtianeti – 2 schools;

      - Samegrelo- Zemo Svaneti - 32 schools;

      - Samtskhe-Javakheti – 4 schools;

      - Kvemo Kartli – 33 schools;

      - Shida Kartli – 24 schools

Approximately 10% of all schools in the list are schools with ethnic minority students. The main target group of MT are students in grades 9 and 10, as civics is a mandatory class in these grades and is taught in all schools across Georgia. Students from grades 11 and 12 also have an opportunity to become involved in the activities of the program through civics clubs and other applied learning activities.

The final school list was shared with MESCS. MESCS sent letters to selected schools with information about MT and its upcoming activities.

### 1.2. Start-up of the communication with partner schools

This task is completed.

To ensure efficient implementation of MT activities, it was critically important that schools are fully informed about the goals of MT, know the resources it will provide, and realize their own role in the implementation of program activities.

In January-February, 2018, PH prepared agreements with schools that were signed by each partner school principal, civic education teacher(s), regional partner NGO representative and MT representative. Agreements stipulate the roles and responsibilities of all four parties in the process of MT implementation at schools. By signing the agreement, the schools confirmed their commitment to allocate the needed time and resources for the implementation of the program.

In October, 2018, PH prepared and signed amendments to the agreements with those schools, where new civics teacher(s) were appointed at the beginning of the academic year 2018-2019, to ensure that newly appointed civics teachers were aware of their responsibilities in the process of MT implementation.

In the period of February – March, 2018, MT program regional launch events were held by regional partner NGOs in the respective regions. During the launch events, partner NGOs and MT staff introduced the program’s objectives, and presented project activities to the audience. School administration officials, students, local government officials, education resource center representatives and civics teachers took part in the events and learned more about the program activities and concrete results of the civics activities of the youth.

## 2. Revision and Printing of Supplemental Civic Education Materials

### 2.1. Revision and printing of civics supplemental textbooks

This task is completed.

In spring of 2018, MT’s contractor printing company, Publishing House Color LTD, completed printing of MT’s three sets of civics supplemental textbooks: “How to Become an Active Citizen” (for 9th grade), “Cooperation for Social Benefit” (for 10th grade) and “Participation in School Self-Governance” (for 10th grade). The textbooks, each comprising the student book and teacher manual, were printed in Georgian and Azeri. MT didn’t print the textbooks in Armenian as PH had a reserve of sufficient quantities of each of the three sets in the Armenian language, which were printed within an earlier MT framework. These textbooks were created in the framework of ACETT program by civics experts through incorporation of input from MESCS.

The textbooks were delivered to all 230 program partner schools. Each school received 4 copies of teacher manuals from each set. As for student books, they were delivered based on the student numbers in respective grades in each school. The civics supplemental textbooks were received by schools after signing of the handover letters clearly stating the purpose of the textbooks and terms for their use in civics classes. A total of 19,085 textbooks (17,102 Georgian, 1,656 Azeri and 327 Armenian) were received by the schools.

The fourth set of the civics supplemental textbook - “Cooperation with Local Government and Media”, which was initially developed within ACETT and then revised within MT earlier, was updated because of the changes in the local self-governance law. The student textbook and teacher manual were updated by its co-author, local government expert David Losaberidze, and civics expert Nino Gvaramadze in close cooperation with PH. The revised versions were edited by PH-hired editor Rita Baindurashvili. The textbooks (student book and teacher manual) was set up and printed in Georgian by publishing company Cezanne Ltd. In November, the textbooks (student books and teacher manuals) were delivered to MT’s partner schools. A total of 6,379 textbooks (5,551 – student textbooks and 828 – teacher manuals) were received by Georgian-sector schools of MT program.

The revised textbook “Cooperation with Local Government and Media” has been translated and edited by Azeri and Armenian language experts. It will be printed and delivered to MT’s Azeri and Armenian schools in the upcoming period.

Printing of Additional Copies of Textbooks

In the fall of 2018, PH was informed by regional partner NGOs that student numbers in grades 9 and 10 have increased at some partner schools during the new academic year. Hence, civics supplemental textbooks received by these schools in the last academic year were no longer in sufficient quantities. PH printed and delivered additional copies of the textbooks to the respective schools. A total of 939 additional copies of textbooks were delivered to 57 partner schools of the program.

### 2.2. Introduction of toolboxes on civics classroom projects and school civics clubs

This task is completed.

To promote the process of applied learning which is key in civic education, MT designed toolboxes on civics classroom projects – “Instructions for Civics Classroom Projects” and toolboxes on school civics clubs – “Instructions for School Civics Clubs”. These toolboxes are a compilation of instructional cards, each presenting brief information about the essence and steps of a student’s civics project.

The toolboxes were printed in Georgian, Armenian, and Azeri by Fountain Georgian Ltd, a company selected by MT through an open tender.

A total of 15,620 toolboxes (Instructions for School Civics Clubs – 5,336 copies; and Instructions for Civics Classroom – 10,284 copies) were delivered to MT program’s 230 partner schools. MT’s partner Azeri and Armenian schools received Azeri and Armenian versions of the toolboxes.

Each school received 23 copies of toolboxes “Instructions for School Civics Clubs” (20 copies for civics club, 2 - for civics teachers and 1 - for a school library). “Instructions for Civics Classroom Projects” were delivered based on the student numbers in 9th and 10th grades together, plus 2 toolboxes for civics teachers and 1 for a school library.

## 3. Monitoring the use of civics supplemental textbooks and toolboxes

### 3.1. Visits to schools to observe the use of textbooks and toolboxes

This task is in progress and will continue over the upcoming quarter.

MT curriculum development team members (CDT) carried out a total of 69 monitoring visits to program partner schools to observe the use of the program’s civics supplemental textbooks and toolboxes in civics lessons. Of these 69 visits, 61 were carried out in Georgian language schools, 4 in Azeri language schools, and 4 in Armenian language schools.

Monitoring visits took place in the following regions of Georgia: Tbilisi, Shida Kartli, Kvemo Kartli, Samtskhe-Javakheti, Kakheti, Guria, Imereti, Adjara and Samegrelo.

The visits included the observation of the civics lessons by experts and communication of findings with teachers and students to evaluate the strengths and weaknesses of the process, identify the needs, and give recommendations for future improvement and quality of lessons.

According to CDT leader’s report, most of the schools regularly use MT’s civics supplemental textbooks at the civics lessons. Civics teachers positively evaluated MT’s supplemental textbooks and toolboxes which, according to them, effectively promote development of democratic values among the youth. The students are motivated and interested in applying knowledge of civic education gained from MT’s supplemental resources into practice.  The teachers emphasized that MT’s partner NGOs are actively supporting all activities initiated and carried out by the students.

A major problem that was identified during the monitoring visits was that some teachers failed to follow the three-phase lesson plan and did not demonstrate efficient classroom management practices. Teachers received recommendations from experts for improving their lesson planning and classroom management practices, as well as for making assessments of students, depending on the learning outcome to be measured, to trigger their motivation. The monitoring experts recommend more training opportunities for professional development of civics teachers.

## 4. Teacher Training

### 4.1. Updates to the teacher training program, ToT, core training, additional training

This task is in progress and will continue over the upcoming quarter.

In January-February, 2018, MT’s partner CETF, in consultation with PH MT team, updated a core training course, “Teaching Democratic Citizenship”, that was developed under ACETT and then updated during the initial years of MT. The training course was updated by civics experts Nino Beselia and Nino Gvaramadze. Updates to the training program reflect the changes to the national civics curriculum and the teachers’ professional development scheme, respond to the professional development needs of civics teachers, and refer to applicable documents.

The revised course includes the following 4 modules:

Module 1 – Importance of civic education and the role of a school in civic education. This module covers appropriate documents and helps teachers analyze the National Goals of Civic Education, the Civic Education Curriculum, Teacher’s Professional Standards, and the Teacher’s Code of Ethics. The module also covers the critical problem of bullying, its associated risk factors, and its prevention at school and in the community at large;

Module 2 – Interactive teaching in civic education. This module covers the use of interactive teaching methodologies in civic education, introduces teachers to the psychological and pedagogical foundations of interactive teaching, helps teachers understand the importance of critical thinking in civic education, and covers the development of civic education lessons plans and the demonstration and/or presentation of a civic education lesson;

Module 3 – Civic participation and project-based teaching. This module covers the importance of civic participation and analyzes it within the context of school life, introducing the ladder of participation and motivational theories;

Module 4 – Methods and forms of assessment. This module covers the matrix of competencies, introduces the forms of assessment in civic education, and analyzes problems through student assessment.

Training course materials include course manual, course reader, course exercise book, instructions for trainers, and PP presentations of each module.

In close coordination with PH International, CETF has selected six trainers and seven co-trainers to deliver trainings for civics teachers from the program’s partner schools. The training program was translated to Armenian and Azeri. A five-day ToT course was conducted for trainers. ToT course was divided into two parts: 3 days were spent on “Teaching Democratic Citizenship” and 2 days on textbooks and toolbox use trainings.

In March, 2018, CETF started the core training course “Teaching Democratic Citizenship” for MT’s partner civics teachers on a regional basis. The course was conducted in four days either over the weekends or on days in which teachers were not in school.

CETF, in close coordination with the MT team, conducted a total of 18 core training sessions of “Teaching Democratic Citizenship” for civics teachers of MT’s partner schools. From these 18 training sessions, 2 were held in the fourth quarter of MT extension year 1. A total of 312 civics teachers, 71 males and 241 females participated in core training sessions nationwide. Of these 312, 31 were trained in the fourth quarter of MT extension year 1. Training participants included teachers from Armenian and Azeri schools as well. Through this course, teachers learned how to support students’ civics projects. After successfully facilitating such projects, teachers could receive credits within the teachers’ professional development and career advancement scheme.

Beyond this core training course, civics teachers also received 2 days of additional training: a) one focused on the four supplemental textbooks and b) the other focused on the toolboxes. CETF updated training modules on the use of MT’s civics supplemental textbooks and toolboxes in February, 2018. The updated training program materials include the course manual, course reader, instructions for trainers, and presentations.

A total of 18 additional training sessions were conducted with the participation of 299 civics teachers (60 males and 239 females). Of the 299 trained teachers, 86 teachers were trained in the fourth quarter of MT extension year 1.

The feedback of participants on the training was very positive; they evaluated the courses as “very helpful” and “productive.” Teachers also reported that they were more motivated to apply interactive teaching methodologies in civic education. They indicated that the course helped them to become more confident and learn how to use the new tools for enriching the teaching process.

“I think that MT textbooks meet all the requirements and needs of modern civics teaching.  They provide the right instructions to civics teachers about lesson planning, how to focus on the main topic and how to cover teaching techniques.  These textbooks are really valuable for civics teachers.” – said Ketevan Bregadze, civics teacher of Village Rokhi public school (Imereti).

“The training was intensive and very interesting. I have learned new methods of teaching and hope to use these methods during civics classes. I am grateful to the organizers of the trainings for these wonderful days. I have made a lot of good friends. Many thanks to trainers for their productive work.” – said Tamar Intskirveli, civics teacher of Village Askana public school (Guria).

“Such trainings are very important and valuable for civics teachers. We have deepened our knowledge of teaching methods, assessment tools, development of critical thinking, etc.  I will do my best to apply the gained knowledge in my work with students. I very much liked individual and group work, which helped us to improve our skills “– said Nugzar Shamugia, civics teacher of Jumi public school (Samegrelo).

"Many thanks to PH-International and the Civic Education Teachers Forum! These 4 sets of supplemental textbooks and new teaching methods are very interesting. We learned effective ways and approaches of planning and implementing civics club activities. I hope that these new skills will help me to make civics lessons more productive and purposeful.”-said Aita Gurgenyan, civics teacher of Burnasheti Public School (Samtskhe -Javakheti region).

## 5. Coordination with and capacity building of MESCS to play an expanded role in national civic education efforts

### 5.1. The work of the Project Advisory Committee

This task is in progress and will continue over the upcoming quarter.

As part of building a sense of responsibility and ownership for new applied civic education and participatory teaching approaches and to ensure that the strategic oversight of activity is properly coordinated, PH International discussed with the new management of  the Ministry of Education, Science, Culture and Sport of Georgia (MESCS) the need to continue MT Project Advisory Committee meetings. In a response to an official letter submitted to Deputy Minister of MESCS, new members of the MT Advisory Committee were nominated by MESCS.

On December 17, 2018, MT Project Advisory Committee met at the Ministry of Education, Science, Culture, and Sport of Georgia along with the following individuals: Mariam Chikobava, Head of the Pre-School and General Education Development Department of MESCS; Ekaterine Khutsishvili, Deputy Head of the Pre-School and General Education Development Department of MESCS;  Shalva Mekravishvili, civics expert of MESCS; Nino Buachidze, MT AOR of USAID; Berdia Natsvlishvili, Country Director of PH International – Georgia; Marina Ushveridze, MT Chief of Party; Maka Bibileishvili, CETF Executive Director and Nino Gvaramadze, Civics Consultant from Teachers’ Professional Development Center and MT’s Curriculum Development Team Leader.

MT program Chief of Party Marina Ushveridze presented to the members of the Advisory Committee the results of MT program activities carried out for the promotion of civic education at schools. Participants of the meeting discussed upcoming plans and opportunities for future cooperation.

Meeting participants also covered the need for international expertise with MESCS’s curriculum development department staff members. MESCS representatives have mentioned that they will identify most needed areas for international consultancy.

Parties have also agreed that MESCS will suggest topics to be discussed in the groups of civics teachers during the National Fair-Conference of Civics Teachers to be organized in spring, 2019. Such discussions during the national conference will facilitate the smooth introduction of the MESCS’s new national civics curriculum topics to teachers and will help MESCS to receive any needed feedback about the planned new topics.

### 5.2. Support to government civic education policy-making and implementation

This task is in progress and will continue over the upcoming quarter.

School-based civic education in Georgia cannot be developmentally sustainable if the Ministry does not support this subject discipline with its relevant policies and their due implementation.

In a meeting with the Deputy Minister of Education and Science, the need to support School Activities Program of the Ministry was identified. MT further discussed this need with the representative of the General Education Management and Development Department. The School Activities Program is managed by the Ministry and provides funding for school initiatives that aim to create a student-oriented and motivating learning environment in public schools. It aims to support informal education methodologies based on student interests.

The Ministry identified that schools are clearly in need of more guidance in project proposal development as well as in project management and implementation. Ministry representatives stated that the quality of applications which Ministry receives from schools in its School Activities Program is very low.

PH has rich experience of mini-grant administration and through its civic education programs as it has already administered 769 mini-grant projects by the use of www.initiatives.ge online web portal. ACETT and MT programs have built a system of support for mini-grant program applicant schools. MES expressed its interest in learning from this experience and applying this in improving the administration and implementation of its School Activities Program. In preliminary discussions, PH and MES agreed that MT can provide support to the Ministry in the following actions: creation of a web portal for Ministry’s School Activities Program, creation of project development and project management guide for applicant schools, and arrangement of training for Ministry’s Educational Resource Center representatives to prepare them for working with schools that plan to develop projects supported by Ministry’s School Activities Program. Ministry’s staff will be closely involved in the development of the aforementioned resources through the provision of feedback.

MT and Ministry of Education and Science of Georgia discussed a Memorandum of Understanding in support of Ministry’s School Activities Support Program. After MT and Ministry agreed about the type of the support to be provided, the document was sent to Ministry’s Legal Department. Lawyers of the Ministry provided comments on different versions of the Memorandum, and at all stages, these questions were answered by MT and its lawyer.

Meanwhile, Ministry of Culture and Sport was merged with the Ministry of Education and Science of Georgia. The new management of the newly merged Ministry of Education, Science, Culture and Sport of Georgia (MESCS) shall review memorandum and approve it. MT will start provision of the support to MESCS’s School Activities Program as soon as Memorandum is signed by the both parties.

## 6. Coordination with, capacity building and activities of Civics Teachers Forum (CETF)

### 6.1. The role of the Civics Teachers Forum in the development of civic education in Georgia

This task is in progress and will continue over the upcoming quarter.

Civic Education Teacher Forum, which was established with the support of ACETT program in 2013, brings together more than 1,000 members from all regions of Georgia. Through support provided by MT, CETF’s organizational structure was developed and now CETF has regional councils with member teachers from all regions of Georgia (Imereti and Racha regions are represented together). Regional councils are increasingly involved in sharing professional development opportunities with other colleagues in their respective regions.

MT continues to work with CETF, assisting the organization in expanding its activities to more schools, as well as reaching more teachers. With support from MT, CETF will continue to grow and scale up into a self-sustaining association of teachers that can provide recognition for outstanding performance and promote professional development opportunities for teachers. A subaward issued by PH to this organization will enable civics teachers of the newly participating schools to participate in professional development, to connect with experts, and to share experiences with their colleagues.

PH signed a subagreement with CETF in January, 2018 to provide professional development opportunities for civics teachers from the new MT schools, to advocate for the development of the profession, to expand the range of services offered to civic education teachers, and to develop CETF into self-sustainable professional association of teachers.

On February 17, CETF held a meeting for the representatives of its regional councils. The aim of the meeting was to discuss the Forum’s annual plan and identify the tasks for each regional council. Participants of the meeting reviewed organizational issues, functions of the regional councils, and activities planned within MT program.

Volunteer from Brot für die Welt

CETF has a new staff member, Martin Thalhammer, a volunteer from Brot für die Welt.  Martin Thalhammer will contribute to CETF’s organizational development, capacity building, fundraising and networking. He will be also engaged in the process of CETF members’ professional development.

CETF fundraising activities, professional development activities for member teachers

CETF continues its efforts in the diversification of its income streams to ensure its further institutional development. In the reporting period, CETF, in partnership with the Center for Training and Consultancy (CTC), was granted a project by Hedayah – International Center of Excellence for Countering Violent Extremism within the Strengthening Resilience to Violence and Extremism – STRIVE Global – Support of Civil Society Initiatives to prevent/counter Violent Extremism in Central Asia, South Caucasus and Western Balkans (funded by EU). The title of the project is “Towards a culture of peace”. The project started on the 1st of May, 2018, and will last one year. Through these projects, CETF gets a funding in the amount of 30,000 Euros.

As part of the sustainable organizational development, with support of MT, CETF strives to provide its member teachers, who do not receive support from donor-funded programs, with professional development opportunities and services. CETF launched an online support program, "Forum for Professional Growth," to help civics teachers prepare for teacher certification exams. The program provides civics teachers with a free and efficient online professional development opportunity:

- On a weekly basis, teachers are provided with resources/readings to prepare for the teacher certification exam;

- Before receiving new materials, teachers have to take a test to prove that they have already covered previous materials;

- At the end of the online course, CETF will organize a meeting for the course participant teachers and will provide them with more information before they take part in teacher certification exams.

A total of 145 teachers participated in the program.

CETF encourages teachers to participate in meetings on innovative and interactive teaching methodology. These meetings help teachers learn more about efficient pedagogical methods in civics, and at the same time, by the use of these methods, gain credits in the teacher’s career advancement scheme. In the reporting period, by the use of the funds raised from membership fees, CETF has organized 2 such meetings on project-based teaching in civic education for teachers, one in Kakheti and one Samtske-Javakheti. Thirty-five civics teachers, including teachers from MT, participated in these meetings.

With MT support, CETF hired an expert that developed a set of civics lesson plans, which will be a supportive educational resource to help civics teachers effectively plan and conduct the teaching process. The lesson plans are consistent with the objectives and specific subject indicators of the National Curriculum. A total of 15 lesson plans on five different topics were developed. Each topic includes 3 lesson plans that are based on the National Curriculum.

In March, 2018, by the use of the funds raised from membership fees, CETF organized 5 meetings with the participation of 61 civics teachers in Tbilisi, Adjara, Imereti, and Samtske-Javakheti. The meetings focused on developing critical thinking, creativity, and communication skills in students through project-based teaching. During these meetings, an emphasis was also made on strategies of working with students with special needs. The meetings were organized by CETF regional chairpersons and regional council members.

On September 22-23, within the framework of MT, CETF held an annual meeting for the representatives of its regional councils in Borjomi. Participants of the meeting discussed strategic development plans, up to date achievements, as well as any obstacles in implementation of the planned activities and the ways to overcome challenges. On the second day of the meeting, Ms. Manana Ratiani, representative of Teachers Professional Development Center, joined the meeting to present the new regulations and changes in the Teachers Development and Career Advancement Scheme. Regional Councils ensured that member teachers of CETF receive this important information nationwide.

“The meeting of CETF’s members in Borjomi showed us that changes in the organization's strategic plan shall be made gradually for the sustainable development of the organization. During the meeting, we discussed very important issues and set short-term and long-term goals for the organization. These two days have shown our strengths and weaknesses and the changes we should make to  our action plans.” –  Vladimir Apkazava, Guria Regional Council Chairperson.

First Contacts with Civic Education Organizations in Europe

CETF made efforts to establish cooperation with European civics organizations. CETF established first contacts with two organizations in Poland and Czech Republic: The Centrum Educacji Obywatelskiej and the Centrum Občanského Vzdělávání. CETF plans to cooperate with the organizations with regards to professional exchange and sharing experience in the field of civic education.

NECE – Networking European Citizenship Education

In September, CETF representative Nato Gamtsemlidze attended the Networking European Citizenship Education (NECE) conference in Marseille, France. The conference represents a European initiative on citizenship education that has been managed by the Federal Agency for Civic Education together with seven partners from France. NECE identifies political and societal trends relevant to CE and develops responses to transfer them into practice. The NECE conference is organized by the NECE partners with the support of local organizations. This year's NECE conference in Marseille focused on transnational processes and provided a platform where citizens from more than 40 countries were able to discuss how to reinvent democratic representation and citizenship education – both in terms of countries and disciplines.

CETF applied for membership in the Eastern European Network for Citizenship Education (EENCE), which brings together professionals in the field of Citizenship Education from civil society, the public sector, and research. EENCE was formed within NECE and with an objective to strengthen Citizenship Education within Eastern Europe. CETF project manager Nato Gamtsemlidze received an invitation to participate in the International Conference of the “Bürgerhaushalt” Network for Participatory Budgeting, which was held last November in Berlin.

On December 6, Maka Bibileishvili, CETF Executive Director participated in the conference "Strengthening the Involvement of Civil Society and Youth in the Decision-making Process in Georgia.” The conference was organized by the organization Civitas Georgica.

E-Learning System for Teachers' Professional Growth

On October 1, the Forum launched a project "E-learning System for Teachers' Professional Growth." The project is supported by the Georgian Coalition, Education for All, and is financed by the Gudavadze Foundation.

The project is based on MOODLE technology - a free and open-source learning management system. Teachers are able to make a free online registration for the course and enjoy different services at the desired time. The course includes 11 modules, which are designed for those teachers planning to take subject exams. The modules cover all topics that are included in the Civic Education Program developed by the National Assessment and Examination Center (NAEC). The course includes video seminars related to teaching methods and lesson plans.

CETF member teachers can access the platform on the webpage  http://cetfonline.com/

The program will be beneficial for CETF to raise awareness, as well as to increase the number of members and collection of membership fees.

Training on “Pedagogical Practice Research Methodologies and School Needs Assessment

In September, 2018, with support from MT, CETF developed a new training module "Pedagogical practice research methodologies and school needs assessment" for civics teachers. On October 6-7, Sopo Lobzhanidze, author of the module and lecturer at Ilia State University, conducted a training for civics teachers and CETF regional councils’ chairpersons. Later, in October-December, three more trainings were held in Kakheti, Kutaisi, and Tbilisi led by Nino Chiabrishvili (1 training) and Maka Bibileishvili (2 trainings) for civics teachers.

A total of 96 participants attended the training.

Discussion Meetings for Civics Teachers

In November and December, 2018, CETF, in cooperation with the Open Society Foundation, held five discussion meetings for civic education teachers in Tbilisi, Telavi, Akhaltsikhe, Kutaisi, and Batumi. The meetings were held within a project - "Monitoring of EU-Georgia Association Agreement and Association Agenda Implementation by NGO Coalition", implemented by OSGF.

Topics of discussion included: EU Association Agreement agenda; prevention of discrimination in various groups throughout Georgia; protection of women's rights; children’s rights.

A total of 119 participants attended the meetings.

Working with MES to Improve Civic Education in Georgia

To facilitate policy changes for improved civic education at schools, CETF held discussions with the participation of its member teachers covering MES’s new standard of civic education – “Citizenship.” Teachers discussed the latest changes to the civics curricula and compared them to the recommendations submitted to MES, which were developed by CETF with support of MT for MES in December, 2016. The meetings were held in different regions of Georgia, and a total of 99 teachers participated. CETF developed recommendations on new textbooks for the new subject of social sciences to be taught in grades 3 and 4, “Me and Society.” Recommendations were submitted to the Ministry of Education and Science of Georgia.

### 6.2. Subgrant in support of relevant CETF programs

This task is in progress and will continue over the upcoming quarter.

National Fair-Conference of Civics Teachers

The National Fair-Conference of Civics Teachers was held on June 9, 2018. The Conference aimed to present innovations in the field of civics education, facilitate sharing of the best practices among civics teachers, recognize professional achievements of civics teachers from different regions of Georgia, and facilitate professional interaction between civics experts and teachers in workgroup sessions. A total of 295 participants took part in the National Fair-Conference. The event included an exhibition of civics teachers’ projects and professional accomplishments. Deputy Minister of Education and Science, Lia Gigauri; Head of the Parliamentary Committee on Education and Culture, Mariam Jashi; USAID representatives, representatives from the Ministry of Education and Science of Georgia, and other invited guests visited an exhibition and spoke with teachers about their projects.

Part of the conference was dedicated to the CETF general assembly meeting, where general assembly approved CETF’s financial manual.

During the final part of the conference, participants broke into smaller groups to discuss the following topics:

- The role of media literacy in information sharing, with expert Simon Janashia;

- From Millennium Development Goals to Sustainable Development Goals, with expert Manana Ratiani;

- Reasoning, Argumentation, and Critical Thinking, with expert Revaz Apkhazava;

- Bullying at Schools, with expert David Mezurnishvili.

The best civics teacher of the year award

The award ceremony was held on June 9, 2018, during the Civics Teachers Forum’s National Fair-Conference.

The selection committee reviewed a total of 74 applications received for the Best Civics Teacher of the Year award. Selection committee members included MT Chief of Party, Marina Ushveridze; MT Manager of Regional NGO Network, Tamar Pruidze; MES’s Civics Expert Shalva Mekravishvili; representative of Teachers Professional Development Center, Nino Gvaramadze; CETF former Chairperson, Civics Expert and MES’s representative, Nino Beselia; Assistant Professor at Ilia State University, Nino Chiabrishvili; and CETF Executive Director, Maka Bibileishvili. The committee selected 35 winners from the following categories – the best civics teacher of the region (9 teachers), the most successful teacher (8 teachers), and the best civics club teacher (7 teachers). Eleven more teachers received special prizes for promoting civic education.

Professional Learning Community meetings

In October-November, 2018, in the framework of MT, CETF facilitated a total of 8 Professional Learning Community meetings on “project evaluation methodology while working with students” in Tbilisi, Marneuli, Kutaisi, Zugdidi, Telavi, Gori, Ozurgeti, and Batumi with the participation of partner schools' civics teachers. The meetings were facilitated by CETF Regional Councils’ Chairpersons with support of experts Lia Gigauri, Professor of Tbilisi Open University; Manana Jincharadze, Consultant of the Teachers Professional Development Center; Nino Beselia, Civic Education Expert; and Nino Chiabrishvili, Assistant Professor of Ilia State University.

A total of 132 civics teachers participated in Professional Learning Community meetings nationwide.

Regional Roundtables

In November-December, 2018, CETF organized a total of 8 civics regional roundtables in Ozurgeti, Zugdidi, Tbilisi, Marneuli, Telavi, Gori, Batumi, and Kutaisi. The Roundtables were focused on “Critical Thinking”. The meetings were led by Simon Janashia, an education researcher, and Nino Gvaramadze, civics expert. A total of 189 civics teachers took part in the regional roundtables.

Model lessons

In December, 2018, a total of 8 model lessons led by MT partner schools’ civics teachers were conducted in 8 regions of Georgia – Tbilisi, Imereti, Guria, Samegrelo, Kakheti, Shida Kartli, Kvemo Kartli, and Adjara. A total of 131 civics teachers attended the model lessons nationwide.  Model lessons covered the following topics from MT’s civics supplemental textbooks:

- Discrimination and equality. Everyone is different, everyone is equal;

- Conflict during cooperation;

- The role of students and the opportunities for participation in school self-governance;

- Identification and selection of the partner;

- How to become an active citizen;

- Bullying and discrimination.

## 7. Applied Learning

### 7.1 NGO partners work to promote implementation of the MT program in regions

This task is in progress and will continue over the upcoming quarter.

PH and its regional NGO partners worked to ensure implementation of MT activities in compliance with NGO scope of work, which was approved by the USAID in January, 2018.  All events, meetings and group visits were planned based on students’ interests, and the extent of NGO involvement was limited to logistical support rather than initiation of these events.

On March 16, 2018, PH International organized a workshop for the regional implementing NGO partners. At the workshop, the MT team, together with the representatives of eight regional partner organizations, discussed MT ongoing activities in, challenges to and best practices for stimulating civic engagement of youth. Special emphasis was placed on strategies, based on experience from previous years, which turned out to be successful in stimulating civic engagement of youth. Workshop participants also discussed the updated program reporting system, including technical and contextual issues, an ongoing small grants contest, financial reporting issues and the importance of the program’s media coverage.  An additional session was held with participation of CETF to exchange information about MT activities, which will help teachers accumulate credits within the teachers’ professional development scheme.

In May-June, 2018 MT end-of the semester events were held in 8 regions of Georgia. These events featured presentations on successful projects and initiatives carried out by students and civics teachers during the civic classes and in school-based civics clubs. Students and civics teachers were awarded with certificates for their successful participation in the program. The events were attended by civic education teachers and students, representatives of school administration, local government, NGOs, and educational resource centers.

During the MT extension Y1, NGO partners supported the creation of 230 school-based civics clubs with the participation of 4258 students in total.

During the MT extension Y1, NGO partners supported a total of 629 initiatives implemented by school-based civics clubs to promote civic education among 5,181 beneficiaries. Of these, 2,353 were girls and 2,828 were boys. In addition, , 735 were representatives of national minorities.  (during the 4th quarter of MT extension Y1 numbers are: 254 events for 1,790 beneficiaries). This number includes duplicates, as very often the same students participate in more than one activity during the academic year.

Besides the civics clubs’ initiatives, NGO partners supported the implementation of 418 classroom projects among 2,533 beneficiaries. Of these, 1,089 were girls and 1,444 were boys. Of these, 448 were representatives of national minorities.  (during the 4th quarter of MT extension Y1 numbers are: 349 classroom projects for 1,811 beneficiaries). Events included students’ initiatives to promote healthy lifestyle,  student actions to combat violence against women and bullying, acts of charity, advocacy efforts to improve the environment, cleaning and greening actions by students, student discussions on early marriage, road safety issues, elections, discussions on gender equality and the importance of women’s participation in civic life, , student actions to protect human rights and responsibilities, as well as the celebration of different important dates, such as: Anti-Tobacco day, International Anti-Bullying Day, International Earth Day, World Health Day, International Children’s Day, Georgian Independence Day, NATO and EU days in Georgia,  International Women’s day, World Water Day, World Down Syndrome Day, World Autism Awareness Day, International Day of Peace, International Day of Older Persons, International day for Eradication of Poverty, Girl’s International Day, and 16 Days of Activism Against Gender Based Violence.

During the MT Extension Y1, partner NGOs conducted 102 seminars and trainings on civic education topics for 866 students. This figure contains duplicates. Of the training participants, 508 are girls, 358 are boys and 109 are representatives of national minorities. (during the 4th quarter of MT extension Y1 numbers are: 36 seminars for 209 beneficiaries) Seminars covered the themes of active citizenship, advocacy, gender equality, project proposal writing, bullying prevention, school-based civics club work, first aid assistance, healthy lifestyle, early marriage and violence prevention, leadership and teamwork, identification of community problems, the use of social media in civics work and development of a small video.

During the MT Extension Y1, MT’s NGO partners arranged up to 56 group visits with the participation of 553 students to local non-governmental organizations and media. These visits included 252 girls and 301 boys.  (during the 4th quarter 24 group visits for 75 beneficiaries took place, these figures are included in the overall number for MT extension year 1) Students visited Professional Union Office and Emergency Management Service Office, Women’s Information Center, Georgian Public Broadcaster  Offices, a psychological service office in the Adjara region, Borjomi – Kharagauli National Park in the Samtskhe-Javakheti region, Gori Welfare and Development Center, local Government and Police Office in Kareli and New Technologies and Innovations Center in Gori, Marneuli Radio Station in Kvemo-Kartli region, Tbilisi Court of Appeals, Georgian National Archive Office, Open Society Georgia Foundation and National Parliamentary Library in Tbilisi, Georgian Parliament’s Office in Kutaisi, Police Departments, NATO and  Public Defenders Offices, and local government offices in different municipal centers.

In addition to the group visits, NGO partners facilitated 86 meetings for 1,078 students with expert guests. This number includes 540 girls, 538 boys, and 120 representatives of national minorities. (during the 4th quarter of MT extension Y1 numbers are: 46 meetings for 442 beneficiaries) Students met with local authorities, local NGO officials, doctors, and representatives of Georgian Public Defender’s Office in the  regions of Kakheti and Kvemo-Kartli, lawyers, journalists, migration specialists, famous sportsmen,  local election commission representatives, psychologists, nutrition specialists, World Champions, police department representatives, a successful alumni of civic education program.

With the support of MT’s NGO partners, MT students identified problems in their local communities, addressed local governments and other agencies, and got involved in activities to solve identified problems. Such activities were carried out by school-based civics clubs and/or through civics classroom projects. Initiation and/or participation in civics activities helped students to apply the knowledge gained at civics lessons into practice and engage in activities for community benefit.

The results of such activities include the following:

Adjara

In November 2018, students from Village Zemo Tsinsvla school-based civics club implemented a project on healthy lifestyle, mainly on energy drinks. Students conducted a survey and summarized the results, which showed that the majority of students do not have information on the negative influence of energy drinks on health. Students organized a meeting and presented survey results to their peers, parents, and other invited guests. In parallel, students cooperated with the National Food Agency, which offered a training on leading a healthy lifestyle. Students also participated in a radio show and talked about the risks and negative effects of unhealthy products.

In November, 2018, students of public school #29 from Batumi implemented a classroom project “No to Cannabis and Tobacco.”  Students started with a public survey to determine awareness and general attitude of public about drug use. The results showed that community members are not well aware of the adversarial health effects of cannabis and tobacco. Students met with a representative of the Center for Mental Health and Prevention of Addiction Batumi Branch and police office representatives to get more information on drug laws and regulations. Using the information they received, students prepared informational booklets on drug abuse and announced a slogan contest on drug prevention. The students also plan to organize a marathon together with famous people from their community.

Tbilisi

In December, 2018, students of Tbilisi public school #103 conducted an informational campaign to increase public awareness of road safety. Students concluded that it was necessary to paint a road crossing and set a circle traffic regulating sign for the safety of the students as they walked to school. Students sent a letter to the Transport Department of the Tbilisi Town Hall to get their support. In addition, students invited a representative from Patrol Police to their school to talk about road safety rules; they also prepared posters and organized a street action, calling all drivers and pedestrians to follow road safety rules.

In November, 2018, Students from Tbilisi public school #79 took efforts to help their peers with special needs and rearrange a resource room at the school. Students met with a psychologist and took part in joint entertainment games with their peers. To raise public awareness on the rights and needs of people with special needs, students decided to prepare informational flyers and spread them throughout the community. In addition, students cooperated with local businesses LTD “Sante” and “Technic House”, both of which delivered gifts to the beneficiaries of the Tbilisi Dayhome of Social Therapy (APNSC).

In October, 2018, 10th grade students from Tbilisi public school #48 decided to promote healthy lifestyle and implemented a classroom project “We Choose a Healthy Lifestyle”. Promotion of healthy lifestyle started with the cleaning of the school territory. With the support of school administration, garbage cans and banners are going to be placed.  A culinary competition was conducted at school in order to promote healthy nutrition where not only healthy dishes were prepared, but participants also received advice on importance of healthy eating. 
In order to support the school in its initiative and to promote a healthy lifestyle in the community, the Head of the Nadzaladevi municipality, Irakli Kheladze, and Majoritarian member of Parliament, Tamar Taliashvili, are planning to install fitness devices at the school.

Imereti

In October, 2018, a school-based civics club students of village Kveda Sazano public school #1 organized mock elections at school in which more than 50 students participated.  Students, in cooperation with a civics teacher, organized a meeting with a chairperson of the local election commission and obtained comprehensive information on elections and the importance of voting.

School-based civics club students from the village of Ilemi in the municipality of Zestaponi have generated good practices in solving community problems through the advocacy process and through productive collaboration with different groups. As a result of the advocacy process, students managed to renovate the road leading to the school, as well as fix a small bridge. After this, students decided to address road safety. In cooperation with representatives of the school administration and the local municipality, students painted a road crossing in front of the school and placed an informational banner. “The results of our civics club work make us happy. It is possible to reach success through good cooperation; the best examples are the results of our civics projects,” says Flora Jikhuridze, civics club leader of the village Ilemi public school.

Shida-Kartli

In October, 2018, school-based civics club students of the village Adzvi public school in the municipally of Gori conducted a community survey to determine the level of public awareness of the use of marijuana. The participants of the survey were 30 community members from different age groups. The survey results showed that community members did not have comprehensive information about marijuana’s effects on the brain and overall health, as well as about drug laws and regulations. Students also visited the Shida Kartli police office, where they received comprehensive information about the risks of drug abuse and were informed of the regulations regarding drug control, and storage and selling of substances.  The club members prepared a wall newspaper and booklets informing young people about drug abuse and prevention. The booklets were disseminated among community members.

In November, 2018, 10th grade students of village Kindzati public school in the municipality of Khashuri conducted a survey to determine the quality of food products in nearby grocery shops and found that, in some cases, expired foods were sold.  Using the results of the survey, students prepared presentations about organic products and genetically modified food in order to increase public awareness on healthy food and healthy nutrition. Students organized an exhibition of fruits and vegetables and presented a list of food products that may cause diseases among children. Students also prepared and distributed brochures on healthy nutrition. A "Culinary Duel" where participants prepared dishes from organic products and offered them to the invited guests was held at school to promote proper nutrition.

In November, 2018, school-based civics club students of village Kvemo Gomi public school in the municipality of Kaspi conducted a public survey on bullying and violence. The results of the survey showed that students are informed about bullying and that most of them think that bullying is bad. Nevertheless, some of the students mentioned having bullied others in the past and there are still some cases of bullying at school. For the prevention of bullying, a conference, “No to Bullying, No to Violence!" was held at school. Student’s art and posters were exhibited. The authors of the best works were awarded presents and certificates.

Guria

In October, 2018, students of the village Baileti public school in the municipality of Ozurgeti conducted an informational campaign “Our Four-footed Friends” aimed at animal protection. Students gathered information and prepared presentations. An exhibition of students’ art and slogans was arranged at school, and the best of such projects were exhibited in public places. The meeting and discussion about the protection of animals was held for younger students at school.

In November, 2018, school-based civics club students of village Bokhvauri in the municipality of Ozurgeti initiated the construction of a trail leading to the school toilet in the school yard. This was one of the top priorities of the school. To solve the problem, civics club students advocated for the construction of such facilities and with the support of school administration, as well as through negotiations with regional municipality, received the required construction materials. Parents of students also took part as volunteers in the construction process. In the end, a 30-meter-long trail was constructed in the school yard, signifying a big step in the improvement of the school’s overall infrastructure. “Through the initiative of the civics club students, the long-existing problem was finally solved. We are happy, we did it” – said Lasha Chanishvili, school-based civics club member

Kakheti

In October, 2018, school-based civics club students of villages Atskuri and Qistauri public schools in the municipality of Akhmeta, and the students of public schools from the villages of Chandari and Vejini in the municipality of Gurjaani, conducted an informational campaign to increase public awareness on the importance of elections.  Students organized mock elections at schools, prepared informational flyers about the importance of citizen participation in elections, and disseminated them in their respective communities.

In November, 2018, school-based civics club students of village Gombori public school conducted a survey to identify the level of interest in reading among the peers. They found that many students do not read books. Students decided to enrich the school library and appealed to their local representatives of the Sagarejo municipality and the municipal union of libraries. As a result of this student initiative, the school library received 3,500 books. In order to create a better environment in the library, students renewed book shelves and tables and brought in chairs. To promote reading, a readers' club was established at school, the members of which plan to publish a manuscript magazine.

Kvemo-Kartli

In October, 2018, civics club students of village Algeti public school # 2 in the municipality of Marneuli decided to protect nature. The students organized discussions on how nature is damaged due to deforestation and environmental pollution. In addition, members of the club prepared posters - "Save the Future" and "No to Plastic Bags", organized a cleaning action, and created a Georgian-Azeri bilingual brochure on the issues of environmental protection they later disseminated in the community. Students spoke with the local municipality about the necessity of placing garbage cans in their school.

In November 2018, students of Baidari and Khuldari public schools in the municipality of Marneuli prepared a school wall newspaper on early marriage issues to increase awareness of this issue among their peers. These two Georgian villages are comprised of an Azeri population and the incidence of early marriage is notably high. Students collected information for the wall newspaper and presented topics, such as: Georgian legislation on early marriage, its negative influence on health and on proper education and career. Students will continue the activities for the prevention of early marriage among the youth within their communities in the upcoming school year.

Samegrelo

In November, 2018, Civics Club members of the village Rike public school in the municipality of Zugdidi made efforts to improve road safety. The pedestrian street crossing in front of the school needed a renewal. The students received permission from the school administration, local government, and Zugdidi City Council to paint the pedestrian street crossing. The members of the club hope that the renewed and painted pedestrian street crossing will be helpful for citizens in following traffic rules and that it will support road safety.

In November, 2018, school-based civics club students of village Khamiskhuri in the municipality of Khobi decided to solve some of the environmental problems of their community. In cooperation with the school administration and parents, students organized a cleaning action on school grounds and in the center of the village. The local municipality provided the students with plastic bags, gloves, and transportation of waste. Students and representatives of the local administration agreed that additional trash cans would be placed in the village and that timely transportation of waste would be provided. Students are planning to continue informational campaigns to increase public awareness of waste management issues.

### 7.2. Equipment Contest for Schools

This task is in progress and will continue over the upcoming quarter.

In October, MT announced equipment contests for program’s partner schools and civics teachers. The contests aim to recognize the work of the most successful partner schools and civics teachers and award them with equipment (laptops for schools and tablets for civics teachers) to support implementation of their civics activities in the future.

The equipment contest was announced through MT’s social networks and webpage - www.civics.ge. Application forms were also distributed by PH’s regional partner NGOs to schools.

By the set deadline, December 20, a total of 149 applications (80 applications from schools and 69 from civics teachers) were received. Applications will be first assessed by MT’s regional partner organization representatives, who will review and recommend the best schools and teachers for awards. Along with recommendations, NGO partners will provide arguments and facts about successes and activities carried out by recommended schools and teachers. At the second stage, applications will be examined and assessed by the MT selection committee and representatives of NGO partners together. The final candidates will be confirmed and awarded in January.

Successful applicants will be awarded in the upcoming quarter.

## 8. Mini-Grants for Students Activities

### 8.1. Education of students, teachers, and communities on mini-grants program

This task is in progress and will continue in the next quarter.

As agreed with the USAID, during the MT extension Y1 mini-grant competitions for 230 partner schools were announced three times.

Regional NGO partners provided all interested and eligible applicants with consultations. Schools received information about the program and its purpose, gained skills needed to develop the project proposal and budget, learned how to describe proposed activities in an action plan, and mastered how to pull together and document matching resources. Partner NGOs informed the students, teachers, and school administration officials about the deadlines, application procedures, and provided technical help whenever needed. There were total of 89 open days, 44 training sessions, and 203 group and individual consultations with participation of 1950 beneficiaries held for applicants of the mini-grants program. This number of beneficiaries includes 1202 females, 748 males, and 129 ethnic minorities.

During its first year of MT program extension, PH International received 503 applications for mini-grant proposals from students, teachers, and school administration officials through www.initiatives.ge.

### 8.2. Identification of themes for mini-grants with inputs from schools and communities

This task is in progress and will continue in the next quarter.

The identification of thematic areas for the first call for mini-grant proposals (for civics clubs and classroom projects) took place in January, 2018, the themes for mini-grant proposals for second call (for classroom projects) were selected in August, 2018, and the themes for third call of mini-grant proposals (for classroom projects) took place in October, 2018. In all the three cases, the themes for mini-grants were identified in consultation with students via regional partner NGOs based on the needs of local schools and communities. Mini-grants covered civic participation by youth as well as efforts to educate youth about civics issues and involve peers in important initiatives for their schools and communities.

The selected themes for mini-grants competitions included the following:

- Prevention of bullying;

- Student initiatives to improve school environment;

- Promotion of integration of persons with disabilities in local communities;

- Promotion of healthy lifestyle;

- Solving/advocating for ecological problems;

- Promotion of integration of different vulnerable groups (ethnic minorities, children in the streets, elders, IDPs and others);

- Collaboration of youth with local government, media, private, and NGO sectors to solve school and community problems;

- Promotion of voluntarism in society;

- Prevention of human trafficking;

- Prevention of violence (especially violence towards women, violence in families, and other forms of violence);

- Supporting public education on elections;

- Strengthening of students-self-government;

- Prevention of early marriage;

- Promotion of gender equality;

- Promotion of cultural sightseeing and historical heritage to support development of tourism in villages and towns;

- Promotion of literacy among youth;

- Supporting the youth in social entrepreneurship

- Supporting public education on democracy and democratic governance;

- Increasing public awareness of human rights and citizen responsibilities, and rule of law;

- Supporting education of youth on first aid;

- Supporting public education on healthy food;

- Supporting student initiatives to increase girl’s involvement in civic activities;

- Promotion of social media used by students for solving problems in their communities;

- Supporting professional orientation among youth;

- Collaboration of parents with students and school administration to solve school problems;

- Students’ initiatives to support road safety;

- Supporting public education on Euro-Atlantic integration.

- Societal awareness of labor safety and employers’ rights;

- Student initiatives to implement business ideas;

- Support citizen journalism in students;

- Promotion of integration of people with disabilities into society;

- Support of public knowledge on the constitution;

- Student awareness of media-literacy;

- Student initiatives for the prevention of crime among youth;

- Support of public education on the risks of GMO products.

### 8.3. Functioning and management of mini-grant program resulting in 60 grants to students and/or student-teacher groups

This task is in progress and will continue over the upcoming quarter.

Funding decisions for the first round of applications were made in March, 2018 and 17 civics club projects were selected. Seventeen classroom projects were selected in November, 2018 as a result of the second round of mini-grants competition. In February 2019, PH International will announce the 22 classroom project winners, as a result of the next mini-grants competition. As in the previous two cases, decisions will be made by the committee based on the following criteria:

- Application should be related to civics education and should cover one of the announced topics

- Selected theme should respond to the interests and needs of the target groups

- The project should aim to conduct surveys and increase societal awareness on a selected issue

- The planned cooperation of youth with local media, government, business, school administration or other partners to solve the problems of schools or communities will be considered a plus, and the potential of the project for sustainability will also be considered.

- Project results should be clear and measurable

- Applicant should be a representative of a partner school (teacher, student or representative of school administration)

- Grant amount shall not exceed $ 450

- Application should be filled and sent online via www.initiatives.ge with its corresponding appendices (budget, implementation plan, and school administration letter)

- Applications should be submitted no later than the given deadline.

Through the mini-grants program, students, teachers, and school administrations are able to open new channels of communication with local government officials and facilitate decision-making processes from the grassroots level. Such projects positively influence motivation of civics teachers as they are able to get involved in small projects with their students and deliver the results of their work, which brings benefits to their schools and communities. All the 17 mini-grant projects funded in March, 2018 have been completed. The projects funded in November, 2018 are ongoing and will be finalized in spring, 2019.

A total of 542 students were involved in the planning and implementation of the 17 mini-grant projects. Among these students, 318 were girls and 224 were boys. Of these, 176 students were in the 9th grade, 201 were in 10th grade, 118 were in 11th grade, and 47 were in 12th grade. Among these students, there were 151 ethnic Armenian and Azeri students. The beneficiaries of the 17 projects implemented in the first year of MT program extension were 3,922 people in total.

Some examples of ongoing mini-grant projects are:

Adjara

Grant Receiver: Village Chaisubani Public School # 2

Project Title: Say no to early and forced marriage

Project Description: Early marriage is a critical problem in Adjara region. The school students of Chaisubani public school #2 conducted an information campaign to break stereotypes and increase public awareness about the negative influence of early marriage with a mini grant project titled “Say no to early and forced marriage.” Within the information campaign, students organized discussions with a doctor, a psychologist, a public defender and a lawyer. To determine the reasons for and the consequences of early marriage, students interviewed people who got married young.

In addition, the students plan to distribute booklets, organize a photo contest, stage a pantomime performance, and speak about the issue in the local TV and/or radio talk show.

Imereti

Grant Receiver: Village Merjevi Public School

Project Title: Healthy food, GMO products, and hygiene

Project Description: Students of the village Merjevi public school initiated a study on the hygienic conditions in the Sachkhere agrarian-market. They met the market administration to determine key problems, took photos of the hygienic state of the market, and started an advocacy campaign with support of the local government. As a result of students’ efforts, decision-makers promised to place trash bins throughout the market.

In addition, the students surveyed the community and learned that they lacked sufficient information about GMO products. To increase public awareness of the negative impact of GMO products, students cooperated with the local National Food Agency, which organized a training on the potential risks of using GMO products.

Within the mini-grant project students plan to prepare and disseminate booklets and organize an informational meeting on the importance of healthy foods.

Grant Receiver: Village Jalaurta Public School

Project Title: More respect to women

Project Description: Village Jalaurta public school, in the framework of MT program, received a mini-grant to increase public awareness about women’s rights. For this, students first observed community members to determine their attitude towards this issue. They invited a lawyer to discuss the cases in which women’s rights were violated, organized the screening and discussion of four films on the same topic, and met with a successful woman and a Social Agency representative in the municipality. Students also plan to prepare booklets and posters about 10 women that have changed the world.

Kakheti

Grant Receiver: Village Gombori Public School

Project Title: Movie in the open air

Project Description: Civics students of Gombori public school initiated a mini-grant project on human rights. They arranged an area for film screening in the administrative building of the village, as a result of successful cooperation with the local government. In addition, students organized a meeting with a poet to discuss the cases where human rights are frequently violated.

Within the mini-grant project students plan to keep film screenings on different themes which will be identified through community surveys. They will also prepare posters to inform the community about upcoming movies. Time after time, students intend to invite successful people and discuss the films with them. During the summer, films will be screened in the open air in the village.

Guria

Grant Receiver: Village Tskaltsminda Public School

Project Title: Say no to early marriage

Project Description: Tskaltsminda public school students decided to raise public awareness of the negative influence of early marriage through the implementation of the mini-grant project “Say no to early marriage”. The students surveyed community members of different age groups to determine their attitude towards early marriage, as well as the reasons for it and its consequences. According to the survey results, elderly people have the least negative attitude towards early marriages. Students organized a meeting with a doctor and lawyer, visited a local women’s rights organization and discussed the issue with them.

The students plan to prepare information booklets on early marriage and cooperate with local media to broadcast the project’s implementation and its results.  In addition, students are working on a short film, “The Lost Future”, which will be screened in two neighboring villages and shared through social media networks.

Kvemo Kartli

Grant Receiver: Village Baidari Public School

Project Title: We reject unhealthy food

Project Description: The students of the village Baidari public school in the municipality of Marneuli decided to raise the population’s awareness of genetically modified and unhealthy food, all within the framework of a small grant project. The students prepared a questionnaire and conducted a survey that showed that the consumption of unhealthy products at school is practiced more frequently than at home. To address this problem, students planned different activities as part of the campaign “We Say No to Unhealthy Food.” The students prepared the news wallpaper and met with expert and a doctor to discuss the protection of customer rights and other food safety issues. In addition, students prepared brochure about unhealthy and genetically modified foods that was distributed in the village. At the project closing event, students presented in Georgian and Azeri the importance of healthy foods to the audience.

Samegrelo-Zemo Svaneti

Grant Receiver: Village Chkhoria Public School

Project Title: Our village on the touristic map

Project Description: Students of Chkhoria public school, in the municipality of Zugdidi decided to inform wider society on the historical heritage of the village. They visited different places and took photos that were then used in booklets and for the informational banner. To collect information about the village sights, students met with community leaders, tour agencies, and local government representatives.

In addition, students cooperated with the local government to install an informational banner on the main road of the village. To ensure better results, students plan to distribute booklets and albums titled “Sights of my village” among the community members and tour agencies.

Samtskhe-Javakheti

Grant Receiver: Village Benara Public School

Project Title: Future belongs to us

Project Description: Benara public school students, in the framework of mini-grant project, raised the problem of improving the environment of the Otskhe gorge. According to a community survey conducted by students, the ameliorating environmental conditions is important not only for the village of Benara, but also for 5 other neighboring villages. The students started to negotiate with the local government to clean illegal landfills in the river-bed. With the participation of representatives of 5 neighboring villages, school students from the village of Benara organized a cleaning action in the main road of each village.

Grant Receiver: Village Burnasheti Public School

Project Title: Civics club room - A space for implementing youth initiatives

Project Description: Burnasheti school students decided to increase public awareness about human rights. In the framework of the project, students conducted a survey with community members and organized training sessions on human rights. Students also arranged a box at school in which the cases of human rights violation could be collected. By the end of the project, the box will be opened in the presence of a public defender’s representative and a lawyer; these individuals will give a detailed explanation on each case through a local radio. The broadcast will be shared through the social media.

In addition, students are going to prepare a thematic booklet, organize a conference and a flash-mob show. They also plan to renovate a civics club room at the school.

Shida Kartli

Grant Receiver: Village Osiauri Public School

Project Title: Pain told in a book

Project Description: Civics club students of village Osiauri public school implemented a mini-grant project to prevent bullying at school. The students conducted a survey of their school peers to determine the reasons for and cases of bullying. They drafted sketches of violence and bullying with the help of an invited artist and announced an essay contest at the school. Students are planning to meet with a lawyer and with a representative of local Education Resource Center to discuss cases of bullying and ways of preventing it.

Tbilisi

Grant Receiver: Tbilisi Public School #213

Project Title: Road Safety

Project Description: Students of Tbilisi public school # 213 decided to work on road safety issues. The school is located in Tabakhmela. The survey conducted by students showed that road signs are not properly located in Tabakhmela. To address this issue, students planned different activities. 
After discussions on road safety issues with the patrol police representatives at the school meeting, the participants decided that the representatives of patrol police will help students to prepare the information booklets to increase public awareness on road safety and apply to the Tbilisi municipality regarding the installation of proper road signs.

Grant Receiver: Tbilisi # 70 Public School

Project Title: Book – Freedom, reading – pleasure

Project Description: Tbilisi public school #70 students are implementing a project aimed at increasing the level of literacy among the youth. As a result of successful cooperation with school administration, students gained a space for a literature café. Now they are carrying out fund-raising activities to get additional funds for renovating the space. At the same time, the students are collecting scraps with the support of their parents.

In addition, students are planning to identify the favorite books of their peers, meet with writers, and discuss books with them.

### 8.4. Monitoring and evaluation of mini-grant component

This task is in progress and will continue over the upcoming quarter.

Mini-grant allocations were monitored by PH staff. NGO partners had the responsibility of supervising the grant allocation and implementation process in the field.  Monitoring involved visits of MT staff as well as written reports from NGO partners, which included project reports and success stories from grant recipients. MT’s Mini-Grants Coordinator maintained regular contact with NGO partners, attended events and activities carried out by grant recipients, and provided feedback in case the need of changes occurred throughout the grant implementation. MT worked with its NGO partners to ensure support to schools (either in a form of in-kind contributions or cash) for projects from outside sources, such as local governments, businesses, media, etc.

## 9. Interactive Website and Social Networking

### 9.1 Program websites and social networks

Updating of the Program Websites and Social Networks

To support teachers, students and parents with professional resources and materials, MT’s website www.civics.ge was updated regularly during the reporting period. The website included media coverage of many different civics events and activities, and featured TV and Radio programs with the participation of MT beneficiaries and stakeholders on MT’s civic initiatives Facebook page (www.facebook.com.civicinitiatives), as well as on the program’s YouTube channel. It should be noted, that video coverage materials are mostly viewed from Facebook page. Along with civics.ge, MT also operated a web portal of civic initiatives, www.initiatives.ge, which offered applied learning opportunities to students through mini-grants. Photo and video galleries of the program web portals were regularly updated to reflect the news and recent developments. In addition to www.civics.ge and MT’s Facebook page, the news and stories of the MT program were sometimes also published on www.ph-int.org at and USAID Facebook. The stories were linked to the MT’s Facebook http://www.facebook.com/civicinitiatives

During the first year of the MT program extension, www.civics.ge had 6,273 new visitors.  In total, there were 6,379 users on the civics.ge site and 23,267 page views.

MT’s social network, www.facebook.com/civicinitiatives  has 13,614 likes (2104 new likes in the reporting period) of students, parents, and teachers.

## 10. General/Administrative

### 10.1 Development of promotional materials of the program

This task will be in progress in the next reporting period.

During the reporting period, MT program brochure, poster, bookmarks, t-shirts, cups, balloons and plastic bags with program branding were developed and distributed among partners in all regions of Georgia.

### 10.2. Meeting with Media Representatives

This task will be in progress in the next reporting period.

On March 10-11, 2018, a meeting with media representatives was held to inform media about MT activities, results, success stories and future plans. Journalists and producers were able to meet with the Winner of the National Teacher Award 2017, civics teacher Lado Apkhazava and his students to get information about his teaching methods. Member students of the school-based civic club in Chibati presented the results of implemented projects to media representatives. They answered the questions of journalists and involved them in an exercise on democracy; they also spoke about the greenhouse and a sports space arranged with their collaboration.

A total of 25 participants took part in a media seminar and info tour, including representatives from different TV companies – Rustavi 2, Imedi TV, Georgian Public Broadcaster, Ersulovneba, Palitra TV, Radio Palitra, TV Pirveli, Adjara TV/Radio and newspapers. Representatives of MESCS and USAID also participated in the seminar and info tour.

### 10.3. Cooperation with Media

This task will be in progress in the next reporting period.

During the reporting period, news on MT program activities were covered by TV and radio companies, print media, and online resources all across Georgia.

During the first year of the MT program extension, central TV companies covered information about MT activities 14 times, while regional TV companies broadcasted MT news 25 times; 2 articles were published in the newspapers and 9 radio broadcasts were held. An additional 33 instances of online coverage also took place.

In their daily and morning programs, central TV companies organized talk shows and promoted the importance of civic education. To this end, they invited representatives of the Ministry of Education and Science of Georgia, civics experts, students and teachers, and MT program and NGO partner representatives to take part in their programs.

Media coverage, listed below took place during the 4th quarter of MT extension year 1. Information about the media coverage of previous quarters is given in the respective quarterly reports.

TV Coverage

On October 2, 2018, TV Company “Georgia Public Broadcaster” hosted Marina Ushveridze, Chief of Party of the civic education program “Momavlis Taoba,” in its midday program to speak about the importance of teaching civic education at schools.

https://bit.ly/2HemXhX

On October 5, 2018, TV Company “Ertsulovneba“ in its morning program covered “Momavlis Taoba” and the support it provides to schools. Guests of the program were MT staff member Tamar Pruidze and a student of Tbilisi public school #70.

https://bit.ly/2SVXtHp

On October 19, 2018, TV Company, “Guria TV” covered information about Chargé d’affaires Elizabeth Rood visit to village Chibati public school and meeting with students, as well as her visit to  Lanckhuti Museum of Occupation.

https://bit.ly/2svaLPD

On October 19, 2018, TV Company, “Guria TV” covered information about Chargé d’affaires Elizabeth Rood visit to village Chibati public school and meeting with students, as well as her visit to  Lanckhuti Museum of Occupation.

https://bit.ly/2AMCa3X

On October 19, 2018, TV Company, “Guria TV” covered information about Chargé d’affaires Elizabeth Rood visit to village Chibati public school and meeting with students, as well as her visit to  Lanckhuti Museum of Occupation.

https://bit.ly/2FtnTgr

On December 21, 2018, TV Company “Guria TV” covered information about a charity event organized by civics students from MT program partner school to prepare New Year presents for economically disadvantaged people (Guria region).

https://www.facebook.com/guriatv/videos/337089390207918/?eid=ARCxZNn2KvL0Ymx75UH60S4SufhPuoHOWPMXkpXezySZjBSmT10Lez4SXCbuYxg1-AzEZj0vqvj0kz-p

Radio

On November 27, 2018, radio “Imedi” morning program hosted Marina Ushveridze, “Momavlis Taoba” chief of party and Simon Janashia, education researcher, to speak about teaching civic education at schools.

https://bit.ly/2ALCRdU

On October 31, 2018, radio “Imedi” morning program hosted students of Tbilisi public school #139 to speak about a project dedicated to women’s rights.

https://bit.ly/2RNp6oH

On December 7, 2018, radio “Adjara” broadcasted information on village Zemo Tsinsvla students, who conducted an information campaign to promote healthy nutrition and a healthy lifestyle (Adjara region).

https://www.facebook.com/1730187050533175/photos/pcb.2273211286230746/2273210949564113/?type=3&theater

On November 15, 2018, radio “Atinati” shared information about village Ganmukhuri students’ initiative about the use of plastic bags.

https://m.facebook.com/story.php?story_fbid=10161072140530274&id=316731145273

Online Media

On October 19, 2018, www.gurianews.com covered information about Chargé d’affaires Elizabeth Rood visit to village Chibati public school and her meeting with students, as well as her visit to the Lanckhuti Museum of Occupation (Guria region).

https://bit.ly/2OzIkxb

On December 6, 2018, www.etaloni.ge covered information about village Kekhijvari school student project “Be fast, save life” (Shida Kartli region).

.http://www.etaloni.ge/geo/main/index/17556?fbclid=IwAR2pxLM2BvO8zGCKBd3LHAg8g4tO0YrivEbapXq7_x2xecjGEygFMMRCCB0_

On October 15, 2018, web page www.etaloni.ge covered information about village Sakasheti public school student activities during World Peace Day. (Shida Kartli region).

http://www.etaloni.ge/geo/main/index/14983

On November 28, 2018, web page www.etaloni.ge covered information about village Kvemo Khviti public school students’ project about the negative influence of early marriage. (Shida Kartli region).

http://www.etaloni.ge/geo/main/index/17143?fbclid=IwAR0Z7mYKGN6ellyJmkOsPtVeWCLPIDJjj2TlH4r7MoiOVxVkt_FpVT7JBsk

On November 27, 2018, web page www.etaloni.ge covered information about village Kvemo Khviti public school students’ project about the negative influence of drug use (Shida Kartli region).

http://www.etaloni.ge/geo/main/index/17087

On November 26, 2018, web page www.etaloni.ge covered information about village Breti public school students’ meeting with the representatives of local municipality (Shida Kartli region).

http://www.etaloni.ge/geo/main/index/17047

On December 28, 2018, Facebook of EU and NATO covered information about the study visit of students of the Kareli municipality (Shida Kartli region).

https://www.facebook.com/EUNATOinfo/photos/pcb.1100841190089501/1100840293422924/?type=3&theater-

### List of attachments:

DVD with photos and media coverage materials of MT events.