Momavlis Taoba (Future Generation) Program

U.S. Agency for International Development

Cooperative Agreement AID-114-A-14-00006

AWARD PERIOD:  June 30, 2014 through December 15, 2020

MT extension Y2 Annual Report

Reporting Period: January 2019 – December 2019

Prepared for

USAID/Georgia

United States Agency for International Development

ATTN: Nino Buachidze, AOR

11 George Balanchine St.

Tbilisi 0131

Prepared by

PH International

Project Harmony, Inc.  
5197 Main Street, Unit #6

Waitsfield, VT, 05673

January 31, 2020

This report was produced for review by the United States Agency for International Development. It was prepared by PH International.

Table of Contents

List of Acronyms................................................................................................................................................iv

I.	Overview of the Momavlis Taoba Program	6

II.	Tasks Completed in the Reporting Period	7

1.	Identification of Partner Schools for MT Extension	7

2. Revision and Printing of Supplemental Civic Education Materials	8

2.1. Revision and printing of civics supplemental textbooks	8

3. Monitoring the use of civics supplemental textbooks and toolboxes	8

3.1. Visits to schools to observe the use of textbooks and toolboxes	8

3.2. Meetings with civics teachers and students on the use of toolboxes in	9

project planning	9

4. Teacher Training	10

4.1. Updates to the teacher training program, ToT, core training, additional training	10

5. Coordination with and capacity building of MESCS to play an expanded role in	11

national civic education efforts	11

5.1. Support to government civic education policy-making and implementation	11

5.2 Local Consultancy to MESCS	11

5.3 International Consultancy to MESCS	12

5.4. Technical Assistance to MESCS	12

6. Coordination with capacity building and activities of Civics Teachers Forum (CETF)	13

6.1. The role of the Civics Teachers Forum in the development of civic education in Georgia	13

6.2. Subgrant in support of relevant CETF programs	14

7. Applied Learning	18

7.1 NGO partners work to promote implementation of the MT program in regions	18

7.2. Equipment Contest for Schools	23

8. Mini-Grants for Students Activities	23

8.1. Education of students, teachers, and communities on mini-grants program	23

8.2. Identification of themes for mini-grants with inputs from schools and communities	24

8.3. Functioning and management of mini-grant program to students and/or	26

student-teacher groups	26

8.4. Monitoring and evaluation of mini-grant component	27

8.5. Funding of the mini-grant proposals from sources outside MT program	27

9. Interactive Website and Social Networking	30

9.1 Program websites and social networks	30

9.2. Online conference	30

10. Etaloni Competition	31

11. General/Administrative	31

11.1 Development of promotional materials of the program	31

11.2. Cooperation with Media	31

List of attachments:	34

List of Acronyms

MT – Momavlis Taoba (Future Generation Program)

PH – Project Harmony, Inc (PH International)

MESCS – Ministry of Education, Science, Culture and Sport of Georgia (name of the Ministry of Education and Science after the merger with the Ministry of Culture on July 14, 2018)

CETF – Civic Education Teachers’ Forum

CDT – Curriculum Development Team

ToT – Training of Trainers

ERCs – Educational Resource Centers of the Ministry of Education, Science, Culture and Sport of Georgia

Partner NGOs – program’s partner non-Governmental organizations in Tbilisi and other regions

ACETT - Applied Civic Education and Teacher Training Program

MAC - McLain Association for Children

## Overview of the Momavlis Taoba Program

The Momavlis Taoba Program (MT), funded by the United States Agency for International Development (USAID), is implemented by PH International. The program is supported by the Ministry of Education, Science, Culture, and Sport of Georgia. The program aims to 1) promote greater civic engagement of young people; and 2) enhance civil society’s role in promoting transparent and accountable governance at the national and local levels by expanding and institutionalizing secondary school civic education curricula and its practical applications. The program was built on the progress made under ACETT, which worked with civics teachers and students in approximately 30% of schools in Georgia. Through the initial MT award, the program reached another 20% of secondary schools (480 schools) throughout the country. Now, in the MT 3-year extension period, the program works with an additional 10% of secondary schools (230 schools), improving the quality and scope of school-based civic education as a means to positively influence the knowledge, attitudes, and behaviors of youth (and, through their example, those of the broader community) as active participants in Georgia’s democratic society. MT introduced additional approaches or variations to promoting applied learning by students in school civics classes, seeking to find the best approach or combination of approaches for maximizing the translation of learning into action. The program included schools in all 11 regions of Georgia: Tbilisi, Adjara, Guria, Imereti, Kakheti, Kvemo Kartli, Mtskheta-Mtianeti, Racha-Lechkhumi, Samegrelo-Zemo Svaneti, Samtskhe-Javakheti and Shida Kartli. PH partnered with regional NGOs to take advantage of their knowledge of regional differences and approaches to mobilize collaboration among young people, civil society, local authorities, and other stakeholders in ways that increase citizen engagement. PH International worked closely with its Georgian partner, the Center for Training and Consultancy (CTC), to accomplish the objectives of MT.

The MT extension, which is consistent with the scope of the initial MT award, further strengthens and consolidates its major activities and enables PH to accomplish MT results through an integrated set of program activities that include:

(1) selecting and working with 230 schools in Georgia to engage teachers, students and communities as partners in civic education and practice;

(2) updating (as needed) and delivering a modern teacher training course for civics teachers from project schools to assist them in better meeting civics curriculum goals for students;

(3) providing the new 230 schools with four high quality, interactive resources developed under ACETT and updated under MT to supplement and enhance existing, approved civic education textbooks and teaching resources. These resources (textbooks) are: “How Can I Become an Active Citizen”; “Cooperation for Community Benefit”; “Cooperation with Local Government and Media” and “Participation in School’s Self-Governance”;

(4) working with the Civics Teachers Forum and the Ministry of Education, Science, Culture & Sport (MESCS) to provide a sustainable system of supportive resources and incentives to civics teachers through an interactive website, peer skills development using professional learning community meetings and model lesson approaches, mentoring, and annual professional recognition awards;

(5) introducing varied approaches that encourage and support students from participating schools in applying their civics lessons into practice in their schools and communities, as well as local NGO and mini-grant support for teacher and student-created projects;

(6) holding multiple local, regional, and national activities including competitions, civics club fairs and other programs that further stimulate and reward the civic engagement by youth;

(7) working with MESCS to stimulate improvement of civic education in all secondary schools throughout the country and to prepare MESCS for the implementation of best practices as demonstrated through USAID civic education programs; and

(8) raising public awareness about the importance of civic education through media and other channels (TV, radio, print media, online sources, and social media).

PH International works closely with its Georgian partner, the Civic Education Teachers Forum (CETF), and regional partner organizations to accomplish the program objectives of MT.  The program is managed from PH International’s Country Office in Tbilisi, with contractual relationships with USAID managed from PH International’s US based headquarters located in Waitsfield, Vermont.

## Tasks Completed in the Reporting Period

## Identification of Partner Schools for MT Extension

This task is completed.

In December, 2019, PH received a letter from MT partner Tbilisi public school #139, stating that the school is not continuing its participation in the MT program. Receipt of this letter was preceded by information provided by PH’s partner NGO in Tbilisi that despite many attempts from the partner NGO, the school no longer cooperating with the program. The apparent reason was that there was a new school principal and there were internal conflicts taking place in the school between the school principal and different teachers. Meanwhile, the civics teachers were replaced twice and PH continued cooperation with the new civics teachers every time a teacher was replaced. Eventually, the new principal declared that the school does not need external support in teaching civic education and refused to cooperate with MT. In spite of PH’s several attempts to negotiate, the new principal said in a conversation that the school does not have the human resources to cooperate with the program (even though both civics teachers worked well with MT). PH even discussed this situation with the Ministry of Education representative, who contacted the school, but received the same response from the principal. Formally, the Ministry has no legal power to require the school to cooperate with the program if the school chooses not to.

Based on advice provided by the PH lawyer, MT staff drafted a response letter to the school administration underlining the roles and responsibilities of the school under the cooperation agreement signed by school and PH International early in 2018. According to the terms outlined in the agreement, the school is required to return the civics supplemental textbooks and toolboxes. At this point, the school administration is in the process of collecting the resources, which will be returned to PH.

Tbilisi public school #139 was replaced with LEPL – Tbilisi public school #174, which expressed its interest in getting involved in the MT program. PH will soon sign an agreement of cooperation with the new school, confirming the commitment by the parties to allocate the needed time and resources for participation of the school in the MT program.

Please see Attachment #1 – MT Extension Partner Schools List.

## 2. Revision and Printing of Supplemental Civic Education Materials

### 2.1. Revision and printing of civics supplemental textbooks

This task is completed.

The fourth set of the revised civics supplemental textbook, “Cooperation with Local Government and Media”, for 9th grade students in Azeri and Armenian languages was delivered to MT’s Azeri and Armenian partner schools. Each school received 4 copies of the teacher manuals and student books were delivered based on the number of student in 9th grade in each of the respective schools. The textbooks were received by the schools after signing a handover letter clearly stating the purpose of the textbooks and terms for their use in civics classes.

A total of 850 textbooks (660 Azeri and 190 Armenian) were received by the schools.

Printing of Additional Copies of Civics Materials

In September, 2019, regional partner NGOs notified PH that student numbers in grades 9 and 10 have increased at some partner schools during the academic year 2019-2020. Hence, there were no longer sufficient quantities of the civics supplemental materials for these schools. PH printed additional copies of the supplemental materials and delivered them to the respective schools. A total of 1,660 additional copies of the textbooks, “Cooperation with Local Government and Media”, “How to Become an Active Citizen”, “Cooperation for Social Benefit” and “Participation in School Self-Governance”, and 950 toolboxes - “Instructions for Civics Classroom Projects” - were delivered to 46 partner program schools.

## 3. Monitoring the use of civics supplemental textbooks and toolboxes

### 3.1. Visits to schools to observe the use of textbooks and toolboxes

This task is in progress and will continue over the upcoming quarter.

MT curriculum development team members (CDT) carried out a total of 105 monitoring visits to program partner schools to observe the use of the program’s civics supplemental textbooks and toolboxes in civics lessons. Of these 105 visits, 92 were carried out in Georgian language schools and 13 in Azeri and Armenian language schools. Of these 105 visits, 41 visits were made in the fourth quarter of the MT extension year 2.

Monitoring visits took place in the following regions of Georgia: Tbilisi, Shida Kartli, Kvemo Kartli, Samtskhe-Javakheti, Kakheti, Guria, Imereti, Adjara and Samegrelo.

The visits included the observation of the civics lessons by experts and discussions with teachers and students to evaluate the strengths and weaknesses of the process, identify the needs, and give recommendations for the improvement of future lessons.

Civics teachers positively evaluated MT’s supplemental textbooks and toolboxes which, according to them, effectively promote development of democratic values among the youth. The students are motivated to use the textbooks and are interested in applying their knowledge in civics, gained from MT’s supplemental resources, into practice. Civics club projects and civics classroom projects are carried out by students and facilitated by teachers. The teachers emphasized that MT’s partner NGOs are actively supporting all activities initiated and carried out by the students.

Although most of the teachers already practice project-based teaching, the monitoring experts observed that many teachers still need to master their skills in duly facilitating students’ classroom projects. MT and its partner NGOs will continue to work closely with schools and consult with teachers in the process of project planning and implementation.

The monitoring experts also identified that teachers are demonstrating low competency in the evaluation of students’ project activities. CTD members recommended that teachers develop special assessment rubrics as a tool to interpret and grade students' work against criteria and standards in compliance with the national curricula.

Some teachers also fail to demonstrate efficient classroom management practices. Teachers received recommendations from experts for improving their lesson planning and classroom management practices.

Teachers welcomed the feedback and recommendations received during the monitoring visits. MT curriculum development team members will continue monitoring visits in the upcoming quarter.

### 3.2. Meetings with civics teachers and students on the use of toolboxes in

### project planning

This task is completed.

To promote the process of applied learning which is key in civic education, MT designed “Instructions for Civics Classroom Projects” and “Instructions for School-Based Civics Clubs” toolboxes. These toolboxes are a compilation of instructional cards, each corresponding to one step of a student civics project. The toolboxes were printed in Georgian, Armenian, and Azeri languages and delivered to schools in the spring of 2018.

Monitoring visits by CDT experts and NGO representatives to schools showed that in some cases the toolboxes were not fully used in the process of civics projects planning and implementation. To stimulate proper use of toolboxes in civics project planning and implementation, in February-March, 2019, MT supported a total of 23 instructional meetings of practicing teachers with other teachers and students on toolbox use. At these meetings, participants discussed how they use toolboxes in planning and implementation of the civics projects and even designed new projects according to the steps outlined in the toolboxes to make those projects more organized and easier to assess. A total of 564 civics teachers and students participated in the meetings nationwide including Azeri and Armenian schools.  The meetings were held in the following cities: Kutaisi, Tbilisi, Telavi, Zugdidi, Batumi, Marneuli, Bolnisi, Ozurgeti, Akhaltsikhe, Kaspi, Gori.

As a result of meetings, hundreds of student projects on environmental protection, early marriage prevention, healthy lifestyle, human rights, bullying prevention, road safety, volunteerism, children’s rights and other topics were developed and will be implemented in the upcoming period.

## 4. Teacher Training

### 4.1. Updates to the teacher training program, ToT, core training, additional training

This task is in progress and will continue over the upcoming quarter.

In the first year of the MT extension, CETF in close coordination with the MT team, conducted a total of 18 core training sessions, “Teaching Democratic Citizenship”, for civics teachers of MT’s partner schools with the participation of 312 civics teachers.

Since schools have autonomy in appointing civics teachers each academic year and civics teachers cannot get a full-time work schedule by only teaching civics, the turnover rate for civics teachers in schools is quite high. MT needs to ensure that all teachers involved in the program receive core training. For this purpose, during the fall semester of 2019, MT’s partner CETF, under the guidance of PH International, provided additional 4-day core training courses to newly-appointed teachers as well as to other civics teachers from MT’s partner schools who hadn’t yet had a chance to participate in these trainings during the previous academic year. A total of four training sessions were held in Tbilisi and Kutaisi with the participation of 45 civics teachers.

Beyond this core training course, in the fall semester of 2019, civics teachers also received 2 days of additional training: a) one day focused on the four supplemental textbooks and b) the other day focused on the toolboxes. Three 2-day trainings were organized for 36 civics teachers in Tbilisi and Kutaisi.

The feedback of participants on the training was very positive; they evaluated the courses as “very helpful” and “productive.” Teachers also reported that after the training they were more motivated to apply interactive teaching methodologies in civic education. They indicated that the course helped them to become more confident and learn how to use the new tools for enriching the teaching process.

“I am very satisfied with these 4 working days. In addition to the content, the friendly environment provided during the course was remarkable. It is important for teachers to connect and widen their social networks, especially for teachers in the regions, and share their experiences”- said Tornike Shevardnadze, civics teacher of Tbilisi Public School #162.

“The training on how to use civics toolboxes of the ‘Momavlis Taoba’ program was quite interesting. I received the necessary information on the use of instructional cards and planning and implementing classroom and club projects. Now, I better understand the civics club work. This will help us to bring up more responsible and active citizens. Thanks to the organizers of the training"- said Nino Dautashvili, civics teacher of Gantiadi village public school, Dmanisi Municipality.

## 5. Coordination with and capacity building of MESCS to play an expanded role in

## national civic education efforts

### 5.1. Support to government civic education policy-making and implementation

This task is in progress and will continue over the upcoming quarter.

A series of civics teachers roundtables took place in October, 2019, in 8 regions of Georgia with the participation of 167 teachers. Changes in the “Citizenship” course standard, developed by MESCS were discussed by teachers. After the roundtables, MESCS received a document with the recommendations of civics teachers on the proposed changes, with the goal of improving the standard of the “Citizenship” course.

As a result of the Annual Civics Teachers Conference (held May 25, 2019), recommendations for MESCS for the improvement of teaching civic education in schools are being developed. Recommendations are based on a survey of hundreds of civics teachers and include the following: the need to attract a younger cohort of teachers into civics teaching who could teach civics at different school levels (primary, middle and high school); mandatory number of weekly teaching hours; how to avoid the misuse of civics for filling out “hours” of other subject discipline teachers; what steps shall be undertaken by MESCS for professional development of civics teachers; the need to emphasize the importance of civic education by MESCS; recommendations for changes in the Teachers’ Professional Development Scheme to improve the system of motivation and support for teachers’ professional development; recommendations for the creation of a culture of cooperation at schools; and others. Recommendations will soon be finalized and formally shared with MESCS.

### 5.2 Local Consultancy to MESCS

After discussing the needs with MESCS and at their request, MT began providing local technical assistance to MESCS for the improvement of its annual programs. Expert Nino Chiabrishvili, identified by MT, started to work on annual programs for the “Citizenship” course. With MT’s support, sample thematic programs were prepared on the following topics: “Community in Which I Live”, “School Environment / School Community”, “Protection of Natural Environment and Cultural Heritage”, “Local Government” and “Central Government”.

At all stages of the work, the Civics Expert at MESCS, Shalva Mekravishvili, provided feedback to MT expert Nino Chiabrishvili and at the end of the process approved each thematic program.

Based on discussion with MESCS, two practicing civics teachers were identified to assist Nino Chiabrishvili in developing the next sample thematic program. The role of the civics teachers will be to identify and test classroom activities and ideas for student projects and determine which ones are successful. Practicing civics teachers may also be involved in the development of other sample thematic programs.

With this local consultancy, MT helped to facilitate the introduction of the national civics curriculum in schools, as annual programs help teachers to take concrete steps and activities for achieving the curriculum goals in the classroom.

### 5.3 International Consultancy to MESCS

Based on discussions taking place throughout the reporting period, MT Chief of Party and MESCS representatives, Nikoloz Silagadze and Shalva Mekravsivhili, finalized the ToR for international Civics Education Consultancy Services. Once the ToR was approved by all involved parties, it was prepared for publishing. The announcement will be published on PH International’s website, will be sent out to different entities, and will be circulated in the relevant professional networks in the United States and in Europe.

### 5.4. Technical Assistance to MESCS

In the reporting period, a meeting was held at the Ministry of Education, Science, Culture and Sport (MESCS) to discuss the pending cooperation between MT and MESCS regarding support to the School Activities Program. Participants of the meeting included Deputy Minister Irina Abuladze and representative of MESCS Ketevan Kurtskhalia, Ninka Buachidze of USAID and Marina Ushveridze and Berdia Natsvlishvili from the MT Program. MESCS representatives emphasized that changes are expected to be made to the School Activities Program, therefore MESCS sees their cooperation with MT as support to MESCS programs, which aim at supporting school projects. The parties have also agreed that instead of pursuing a memorandum of understanding, the document will be titled “Agreement about Cooperation”. The final text was agreed between the parties as per MESCS’s suggestions and Agreement about Cooperation was signed by PH and MESCS.

As per recommendation of the Deputy Minister, after signing of the document, MT representatives met with the officials at Education Management Information System (EMIS), an agency of MESCS, to discuss the technical requirements for developing the website for MESCS’s school projects (the one similar to www.initiatives.ge). Through a public tender, PH selected a company - Circle Ltd - to develop a website for MESCS School Activities Program. The decision was made in consultation with MESCS’s agency. Education Management Information Systems (EMIS). Before awarding a contract, representatives of PH, EMIS, MESCS and Circle met and agreed on contract terms and main technical requirements: web technologies and web development concepts to be applied while creating the website; design of the website; frontend and backend development; website security; administrative functions of the website, etc.

After signing of the contract, Circle Ltd started the work and submitted the design of the website.  PH and MESCS have approved the design. The work on website development is now in progress, MT staff regularly meets with the representatives of CIRCLE to assess what was accomplished and identify next steps are needed for the development of the website. The process is closely coordinated with MESCS’s representative, who provides feedback so that the website best meets the needs of the MESCS.

## 6. Coordination with capacity building and activities of Civics Teachers Forum (CETF)

### 6.1. The role of the Civics Teachers Forum in the development of civic education in Georgia

This task is in progress and will continue over the upcoming quarter.

In the reporting period, MT continued to work with CETF, assisting the organization in expanding its activities to more schools, as well as reaching more teachers.

In February and March, CETF held the elections of its regional councils. The councils elected new chairpersons in 10 regions (Imereti regional council covers Racha-Leckhumi as well) for a two-year term.

On March 30, 2019, within the framework of MT, CETF held a meeting for the representatives of its regional councils. The aim of the meeting was to discuss CETF’s ongoing and future activities and identify tasks for each regional council. The meeting focused on the forum membership system and monitoring and fundraising opportunities. The members of the meeting discussed  effective ways of identifying the needs of civics teachers in their respective regions.

In addition to offering professional development activities to MT teachers, CETF also continued to provide professional development support to other civics teachers in Georgia. This support is possible as a result of CETF’s fundraising efforts, which are supported by MT.

During the reporting period, CETF’s project proposal “Civic Education Simulations for Georgian Schools” was approved within the program “Expanding Cooperation with Civil Society in the Eastern Partnership Countries and Russia”. The program was funded by the German Federal Foreign Office and aimed at enabling civil society organizations to play their part as key actors and important partners of governance. Within the program, CETF conducted trainings for civics teachers on developing simulation games. The participant teachers were trained in civics simulation games in Berlin, Germany. Applying the learning gained from this training they have created games for their schools and plan to carry out these games with students in their respective schools during the academic year 2019-2020. The topics of the simulation games include local action plans for youth civic engagement at the local level; inter-group ethnic conflicts; and political participation for environmental protection.

CETF, in partnership with CTC, successfully completed the project “Towards a Culture of Peace”, funded by the EU STRIVE Global Program. The project aimed at strengthening the competencies of civics teachers, raising their awareness of early signs of radicalization and violent extremism, and encouraging civic engagement of school students. The project partnered with a total of 20 schools in 4 regions of Georgia - Tbilisi, Adjara, Kakheti and Kvemo Kartli.

CETF conducted a 2-day training on “Countering Radicalization and Preventing Violent Extremism” within the Project "Towards Resilient School Communities" funded by Canadian Fund for Local Initiatives (CFLI) of the Canadian Embassy in Ankara. A total of 16 civics teachers from 4 regions (Adjara, Guria, Akhmeta, Tbilisi) of Georgia were trained in detecting early signs of radicalization and how to counter violent extremism at schools. The training introduced to teachers the tools for countering intolerance, bullying and violence in order to make the schools more peaceful and resilient.  A project proposal - “1+1 Synergy for Democratic Culture”, which was developed by CETF together with its 5 partner organizations (2 Georgian, Norwegian, Spanish and Czech) was approved by Erasmus+ Programme of the European Commission. The project aims at building partnerships of civics teachers and youth workers for developing non-formal learning approaches to promote social and civic competences of students.

CETF, in partnership with the National Bank of Georgia and the German “Savings Bank Foundation” (Sparkassenstiftung), developed modules on financial education. Within the initiative, CETF will train civics teachers as multipliers, who will conduct further trainings for teachers who are teaching “Citizenship” for 7th grade in their respective regions for teachers who are teaching the “Citizenship” unit at 7th grade all over Georgia.

CETF has 1,100 registered members. Forty percent of the members have never paid membership fees and sixty percent have paid at least once. In consultation with MT, CETF will start a reminder system via SMS to support membership fee collection. Also, the rule for accepting new members will be changed: a person can only become a member after paying a portion of the membership fee.

In consultation with MT, CETF is also developing a basic package offer for its members. The basic package will include some of the following: annual news bulletin, participation in the annual National Fair-Conference of Civics Teachers, professional consultations, opportunities to participate in the teacher trainings and other professional development activities.

### 6.2. Subgrant in support of relevant CETF programs

This task is in progress and will continue over the upcoming quarter.

National Fair-Conference of Civics Teachers

National Fair-Conference of Civics Teachers was held in the framework of MT on May 25, 2019. The Conference aimed to present innovations in the field of civics education, facilitate sharing of the best practices among civics teachers, recognize professional achievements of civics teachers from different regions of Georgia, and facilitate professional interaction between civics experts and teachers in workgroup sessions. Approximately 300 participants took part in the National Fair-Conference. The event included an exhibition of the student projects, facilitated by teachers. Deputy Minister of Education, Science, Culture and Sport of Georgia, Irina Abuladze; Director of USAID’s Democracy, Governance and Social Development Office, Adam Schmidt; Director of Teachers Professional Development Center, Berika Shukakidze; PH International’s Executive Director, Ann Martin, education experts and other invited guests visited an exhibition and spoke with teachers about their projects.

The plenary session featured speeches by Deputy Minister of Education, Science, Culture and Sport of Georgia, USAID Democracy, Governance and Social Development Office Director, MT Chief of Party, Director of Teachers’ Professional Development Center and MESC’s National Curriculum Coordinator.

CETF’s general assembly meeting took place during the noon session, where the general assembly approved CETF’s newly elected regional councils.

During the final part of the conference, participants broke into smaller groups to discuss the following topics:

1. Data usage in teaching civic education - Simon Janashia, Education Researcher;

2. Democratic culture competences- Natia Natsvlishvili, TPDC;

3. Financial education - Tinatin Gogatadze, Mariam Guniava, National Bank of Georgia;

4. The role of civic education in preventing bullying at schools - Ekaterine Burkiashvili, Office of Resource Officers of Educational Institutions.

Please see attachment 2 – Agenda of the Annual Civics Teachers Fair-Conference.

The best civics teacher of the year award

The award ceremony of the best civics teachers was held on May 25, 2019, during the Civics Teachers Forum’s National Fair-Conference.

The selection committee reviewed a total of 104 applications received for the Best Civics Teacher of the Year award. Selection committee members included: MT Chief of Party Marina Ushveridze, MT Manager of Regional NGO Network Tamar Pruidze; MESCS’s Civics Expert Shalva Mekravishvili; representative of Teachers Professional Development Center Nino Gvaramadze; Civics Expert Nino Beselia; Assistant Professor at Ilia State University Nino Chiabrishvili; civics expert Manana Jincharadze; and CETF Executive Director Maka Bibileishvili. The committee selected 26 winners in the following categories – the best civics teacher of the region (7 teachers), the most successful teacher (7 teachers) and the best civics club teacher (8 teachers). Four more teachers received special prizes for promoting civic education.

Developing additional teaching materials

Civics teachers face challenges in the classroom and are sometimes in need of new teaching materials to meet the newly occurring challenges. MT makes an emphasis on empowering civics teachers to be able to identify additional teaching materials and develop their own teaching materials. In the framework of MT, training sessions on "Graphical Visualization in the Process of Teaching", teachers learned how to develop their own teaching materials with the help of graphic facilitation and online platforms in response to classroom needs.

The first training session was held on 6-7 of April in Tbilisi. The structure and design of the session was fully based on non-formal education approaches and aimed at developing teaching competencies (knowledge, values, attitudes and skills) of the participants. During the session, both experience-based and collaborative learning approaches were applied. Participants had the opportunity to share their experiences, as well as develop important competences and create products through various materials and practices. A total of 23 civics teachers participated in the session.  As a result of the session, a total of 10 teaching resources were created.

The second training session was held on 18-19 of May in Batumi. The session was led by Nana Dikhaminjia who introduced different information sharing, communication and graphical visualization technologies to civics teachers. During the session, the teachers learned how to create online questionnaires, concept maps, thematic infographics, supporting materials, sample question-answer games with the help of various online tools and applications: Sli.do, Canva, Adobe Spark, Padlets, Kahoot, TedED, EdPuzzle, BrainScape, MindMup, MindMeister. Teachers also learned how to use free, available learning video resources, make their own video clips and integrate them into the teaching processes.

Model Lessons

In April-May, 2019, a total of 8 model lessons led by MT partner schools’ civics teachers were conducted in 8 regions of Georgia – Tbilisi, Imereti, Guria, Samegrelo, Kakheti, Shida Kartli, Kvemo Kartli, and Adjara. A total of 107 civics teachers attended the model lessons nationwide.  Model lessons covered the following topics from MT’s civics supplemental textbooks:

- Discrimination and equality. Everyone is different, everyone is equal;

- The role of students and the opportunities for participation in school self-governance;

- Identification and selection of the partner;

- How to become an active citizen;

- Bullying and discrimination.

Professional Development Training for Civics Teachers

Civics teachers requiring preparation for a subject exam in civic education were identified and trained. Civics teachers’ professional development training was organized in the framework of MT on 22-24 of June. The training was led by Assistant Professor at Ilia State University, Nino Chiabrishvili, and Professor of the University of Georgia, Eka Gegeshidze. Twenty-three teachers from different regions of Georgia participated in the training.

With support from MT, in September CETF organized a professional development training "Planning of Interactive Lesson" for civics teachers from different regions of Georgia.

The training helped participant teachers to learn more about interactive teaching methods and approaches and provided them with support in the creation of efficient lesson plans. Eighteen civics teachers participated in the training, which was conducted by a trainer Nino Kapanadze.

“During the training, I learned about the methods and strategies of planning an interactive lesson and the structure of reflexivity. I think I will be able to develop a better lesson plan now and also share this knowledge with my colleagues at school” - said Kakhaber Shonia, a civics teacher of Kvemo Potskho village public school in Senaki Municipality.

“The issues discussed at the training have clearly shown the weaknesses that I did not consider before during lesson planning. Knowledge gained at the training will help me to better manage service-learning process” - said Tamar Mamulashvili, a civics teacher of Tbilisi Public School # 132.

Discussion Meetings for Teachers and Students

In the reporting period, four discussion meetings for civics teachers and students were organized. "Pedagogical and School Needs Survey", led by Assistant Professor at Ilia State University, Nino Chiabrishvili, and the second discussion meeting featuring a presentation on "Feminism and the Fight for the Right to Education" by Associate Professor of Ilia State University, Tamar Tskhadadze. This meeting addressed issues related to women's movements, emancipation, gender equality and professional choice.

In December, two more discussion meetings for teachers were held in Tbilisi and Batumi. The topic of the meetings was the Georgian Constitution. The meetings were facilitated by Dimitri Gegenava, a constitutionalist and Deputy Rector in the Sulkhan-Saba Orbeliani University of Georgia. During the discussion meetings, teachers identified key challenges in the constitution and its limitations. They also compared the Georgian constitution to the constitutions of other countries.

Professional Learning Community meetings

In October-November, 2019, CETF facilitated a total of 8 Professional Learning Community meetings on “the evaluation methodology” in Tbilisi, Marneuli, Kutaisi, Zugdidi, Telavi, Gori, Lanchkhuti, and Batumi with the participation of partner schools' civics teachers. The meetings were facilitated by CETF Regional Council Chairpersons with support of Nino Gvaramadze, civics expert of Teachers Professional Development Center (TPDC); Manana Jincharadze, Consultant of TPDC; Nino Beselia, Civic Education Expert; Nino Chiabrishvili, Assistant Professor of Ilia State University; and Davit Malazonia, Professor of  Ilia State University.

A total of 112 civics teachers participated in Professional Learning Community meetings nationwide.

"Today's meeting was interesting because we discussed one of the most important issues - evaluation of complex tasks. We discussed how to create an evaluation rubric, what details should be considered and what we value. The meeting has made it clear that we should provide learners with our assessment rubric and improve it with them" – said Nino Beritashvili, civic teacher of Tbilisi Public School #118.

Regional Roundtables

Teachers often lack information and need a broader understanding on certain topics that are part of civic education, such as the national curriculum or a specific methodology.

For this purpose, a total of 8 civics regional roundtables on a new civics subject “Citizenship” took place. The roundtables were held in Lanchkhuti, Zugdidi, Tbilisi, Marneuli, Telavi, Gori, Batumi, and Kutaisi, with the participation of civic education teachers. The meetings were led by the civics experts Nino Gvaramadze, Aluda Goglichidze and Nino Chiabrishvili.

During the roundtables, a special questionnaire by MESCS was completed by teachers from which recommendations were developed and sent to the Minister Mr. Mikheil Chkhenkeli.

A total of 169 civics teachers took part in the regional roundtables.

"Meetings organized by the ‘’Momavlis Taoba” program are always informative and provide teachers with opportunities to learn about the latest changes and the ways of adapting them to the education process"- said Lali Sichinava, civics teacher of Tskhemliskhidi village public school.

“It is very important to me to attend the meetings held within the ‘Momavlis Taoba’ program. Trainings are always well organized, facilitated by professionals and oriented to the needs of the teachers” – said Ketevan Ruseishvili, civics teacher of of Batumi School “Euro 2000”.

## 7. Applied Learning

### 7.1 NGO partners work to promote implementation of the MT program in regions

This task is in progress and will continue over the upcoming quarter.

On January 23-24, 2019, MT organized a two-day meeting with regional implementing partner NGOs. Meeting participants discussed ongoing activities, challenges, and best practices in stimulating civic engagement of youth. The MT team spoke about strategies to maximize the use of MT resources by beneficiaries, about motivational strategies for teachers and students, and discussed the best practice examples and any dilemmas that have occurred in program implementation in different locations. Participants also covered other details of program implementation including program and financial reporting, small grants, and media coverage. During the meeting, the MT team, together with partner NGOs, finalized the list of equipment contests, winner schools, and teachers. Decisions were made based on the discussion of received applications, verifying the data with different individuals (for example: experts who conducted classroom monitoring visits, or results of mini-grant implementation), and taking into account specific recommendations provided by partner NGOs.

In January-February and May-June of 2019, MT end-of the program year and end-of the semester events were held in 8 regions of Georgia. These events featured presentations on successful projects and initiatives carried out by students and civics teachers during the civic classes and in school-based civics clubs. Students and civics teachers were awarded with certificates for their successful participation in the program. The events were attended by students, civic education teachers,  representatives of school administrations and local governments, NGOs, and educational resource centers.

During the MT extension Y2, NGO partners supported the work of 230 school-based civics clubs with the participation of 3008 new member students.

During the MT extension Y2, NGO partners supported a total of 600 initiatives implemented by school-based civics clubs to promote civic education among 3,567 beneficiaries. Of these, 2,129 were girls and 1,438 were boys. In addition, 279 were representatives of national minorities.  (4th quarter numbers are: 279 events for 1,766 beneficiaries). This number includes duplicates, as very often the same students participate in more than one activity during the academic year.

Besides the civics clubs’ initiatives, NGO partners supported the implementation of 738 classroom projects among 2,276 beneficiaries. Of these, 969 were girls and 1,822 were boys, and 289 were representatives of national minorities.  (4th quarter numbers are: 372 classroom projects for 1,533 beneficiaries). Events included students initiatives to promote healthy lifestyles and healthy nutrition, students activities for gender equality, student-led actions to promote democracy, to protect human rights, combat violence against women, and prevent bullying, charity actions, advocacy efforts to improve the environment, cleaning and greening actions, discussions on early marriage and trafficking, and contests and quizzes on civic education topics. These events also included celebration of international days by students such as World Autism Awareness Day, World Tuberculosis Day, Women’s International Day, International Day for the Protection of Children, World No Tobacco Day, Earth Day, the 25th anniversary of April 9 tragedy, International Day Against Drug Abuse, International Youth Day, Clean the Earth, Illicit Trafficking, European Day Without A Road Death, International Day of Peace, International Day of Older Persons, International day for Eradication of Poverty, Girl’s International Day, and 16 Days of Activism Against Gender Based Violence.

During the MT Extension Y2, partner NGOs conducted 112 seminars and trainings on civic education topics for 966 students. This figure contains duplicates. Of the training participants, 587 are girls, 379 are boys and 14 are representatives of national minorities. (4th quarter numbers are: 38 seminars for 238 beneficiaries). Seminars covered the themes of active citizenship, advocacy for community benefit, effective presentation, problem identification, children’s rights, bullying prevention, effective communication, team work, road safety, cooperation with local governments for resolving community issues, online petition management, early marriage prevention, advocacy, conflict management, volunteering, the use of Google and other social media platforms, conflict resolution,  the use of MT supplemental toolboxes in project development, professional orientation, and career planning.

During the MT Extension Y2, MT’s NGO partners arranged 56 group visits with the participation of 291 students to local non-governmental organizations and media. These visits included 190 girls and 101 boys.  (4th quarter numbers are: 25 group visits for 144 beneficiaries) Students visited Gurjaani City Hall, the Sighnaghi and Gurjaani municipality mayors’ offices in the Kakheti region, Rustavi City Hall in the Kvemo Kartli region, the local radio station and mayor’s office in Akhalkalaki, in the Samtskhe-Javakheti region, the Women's Information Center and the Museum of Occupation in Gori, the Georgian Olympic Museum, Parliamentary Library of Georgia, the Caucasian House, Tbilisi City Hall, Georgian Public Defender’s Office in Tbilisi, the Department of Tourism and Resorts of  the Adjara Autonomous Republic and the local radio office in the Adjara region,  the Cadets Military Lyceum, a local TV company, and a publishing house in Kutaisi, Ozurgeti municipality office in Guria region, and various local government offices in different municipal centers.

In addition to the group visits, NGO partners facilitated 84 meetings for 543 students with expert guests. This number includes 337 girls, 206 boys, and 20 representatives of national minorities. (4th quarter numbers are: 25 meetings for 144 beneficiaries) Students met with local authorities, local NGO officials, doctors, representatives of the  Georgian Public Defender’s office in the  regions of Kakheti and Kvemo-Kartli, Imereti and Shida Kartli, they also met with lawyers, journalists, migration specialists, sports people and world champions,  local election commission representatives, psychologists, doctors, social workers, nutrition specialists, cyberbullying expert and police department representatives. Students also met with successful alumni of the civic education program. In Adjara region, students met with the USAID Georgia Mission Director, with Deputy Mission Director of USAID Georgia and with the Director of the Democracy, Governance and Social Development Office of USAID Georgia.

With the support of MT’s NGO partners, MT students identified problems in their local communities, addressed local governments and other agencies with their requests, and became involved in activities to solve identified problems. Such activities were carried out by students in school-based civics clubs and/or through civics classroom projects. Involvement in civics activities helped students to apply the knowledge gained at civics lessons into practice and engage in activities for  community benefit.

Specific examples of students’ activities from different locations are listed below:

Tbilisi

In December, 2019, school-based civics club students of Tbilisi Public School #119, in cooperation with the representatives of local government, improved road safety in the community. In response to students’ request and with support provided by a member of Tbilisi City Assembly, Shalva Ogbaidze, a pedestrian crosswalk was painted near the school, a sign prohibiting trucks from parking was installed, and an electronic tab of the bus schedule was installed. Students also worked to raise awareness of younger schoolmates about road signs and disseminated flyers in the community.

In November, 2019, the 9th-grade students of Tbilisi Public School #75 decided to organize an informational campaign to raise public awareness about the negative impact of plastic on the environment. They conducted a survey among community members from which they learned that 80% of respondents lack information about the harmful influence of plastic on the environment. In the framework of the campaign, students organized a seminar at school on environmental protection issues, organized thematic exhibition of paintings and disseminated flyers about the negative impact of plastic on the environment in the community.

Samegrelo

In October 2019, students of the Menji village public school in the Senaki municipality decided to promote the health benefits of the mineral water of their village. Years ago, there was a Balneological Resort, which was well known and visited by many people. The resort is no longer functioning, but many local and foreign visitors still visit the place for water. However, due to the lack of landmarks, visitors have difficulties finding their way to the village. At first, students did a little research and learned that certain diseases can be treated using the mineral water baths. To raise public awareness about this, they prepared leaflets and distributed them to the community in the Senaki city center. Students successfully cooperated with the school administration and the local government. As a result of the students’ efforts, a bilingual banner showing the way to the Menji resort was placed on the Zugdidi-Tbilisi highway.

In December, 2019, school-based civics club students of Mestia public school, an MT partner, decided to improve road safety in their community. The school is located next to the central highway where there was neither a pedestrian road sign nor a crosswalk. Students applied to the mayor of the Mestia region for help and as a result, the problem was solved and a crosswalk was painted. In addition, students prepared leaflets on road safety and disseminated them in the community.

Shida Kartli

In December, 2019, civics club students of Aghaiani village public school initiated a project “We Choose Equality,” to raise public awareness about discrimination, equality, and tolerance. Tolerance is especially important in this village, as there are ethnic minorities living there. Students arranged an informal meeting at the school during which Georgian and Azeri students discussed the importance of equality, created a newspaper and flyers and disseminated them in the community. Students also performed a flash mob in the schoolyard and painted the yard with colorful chalk, leaving messages about equality and tolerance.

In December, 2019, civics students of Osiauri village public school met with local government representatives to discuss community problems. The main problem identified by students was related to contamination of Suramela river. Students organized a joint cleaning campaign of the river’s surroundings and asked for permission to paint the river jetty. Students also invited an artist to the school and developed samples of paintings for the river jetty. Students informed peers from other schools of Khashuri municipality about their project and initiated a cleaning campaign for Suramela river. In cooperation with school administration and local government, students painted the river jetty, organized a cleaning campaign, and called upon the community to protect the environment.

Imereti

In November, 2019, civics students from Vartsikhe village implemented a project about labor rights protection. The students cooperated with a lawyer from the Imereti branch of the Public Defender Office and participated in a training on juvenile employment and labor rights. Based on the knowledge they gained from this training, students conducted informational sessions for their peers from 3 different schools in the Baghdati municipality and prepared leaflets which were  distributed within the community.

In November, 2019, students from Rokhi village public school responded to a 16-day campaign against gender-based violence through  their project “No to Violence.”  The project aimed to raise public awareness on women’s rights, determine cases of violation, and collaborate with relevant agencies for gender-based violence prevention.  At the initial stage, students conducted a community survey to determine the community’s knowledge on domestic violence. Students then invited a lawyer and participated in a training at which they discussed gender-based violence and spoke about relevant agencies focused on eliminating gender-based violence. Following the training, students organized social media campaigns entitled “Let’s Meet Famous Women of the World” and “Say No To Violence Against Women.” Students also organized a film screening on women’s rights and conducted a follow-up survey to determine how well the project changed the attitudes of their peers to gender-based violence.

Adjara

In December, 2019, civics students from Tsoniarisi village public school met with a representative of the Keda municipal council. At the meeting, students learned about the structure and the role of local government. Students also presented the civics projects implemented at their school and spoke about civic engagement. It was decided that civics students will attend Keda Municipality budget discussion sessions to better understand the role of the local government and were offered the opportunity to approach decision makers with issues from their communities.

In October, 2019, 9th grade students from Begleti village public school surveyed their local community’s knowledge on gender equality. Survey results showed a lack of public awareness on gender equality. Students organized an online conference with the head of the Adjara gender media center and met with a local municipality gender council representative to talk about the importance of gender equality. In addition, students initiated a drawing competition at school entitled “What Do I Know About Gender Equality?” and organized debates centered around women’s participation in politics. To further promote gender equality among youth, the Adjara gender media center provided students with special banners about successful women from the Adjara region for the exhibition organized at school on gender equality.

Kakheti

In November, 2019, civics students from Arashenda village public school surveyed the local community from three neighboring villages on road safety issues. It was discovered that the bridge, named LAKBA, that connects villages to the municipality center was in a very bad condition and needed repairs. To solve the problem, students raised the issue first to the local administration of the village and later to central municipality officials. After the meetings, local decision makers decided to further cooperate with students. The bridge renovation process started in November and was successfully finished in December, 2019.

In November, 2019, students from Anaga village implemented a project to supply water to the school and local ambulance. Students began by surveying the local community about the problems connected to the water supply, asking the local community if they had ever applied to the local government with this problem, and if they ever received a positive response from local decision makers. Survey results showed that water supply maintenance was the most critical issue for the local community. After the survey, students visited village kindergarten, ambulance, and school. They found out that the kindergarten had a permanent water supply, schools had a partial water supply and the local ambulance was completely out of water. Students raised water problem issues with the local administration office and received an answer that a permanent water provision will start in early 2020. Until that time, the students will help ambulances on a daily basis by providing them with water from nearby places.

Kvemo - Kartli

In November. 2019, the 9th grade students from Tamarisi village public school took efforts to solve the problem of pollution of the main irrigation channel. Students surveyed the local community about the major problems that cause irrigation system pollution and determined that the lack of trash bins in the village is the main source of  pollution. Students raised the issue with the head of Tamarisi village administration. As a result of their successful cooperation with the local administration, students organized a cleaning campaign of the area around the irrigation channel.  All needed equipment was provided by the local government. Students prepared informational brochures calling on the community not to pollute the environment, emphasizing the harmful effects of a polluted environment on human health. After the cleaning campaign, students organized a meeting with the Marneuli municipality mayor and discussed the necessity placing trash bins around the area of the irrigation channel. The mayor promised to place trash bins near the channel early in 2020.

Guria

In October, 2019, civics students from Bokhvauri village took efforts to raise public awareness on elimination of use of polyethylene in their community. In cooperation with parents, students designed and sewed shopping bags from cloth. Students also prepared informational leaflets about the harm polyethylene has on the environment. They successfully cooperated with the local supermarket’s administration to organize an informational campaign in the supermarkets, calling on community members to replace polyethylene with cloth bags.

In November, 2019, 10th grade students from Askana village public school implemented a classroom project entitled “No to Early Marriage.” The project aimed to raise the awareness of youth on the issue of early marriage. The idea of the project began when students conducted a survey interviewing around 50 people in the village, and survey results showed that from 50 families, around 20 families were the result of early aged marriages Students decided to discuss the results with a specialist and arranged a meeting with a psychologist. At the meeting students obtained detailed information about the causes and effects of early marriage and watched a film. Based on the knowledge they received, students prepared brochures about the issues associated with early marriage and disseminated them in the community.

### 7.2. Equipment Contest for Schools

This task is in progress and will continue over the upcoming quarter.

In October, MT announced equipment contests for the program’s partner schools and civics teachers. The contests aim to recognize the work of the most successful partner schools and civics teachers and award them with equipment (laptops for schools and tablets for civics teachers) to support implementation of their civics activities.

The equipment contest was announced through MT’s social networks and webpage - www.civics.ge. Application forms were also distributed by PH’s regional partner NGOs to schools.

By the set deadline, December 2, 2019, a total of 112 applications (63 applications from schools and 49 from civics teachers) were received. Applications will be first assessed by MT’s regional partner organization representatives, who will review and recommend the best schools and teachers for awards. These recommendations will be made based on projects and activities implemented by students in civics clubs and teachers. At the second stage, applications will be examined and assessed by the MT selection committee and representatives of NGO partners together. The final candidates will be confirmed in January.

Successful applicants will be awarded in the upcoming quarter.

## 8. Mini-Grants for Students Activities

### 8.1. Education of students, teachers, and communities on mini-grants program

This task is in progress and will continue in the next quarter.

During the second year of the MT program extension, two mini-grant contests were announced. The first contest was announced in May 10, 2019, and the second one in September 20, 2019.

Regional partner NGOs provided all interested and eligible applicants with consultations. Through these consultations, interested applicants received hands-on training in how to develop a project proposal and budget, how to describe proposed activities in the action plan, and how to pull together matching resources. Partner NGOs informed the students, teachers, and school administration officials about the deadlines and application procedures, and provided technical help whenever needed.

There were total of 45 open days, 13 training sessions, and 106 group and individual consultations with participation of 689 beneficiaries held for applicants of the mini-grants program. This number of beneficiaries includes 391 females, 298 males, and 65 ethnic minorities

During its second year extension, MT program received 213 applications for mini-grant proposals from students, teachers, and school administration officials through www.initiatives.ge (105 proposals were received from the May, 2019, contest and 108 from the September, 2019 contest).

Winners for the first call of proposals of the second year of MT extension were selected in September, 2019, while the winners of the second call were announced in December, 2019, by the committee based on the following criteria:

- Applicants should propose civics classroom projects, in which all students in the class participate;

- Application should address one of the mini-grant themes;

- Applicant should be a representative of an eligible partner school (teacher, student or representative of school administration);

- Application should be filled out and sent online via www.initiatives.ge with its appendices (budget, implementation plan, and school confirmation letter);

- Grant amount shouldn’t exceed $450;

- Youth involvement and civic participation should be an important part of the project;

- Applications should be submitted within the established deadlines, and

- Innovative project ideas were given a priority.

Partner NGOs helped with the initial screening and shortlisting of all applications while the PH-MT team, in consultation with local NGOs, made final decisions about short-listed applications. In cases where applications met MT objectives but needed to be improved technically, the MT team, together with regional partners, provided feedback recommending specific steps for improvement.

### 8.2. Identification of themes for mini-grants with inputs from schools and communities

This task was completed in the previous quarter.

As mentioned above, PH issued targeted calls for applications two times in 2019 with selected topics each time. Identification of thematic areas for the first call of 2019 mini-grant proposals took place in April, 2019, and the themes for mini-grant proposals for the second call were selected in early September, 2019. In both cases, the themes for mini-grants were identified in consultation with students via regional partner NGOs based on needs of the local communities and schools. Mini-grants covered civic participation by youth as well as efforts to educate youth about civics issues and engage peers in important initiatives for their schools and communities.

The selected themes for both included the following:

- Prevention of bullying by youth;

- Solving/advocating for ecological problems;

- Human rights protection and the rule of law;

- Supporting societal awareness on labor safety and employers’ rights;

- Promotion of healthy lifestyle;

- Prevention of violence (especially violence towards women, violence in families and other types of violence);

- Prevention of early marriage;

- Cooperation of youth with local government, media, private and NGO sectors to resolve critical problems for schools and communities;

- Supporting students in gaining citizen journalism skills to resolve critical problems for schools and communities;

- Promotion of integration of disadvantaged groups into society;

- Supporting students’ initiatives to improve the school environment;

- Promotion of cultural sightseeing, historical heritage, and tourism development in the village/town;

- Supporting public education about Euro-Atlantic integration;

- Supporting public awareness about the constitution;

- Increasing students’ awareness about media literacy;

- Strengthening of students’ self-government;

- Promotion of literacy among youth;

- Promotion of gender equality;

- Supporting business ideas by the students;

- Supporting students’ initiatives about prevention of crime among the youth;

- Supporting public education about GMOs;

- Promotion of parents’ engagement in school life;

- Supporting students’ initiatives to support road safety;

- Supporting youth education about health emergency services.

### 8.3. Functioning and management of mini-grant program to students and/or

### student-teacher groups

This task is in progress and will continue over the upcoming quarter.

Mini-grants serve as a means to stimulate applied learning in civics by students. Through the mini-grants program, students, teachers, and school administrators are able to open the channels of communication with local government officials and facilitate decision-making processes regarding their communities from the grassroots level. Professional motivation is also created for civics teachers as they are able to get involved in small projects with their students and deliver results that bring benefits to their schools and communities. There are also local resources mobilized for the mini-grant component.

Applicants of mini-grants are students, teachers, school administration officials, or combination of the above individuals.

Funding decisions for the applications of fourth round mini-grants contest within the MT program extension were made in September, 2019, and 21 civics classroom projects were selected.

The projects’ implementation started in October and will be finalized in early summer, 2020. Information about the implementation of these projects will be reported in the next quarterly report.

The only mini-grant project finalized in December, 2019, is the Tbilisi Public School #119 project:

Project Title: Safety and self-defense from natural disasters

Project Description:  Tbilisi Public School #119 students’ project: “Safety and self-defense from natural disasters,” benefitted the school and community.

There were landslides around the school territory. To address this problem, students, with the support of their civics teacher, tested the soil to select plants that are useful for preventing landslides.

Within a mini-grant project funded by the MT program, students purchased seedlings and arranged a greening action at school. In addition, students shared information about disaster risk reduction to the younger students of their school, organized an art show, and disseminated flyers at school and in the community.

The data regarding student involvement in implementation of the 39 projects is the following: a total of 1695 students were engaged in mini-grant project planning and implementation. Among these, 1016 were girls and 679 were boys. Of these, 522 students were in the 9th grade, 646 were in 10th grade, 323 were in 11th grade and 204 were in 12th grade. Besides Georgian students, 461 ethnic minority students participated; 14 IDP students  were involved. The beneficiaries of the 39 projects finalized in the second year of the MT program were 11,047 people in total (the figures include data of winners awarded during the second (17 projects) and the third (22 projects) project proposals calls.

### 8.4. Monitoring and evaluation of mini-grant component

This task is in progress and will continue over the upcoming quarter.

During the reporting period, mini-grant allocations were monitored by the MT staff. NGO partners have the responsibility of supervising the grant allocation and implementation process in the field.  Monitoring involved visits of the MT staff as well as written reports from NGO partners, which include project reports and success stories from grant recipients. MT’s Mini-Grants Coordinator maintains regular contact with NGO partners, participates in events and activities carried out by grant recipients, and provides feedback in case the need for change occurs throughout the grant implementation. MT worked with its NGO partners to ensure support from schools for projects from outside sources, such as local governments, businesses, media, etc.

### 8.5. Funding of the mini-grant proposals from sources outside MT program

This task is in progress and will continue over the upcoming quarter.

Fundraising efforts for projects to be supported by non-MT sources were initiated from the beginning of the second year of the MT program extension and will be continued in the third year. The development of these student and teacher-led initiatives is supported by local NGOs to ensure due quality of budget planning, program design, and implementation. This is especially important when schools have to work with new donors and supporters. Once projects are implemented, partner NGOs will provide PH with documentation of these projects. Such new projects help students, teachers, and school administration officials refine their skills in communicating important issues to local government or other decision-makers. Teachers and students also learn how to advocate for these problems to be resolved.

With the support of MT regional partners (including in-kind or monetary resources), schools were able to implement 7 projects from non-MT sources. A total of 160 students were involved in the planning and implementation of such projects. This number includes 81 girls and 79 boys; 37 students from 9th grade, 80 students from 10th grade, 36 students from 11th grade, and 7 students from 12th grade.

Some of the mini-grant projects funded from sources outside the MT program are listed below:

Kakheti

Project Title: Books – a source of knowledge

Project Description: The civics club of Gombori village public school decided to arrange a library and working space at school. The project was started as an advocacy campaign with school administration, the library union of the municipality and local government to gain books for the village library. The negotiations were successful: school administration supported the initiative by providing the space, while the library union of the Sagarejo municipality delivered 5000 books for the village library.

To promote the importance of reading, the students organized an information campaign and reading hours; announced a drawing contest; and conducted a survey to determine students’ favorite books and discuss their findings.

Now, the library is open to school students and community members.

Kvemo Kartli

Project Title: Supporting road safety

Project Description: School-based civics club students of Gantiadi village public school decided to improve road safety in the community. The school is located near the central road, and students often crossed this road to get from the school to a shop on the other side. There were neither cross walk, nor traffic signs on the road, and cars moved at high speed. As a result, the life of the school community was not safe.

The students appealed to the mayor of Tsalka for help and as a result of a successful partnership, the problem was solved: a crosswalk, speed bumps and road signs were arranged.

In addition, the school civics club prepared leaflets on road safety and disseminated them in the community. The students also hosted auto-school representatives and gave training to the junior students to raise awareness on road signs and safety issues.

Project Title: Green cover for village mini-stadium

Project Description: Sameba village public school had no sports facility in the school territory. They used a small stadium of the village, which was in a bad condition and needed renovation. Students started to advocate for the renovation of the stadium and as a result of successful cooperation with the local government, the decision was made and in May, 2019, a green, soft cover was arranged for the stadium with the help of the local government.

In addition to the rehabilitation activities, students of Sameba village have launched an informational campaign to promote healthy living. Throughout the campaign, the students gathered information about the importance of healthy living, prepared brochures and distributed them in the community, and posted a wall newspaper at school. Additionally, a seminar on the importance of healthy lifestyle was held for younger students.

Samegrelo

Project Title: Green square

Project Description: School-based civics club students of Oktomberi village public school decided to improve the school environment and arrange a small square on school territory.

The students discussed the issue with the school administration, gained their support, and selected a territory for the arrangement of the square. For additional resources, students met with local government and community members and introduced their project. The cooperation was successful and the municipality representative of Oktomberi village gave 4 benches to school. Additionally, the civics club obtained 10 packages of cement for the path and different types of plants from community members.

Within the project, students organized greening and cleaning actions, a film screening, and an information campaign on the importance of environmental protection. In addition, a biology teacher gave a training to students on ecological issues.

Shida Kartli

Project Title: We like our village

Project Description: Civics students of Osiauri village initiated a project to improve ecological conditions in the village. The students decided to arrange a recreation area in the school yard and improve garbage disposal in the village. As a result of successful cooperation with the local government, the students received plants for greening the school yard. Four  additional trash bins were also installed in the village (two aluminum and two plastic). Additionally, students gained support from the school administration for school yard renovation activities.

Projects funded by MAC Georgia

In the second year of the MT program extension, PH International continued fundraising efforts for projects from non-MT sources.

Within the framework of PH’s partnership with MAC Georgia (former McLain Association for Children), using the PH’s online grant making platform, www.initiatives.ge, students and teachers from the MT program partner schools competed for funds donated by MAC Georgia for projects that contribute to more inclusive environments for students with disabilities.

The grant competition, announced in April, 2019, within the framework of the PH-MAC partnership, was open to all current MT schools with the exception of schools in Tbilisi as per MAC’s request. Fifteen schools submitted video proposals for their proposed projects. In September, 2019, MAC Georgia selected five schools as the winners. These were: Katskhi, Merjevi and Salominao public schools in the Imereti region, Benara public school in the Samtskhe-Javakheti region and Kekhijvari public school in the Shida Kartli region. The projects are to be implemented from October, 2019, through March, 2020, and support local, community-led initiatives that contribute to the building of inclusive environments.  Below is an implemented project of the Benara public school:

Project Title: Being an orphan shouldn’t mean being poor

Project Description: Students of the Benara village public school initiated a project to benefit an economically disadvantaged family in the community.

In addition to MAC funding, the students met with local businesses and government representatives to raise funds for the project. The negotiation was successful, as they gained rehabilitation materials from local business and the local government transferred 100 Gel to the family as financial aid.

A cow was purchased with grant money from the project. The family is waiting for a calf in February, 2020, that will create more income for the family.

## 9. Interactive Website and Social Networking

### 9.1 Program websites and social networks

Updating of the Program Websites and Social Networks

To support teachers, students, and parents with professional resources and materials, MT’s website www.civics.ge was updated regularly during the reporting period. The website included media coverage of many different civics events and activities, and featured TV and radio programs with the participation of MT beneficiaries and stakeholders. Videos were featured on MT’s civic initiatives Facebook page (www.facebook.com.civicinitiatives), as well as on the civics.ge video gallery. It should be noted that video coverage materials were mostly viewed from Facebook page. Along with civics.ge, MT also operated a web portal of civic initiatives, www.initiatives.ge, which offered applied learning opportunities to students through mini-grants. Photo and video galleries of the program web portals were regularly updated to reflect the news and recent developments. In addition to www.civics.ge and MT’s Facebook page, the news and stories of the MT program were sometimes also published on www.ph-int.org and the USAID Facebook. The stories were linked to the MT’s Facebook http://www.facebook.com/civicinitiatives

For the second year of the MT program extension, there were 13,592 users on the civics.ge site and 34,914 page views in total.

MT’s social network, http://www.facebook.com/civicinitiatives, has 15,211 likes (1617 new likes in the reporting period).

### 9.2. Online conference

MT organized one online conference during its second year of the program. Online conferences provide an excellent opportunity for students to meet with expert guests regardless of their geographic location. With the use of internet technologies, students can openly communicate their questions and ideas to invited guests.

Guest speakers - representatives of the Public Defender’s Office of Georgia, Maia Gedevanishvili and Gvantsa Ckhaidze, were selected based on the student interest. During the online conference, questions asked by civics club students mostly addressed the current situation in Georgia in terms of protection of human and children’s rights. Students showed interest in juvenile justice, in the issues related to the protection of the victims of domestic violence, asked questions about bullying, children’s labor rights and learned about the steps taken by the Public Defender's Office to protect children’s rights. At the end of the meeting, representatives of the Public Defender’s Office thanked students for their interesting questions and active engagement.

A total of 140 students from 10 regions of Georgia took part in the online conference via Facebook.

## 10. Etaloni Competition

During MT extension year 2, MT started to cooperate with Etaloni Intellectual competition. In this competition, students nationwide answer the questions from different subject disciplines, which are taught at school. Questions about civic education have never been part of this competition. MT, with the help of civics teachers developed quiz questions in civics which will be used in the Etaloni competition to test the knowledge of students in civics across Georgia. This is seen as an opportunity for increasing the motivation of all participant students in Etaloni to learn more about civic education. At the end of the competition, MT will provide the winner students with equipment prizes.

## 11. General/Administrative

### 11.1 Development of promotional materials of the program

This task will be in progress in the next reporting period.

During the reporting period, t-shirts and cups with MT program branding were developed and distributed during the national Civics Teacher’s Conference to the winner teachers in different nominations.

### 11.2. Cooperation with Media

This task will be in progress in the next reporting period.

During the reporting period, news on the MT program activities were covered by TV and radio companies, print media, and online resources all across Georgia.

During the second year of the MT program extension, central TV companies covered information about MT activities 22 times, while regional TV companies covered MT 28 times; 5 articles were published in the newspapers and 13 radio broadcasts were held. An additional 31 instances of online coverage also took place.

In their daily and morning programs, central TV companies promoted the importance of civic education. They invited representatives of the Ministry of Education and Science of Georgia, civics experts, students and teachers, and the MT program and NGO partner representatives to take part in their programs.

The media coverage listed below took place during the 4th quarter of the MT extension year 2. Information about the media coverage of previous quarters is given in the respective quarterly reports.

TV Coverage

On October 15, 2019, the GPB television company, in its midday program, covered the organic food fair in Zugdidi that was organized by school-based civics club students.  The guest of the program was Marina Ushveridze, Chief of Party of USAID's "Momavlis Taoba" program (video is attached).

On November 7, 2019, the TV Pirveli television company, in its morning program, covered information about importance of civic education at schools. The guests of the program were Marina Ushveridze, Chief of Party of USAID's "Momavlis Taoba" program, Simon Janashia, education expert and Tamar Kapanadze, student of Tbilisi public school #97 (video is attached).

On December 2, 2019, the Ertsulovneba television company covered the greening action that the students of Tbilisi public school #119 to prevent landslides around the school (video is attached).

On October 1, 2019, TV4  television company covered students’ visit to the elderly house to mark International Day of Older Persons with beneficiaries (Kvemo Kartli region).  https://www.youtube.com/watch?v=vXrNjd7AYuM

On October 1, 2019, the GPB television company covered the road safety action dedicated to The World Day of Remembrance for Road Traffic Victims. Action was organized in Kutaisi and MT students joined it (Imereti region).

https://www.youtube.com/watch?v=Ttiw7lm4zjU&t=4s&fbclid=IwAR0Usy_K-OpSUNj4wybbGdnNou3YiLFiFc02BlzgXAGVCA1omC9YDGTLEUo

On October 15, 2019, the Rioni television company covered MT students’ study visit to the company’s office (Imereti region).

https://www.youtube.com/watch?v=iupgeczUNiw&t=1s&fbclid=IwAR2kQW3EzOFDl8AK1b9_XRWIPPJsvN5_NbuxgVFcTF5c9QmgPu952cBGyGY

On November 1, 2019, the TV 25 television company covered MT students’ study visit to the company’s office, a visit which was conducted within the framework of MT’s mini-grant project (Guria region).

http://tv25.ge/news.php?lang=ge&id=17217&fbclid=IwAR1XEW_8pm8EYCDiDlyPHuwnsNWbjgaah5KBSHq9tqrlZnrW4_EZtiIWxj4

Radio

On October 15, 2019, Atinati radio’s morning program hosted Tamar Gamsakhurdia, MT mini-grant coordinator, in the Samegrelo-Zemo Svaneti region. Tamar spoke about Jumi village students’ project on the promotion of healthy food in the community (Samegrelo-Zemo Svaneti region).

http://www.radioatinati.ge/dilis-charthva/article/70539-stumari-thamar-gamsakhurdia.html

On October 15, 2019, Atinati radio broadcasted information about the Festival of Healthy Food organized by Jumi village school students within the framework of mini-grant project (Samegrelo-Zemo Svaneti region).

http://www.radioatinati.ge/regioni/article/70548-zugdidshi-jansaghi-kvebis-popularizaciisthvis-mostsavleebma-gamofena-moatsyes-foto-video-.html

On November 29, 2019, Adjara radio hosted civics students from the MT program partner schools of the Adjara region to talk about their civic initiatives and projects (Adjara region).

http://adjaratv.ge/video/7430

On December 7, 2019, NOR radio broadcasted discussions on gender-based violence with Maka Sudadze, the head of the Akhaltsikhe Youth Center (Samtskhe Javakheti region).

http://nor.ge/?p=130284

On December 7, 2019, NOR radio hosted the students of the Akhalkalaki school to speak about gender issues (Samtskhe-Javakheti region).

http://nor.ge/?p=130298

https://soundcloud.com/nor-radio/gosti-studii-sirushik-i-lamara-uchenitsy-11-klassa-russkoy-shkoly-akhalkalaka

Newspapers

On November 2019, “Ai Ia” newspaper published an article about Kekhijvari village public school student Mariam Nazarova and her civics activities. (Samtskhe-Javakheti region).

(article is attached)

Online Media

On November 1, 2019, the Shida Kartli Information Center web page shared information about the mini-grant projects initiated by students of the public schools of  Sasireti  and  Kvemo Gomi villages (Shida Kartli region).

https://www.qartli.ge/ge/component/content/article/13062-sasirethis-da-qvemo-gomis-skolebi-momavlis-thaobis-konkursis-gamarjvebulebi-gakhdnen

On December 17, 2019, Public Defender office’s Facebook page shared information about the meeting of Public Defender with civics students (Shida Kartli region).

https://www.facebook.com/pg/OmbudsmanofGeorgia/photos/?tab=album&album_id=2546927708678076&__tn__=-UCH-R

On September 28, 2019, the Kaspi Education Resource Center shared on its Facebook page information about the cooperation of Kaspi schools with the MT (Shida Kartli region).

https://www.facebook.com/346233756315176/posts/390105745261310/?sfnsn=mo

On November 12, 2019, etaloni.ge published an article about the “Youth Change the Environment” project implemented by civics students of Mlashe village public school (Samtskhe-Javakheti region).

https://www.etaloni.ge/geo/main/index/31508?fbclid=IwAR2pwfynv1j31bErnKsOQFHaUOaS2gzExulf0L8tHH8EImrp_Jinv44u-MU

On November 19, 2019, etaloni.ge published an article about the “I Choose Equality” campaign implemented by civics students of Aghaiani village public school (Shida Kartli region).

https://www.etaloni.ge/geo/main/index/31991?fbclid=IwAR299m9_zwoRpSta26YY6gwRRF41F88793FYCmEbyh9q8gTetKKkWw6WhP8

On October 15, 2019, www.1tv.ge published information about the Festival of Healthy Food organized by Jumi village school students, which was implemented within the framework of a mini-grant project (Samegrelo-Zemo Svaneti region).

https://1tv.ge/news/zugdidshi-sasoflo-sameurneo-produqtis-gamofena-gayidva-gaimarta-foto/

### List of attachments:

- Attachment #1 (e-copy only) – MT extension Partner Schools List

- Attachment #2 – Agenda of the Annual Civics Teachers Fair-Conference

DVD with photos and media coverage materials of MT events.