Momavlis Taoba (Future Generation) Program

U.S. Agency for International Development

Cooperative Agreement AID-114-A-14-00006

AWARD PERIOD:  June 30, 2014 through June 15, 2021

MT extension Y3 Annual Report

Reporting Period: January 2020 – December 2020

Prepared for

USAID/Georgia

United States Agency for International Development

ATTN: Nino Buachidze, AOR

11 George Balanchine St.

Tbilisi 0131

Prepared by

PH International

Project Harmony, Inc.  
5197 Main Street, Unit #6

Waitsfield, VT, 05673

January 30, 2021

This report was produced for review by the United States Agency for International Development. It was prepared by PH International.

Table of Contents

List of Acronyms................................................................................................................................................iv

I.	Overview of the Momavlis Taoba Program	6

II.	Tasks Completed in the Reporting Period	7

1.	Communication with Partner Schools	7

2.	Monitoring visits to observe the use of MT civics supplemental textbooks in the classroom	8

3. Teacher Training	9

3.1. Core training and additional training	9

3.2. Additional Trainings for Civics Teachers	10

3.3. Support to teachers in distant learning/ teaching tools	11

4. Coordination with and capacity building of MESCS to play an expanded role in	11

national civic education efforts	11

4.1. Support to government civic education policy-making and implementation	11

4.2 Local Consultancy to MESCS	12

4.3 International Consultancy to MESCS	13

4.4. Technical Assistance to MESCS	14

5. Coordination with capacity building and activities of Civics Teachers Forum (CETF)	15

5.1. The role of the Civics Teachers Forum in the development of civic education in Georgia	15

5.2. Subgrant in support of relevant CETF programs	16

6. Applied Learning	19

6.1 NGO partners work to promote implementation of the MT program in regions	19

6.2. Equipment Contest for Schools and Civics Teachers	25

7. Mini-Grants for Students Activities	27

7.1. Education of students, teachers, and communities on mini-grants program	27

7.2. Functioning and management of mini-grant program to students and/or	27

student-teacher groups	27

7.3. Monitoring and evaluation of mini-grant component	32

7.4. Funding of the mini-grant proposals from sources outside MT program	32

8. Interactive Website and Social Networking	33

8.1 Program websites and social networks	33

8.2. Online conference	34

9. Etaloni Competition	36

10. General/Administrative	36

10.1. Cooperation with Media	36

Attachment:	38

List of Acronyms

MT – Momavlis Taoba (Future Generation Program)

PH – Project Harmony, Inc (PH International)

MESCS – Ministry of Education, Science, Culture and Sport of Georgia (name of the Ministry of Education and Science after the merger with the Ministry of Culture on July 14, 2018)

CETF – Civic Education Teachers’ Forum

CDT – Curriculum Development Team

ToT – Training of Trainers

ERCs – Educational Resource Centers of the Ministry of Education, Science, Culture and Sport of Georgia

Partner NGOs – program’s partner non-Governmental organizations in Tbilisi and other regions

ACETT - Applied Civic Education and Teacher Training Program

MAC - McLain Association for Children

## Overview of the Momavlis Taoba Program

The Momavlis Taoba Program (MT), funded by the United States Agency for International Development (USAID), is implemented by PH International. The program is supported by the Ministry of Education, Science, Culture, and Sport of Georgia. The program aims to 1) promote greater civic engagement of young people; and 2) enhance civil society’s role in promoting transparent and accountable governance at the national and local levels by expanding and institutionalizing secondary school civic education curricula and its practical applications. The program was built on the progress made under ACETT, which worked with civics teachers and students in approximately 30% of schools in Georgia. Through the initial MT award, the program reached another 20% of secondary schools (480 schools) throughout the country. Now, in the MT 3-year extension period, the program works with an additional 10% of secondary schools (230 schools), improving the quality and scope of school-based civic education as a means to positively influence the knowledge, attitudes, and behaviors of youth (and, through their example, those of the broader community) as active participants in Georgia’s democratic society. MT introduced additional approaches or variations to promoting applied learning by students in school civics classes, seeking to find the best approach or combination of approaches for maximizing the translation of learning into action. The program included schools in all 11 regions of Georgia: Tbilisi, Adjara, Guria, Imereti, Kakheti, Kvemo Kartli, Mtskheta-Mtianeti, Racha-Lechkhumi, Samegrelo-Zemo Svaneti, Samtskhe-Javakheti and Shida Kartli. PH partnered with regional NGOs to take advantage of their knowledge of regional differences and approaches to mobilize collaboration among young people, civil society, local authorities, and other stakeholders in ways that increase citizen engagement. PH International worked closely with its Georgian partner, the Center for Training and Consultancy (CTC), to accomplish the objectives of MT.

The MT extension, which is consistent with the scope of the initial MT award, further strengthens and consolidates its major activities and enables PH to accomplish MT results through an integrated set of program activities that include:

(1) selecting and working with 230 schools in Georgia to engage teachers, students and communities as partners in civic education and practice;

(2) updating (as needed) and delivering a modern teacher training course for civics teachers from project schools to assist them in better meeting civics curriculum goals for students;

(3) providing the new 230 schools with four high quality, interactive resources developed under ACETT and updated under MT to supplement and enhance existing, approved civic education textbooks and teaching resources. These resources (textbooks) are: “How Can I Become an Active Citizen”; “Cooperation for Community Benefit”; “Cooperation with Local Government and Media” and “Participation in School’s Self-Governance”;

(4) working with the Civics Teachers Forum and the Ministry of Education, Science, Culture & Sport (MESCS) to provide a sustainable system of supportive resources and incentives to civics teachers through an interactive website, peer skills development using professional learning community meetings and model lesson approaches, mentoring, and annual professional recognition awards;

(5) introducing varied approaches that encourage and support students from participating schools in applying their civics lessons into practice in their schools and communities, as well as local NGO and mini-grant support for teacher and student-created projects;

(6) holding multiple local, regional, and national activities including competitions, civics club fairs and other programs that further stimulate and reward the civic engagement by youth;

(7) working with MESCS to stimulate improvement of civic education in all secondary schools throughout the country and to prepare MESCS for the implementation of best practices as demonstrated through USAID civic education programs; and

(8) raising public awareness about the importance of civic education through media and other channels (TV, radio, print media, online sources, and social media).

PH International works closely with its Georgian partner, the Civic Education Teachers Forum (CETF), and regional partner organizations to accomplish the program objectives of MT.  The program is managed from PH International’s Country Office in Tbilisi, with contractual relationships with USAID managed from PH International’s US based headquarters located in Waitsfield, Vermont.

## Tasks Completed in the Reporting Period

## Communication with Partner Schools

This task is in progress and will continue over the upcoming quarter.

In the reporting period MT and its partner NGOs maintained regular communication with teachers, students and school administration officials in all respective regions of Georgia. After the COVID-19 pandemic started in March 2020, schools switched to a distant learning model.

MT team started to support civics teachers and students in the process of switching to the distance learning classes: MT created digital resources for civics teachers and students and shared these  through its website and social networks; based on teachers’ needs survey, organized online seminars for civics teachers on the use of MS TEAMS online teaching program; conducted online conferences with participation of expert speakers for civics students, teachers and parents; provided classroom monitoring visits in an online format; supported students and teachers in the process of implementation of small grant projects, civics club projects and civics classroom projects in online format. In fall 2020, some schools started teaching in the face-to-face format, while schools in big cities continued to teach online, as per Government’s decree. MT provided the needed support to all schools in civics teaching and activities adapted to both, distant and face-to-face teaching formats.

In September, PH International applied to USAID with a request for a no-cost extension of the MT program as COVID-19 resulted in changes in the implementation of different components of the program. Consequently, more time was needed to ensure all components are completed successfully and with reported results. USAID approved a no-cost extension on November 13, 2020. MT staff and contractors (in all components of the program) were given more time to complete all activities and deliver the planned results. MT program will be completed on June 15, 2021.

## Monitoring visits to observe the use of MT civics supplemental textbooks in the classroom

This task is in progress and will continue over the upcoming quarter.

In the reporting period, MT had to modify the format of its monitoring visits to schools. Schools switched to online/distant teaching due to the pandemic. MT also adjusted the format of its curriculum monitoring visits to an online monitoring format. A total of 44 visits were carried out in fall 2020, of which 40 were online visits and 4 were face-to-face visits in schools which still kept teaching in school buildings.

Curriculum monitoring visits did not take place in spring 2020 as schools were having difficulties in transitioning from “normal” teaching to distance teaching, facing numerous challenges. In spring 2020, MT supported teachers through webinars and online teaching resources. The online teaching situation got much better by fall 2020, when teachers had improved their skills, and MT experts were able to observe online civics classes with the use of MT textbooks.  Of the 44 visits, 11 took place in ethnic minority schools.

The visits included the observation of the civics lessons by experts and discussions with teachers and students to evaluate the strengths and weaknesses of the process, identify the needs, and give recommendations for the improvement of future lessons. Experts also spoke with teachers about project-based teaching and provided recommendations for project-based teaching.

Teachers mentioned to experts that supplemental textbooks provide important information which is not available in licensed textbooks. These textbooks help to increase the knowledge of students and positively affect their civic attitudes. Supplemental textbooks help to make lessons more interesting for students as students like the practical activities. Students mentioned to experts that they share the knowledge gained at civics classes with their parents and siblings at home.

In most cases experts gave recommendations to teachers about lesson planning, which includes identification of the lesson goals and relevant activities. They also provided recommendations on how to increase student involvement in class discussions, and advised the use of different resources for making lessons more interesting for students. The experts also spoke with teachers about student assessment and self-assessment.

Teachers welcomed the feedback and recommendations received during the monitoring visits. MT curriculum development team members will continue monitoring visits in the upcoming quarter.

## 3. Teacher Training

### 3.1. Core training and additional training

This task is completed.

Since schools have autonomy in appointing civics teachers each academic year and civics teachers cannot get a full-time work schedule by only teaching civics, the turnover rate for civics teachers in schools is quite high. Because of this, MT needs to ensure that all teachers involved in the program receive core training. For this purpose, MT’s partner CETF, under the guidance of PH International, provided additional training courses to newly-appointed teachers as well as to other civics teachers from MT’s partner schools who hadn’t yet had a chance to participate in these trainings during the previous academic year.

In the reporting period, 43 civics teachers were trained in the MT core training course,  “Teaching Democratic Citizenship,”  and 49 civics teachers received a two-day training in MT supplemental textbooks and materials. These teachers were trained in different training sessions, as described below:

MT core training sessions “Teaching Democratic Citizenship” took place in two parallel training sessions in Tbilisi and in Marneuli on February 15, 16, 22 and 23. In Marneuli, the training was conducted in the Azeri language with participation of ethnic Azeri teachers. A total of 13 teachers were trained through both core training sessions.

In the fall semester of 2020, two additional core training sessions were held in Tbilisi for those MT civics teachers who newly joined schools as civics teachers and/or for those who were not able to participate in  a previously offered core training. One training (on October 3, 4, 10 and 11) took place in face-to-face format and another one was online (on November 29, 30 and December 5, 6), due to the new COVID-19 related restrictions announced by the Government of Georgia. A total of 30 teachers received core training in the fall semester of 2020.

Teachers evaluated the trainings positively. Maia Koplatadze, civics teacher from the village Beindari public school said: “Most recently, a month ago, I returned to the learning environment as a teacher. I will never forget the fruitful hours of this training. Ms. Nino Beselia did her best to teach us as much as possible. Not only about interactive lesson planning, but also about situational tasks management, assessment rubrics and a lot of things I didn't know about before ... I cannot thank PH International and CETF enough for giving me an opportunity for restarting my professional career.”

In addition to the core training, a two-day training about MT supplemental textbooks and materials was held in Marneuli in the Azeri language for 4 civics teachers from Azeri sector  schools in spring semester of 2020 (February 29 and March 1, 2020). Two more two-day trainings were held in fall semester of 2020 with participation of a total 45 teachers. These trainings took place online on November 14, 15 and December 19, 20, 2020.

### 3.2. Additional Trainings for Civics Teachers

This task is in progress and will continue over the upcoming quarter.

MT constantly studies the needs of teachers and tries to design the training programs to help teachers improve their skills and knowledge. Based on high interest from the side of teachers, a training program was designed in the framework of MT in complex assignments and student assessment methods.

Two trainings (on November 7, 8 and December 5, 6) and a webinar (on December 24, 25) were held in “Complex Assignments and Student Assessment”.

A total of 222 teachers participated in both of the trainings as well as the webinar. Participants included teachers from MT partner schools as well as civic teachers from other schools of Georgia.

In addition to the above trainings, a training program in “Teaching with Cases and Dilemmas” was designed. The program was designed in the framework of MT by Sofiko Lobzhanidze, Head of the Ilia State University’s School of Education with active participation of civics teachers from CETF. The training was conducted online on November 14 and 15 in Microsoft TEAMS program. There was also an independent group work of teachers during the training. Twenty-five teachers from MT partner schools, who first registered for the training, were able to participate.

“We learned about the case-based teaching method, learned how to create a complex assignment, how to teach with dilemmas, and what type of dilemmas exist. We also learned how to use cases and dilemmas in a complex assignment. I liked every part of the training, especially Kohlberg’s theories of moral development. I will definitely use case studies in complex assignments.”- said Elene Ogbaidze, civic education teacher from Kakheti Region

“The training turned out to be very interesting and fruitful for me. We discussed the basic principles of constructivism, different teaching styles, spoke about willingness and interest, and discussed problem-oriented teaching and the needs of teaching through cases and dilemmas. We learned about the types of complex assignments, indigenous ideas and target concepts, discussed practical examples, and shared experiences that I will definitely use in my practice, both during online teaching and after returning to face to face teaching at school” – said Manana Begadze, civic education teacher from Tbilisi (Shindisi)

### 3.3. Support to teachers in distant learning/ teaching tools

This task is in progress and will continue over the upcoming quarter.

Due to COVID-19 all teachers across Georgia, and among them civics teachers too, started to face a new and unexpected dilemma – the need to master online teaching tools. To support civics teachers in quickly adjusting to the new realities of online teaching, MT posted a survey in a civics’ teachers group on Facebook, asking the teachers to name online platforms in which they need  training. Most of the teachers named Microsoft TEAMS program.

To respond to the critical need of teachers, MT identified a civics teacher as a trainer, Temur Sukashvili, who efficiently uses TEAMS program daily to conduct civics online lessons with his students. Under the guidance of MT and in cooperation with CETF, Temur Sukashvili developed a plan for webinars to be conducted for civics teachers about the use of the TEAMS program.

MT organized three webinars for civics teachers about the use of Microsoft Teams Program for online teaching. A total of 150 civics teachers participated in the webinars. Participant teachers actively asked questions and received answers from the trainer. Temur Sukhashvili led webinars on;

- Basic functions of Microsoft Teams Program: setting the calendar, assignments, screen sharing and student evaluation forms;

- How to make quizzes in TEAMS and give assignments in the Microsoft Teams program;

- The use of MT’s digital resources in online lessons in Microsoft Teams program;

The webinars were recorded and uploaded in the video gallery of MT’s civic education platform www.civics.ge for those teachers who did not have an opportunity to view the live webinars.

To provide support to teachers in online teaching tools and resources, MT began to digitize its supplemental textbooks in a format of quizzes. Students are given the opportunity to read the material and answer the questions to test their knowledge. Chapters from MT textbooks are prepared on a Quiz Maker platform. These resources were uploaded to the digital materials section on MT’s website www.civics.ge and were also shared with civics teachers in the civics teachers Facebook group and through MT’s Civic Initiatives Facebook page.

In addition, civics expert Sopo Bachilava, with support from CETF, developed 10 complex assignments for civics courses based on MT supplemental texbtooks. These will be uploaded on MT website and in other channels.

## 4. Coordination with and capacity building of MESCS to play an expanded role in

## national civic education efforts

### 4.1. Support to government civic education policy-making and implementation

This task is in progress and will continue over the upcoming quarter.

In June, 8 regional civics teachers’ roundtable meetings were held to discuss the need for new policies/approaches to improve the quality and scope of school-based civic education. Topics of discussion included possible civics design in a high school, civics project activities at school and civic education for the national examinations. Prior to the roundtable meetings, a team comprised of MT Chief of Party Marina Ushveridze, CETF Executive Director Maka Bibileishvili, Civics and History Expert of the National Curriculum Department at MESCS Shalva Mekravishvili and civics experts Nino Chiabrishvili and Aluda Goglichidze worked on a questionnaire for teachers. Teachers were asked to fill out the questionnaire and provide their opinion about the need of the new policies to further support school-based civic education.

Civics teachers roundtable meetings, which were held online, included the teachers from the following regions: Kvemo Kartli, Kakheti, Adjara, Imereti, Guria, Shida Kartli (included teachers from Samtskhe-Javakheti), Samegrelo-Zemo Svaneti and Tbilisi. A total of 200 teachers took part in roundtable discussions.

Recommendations, developed based on the roundtable discussions and feedback, provided by teachers through questionnaires, were shared with the Ministry of Education, Science, Culture and Sport of Georgia.

As a result of the National Civics Conference, which was held in 2019, recommendations for the improvement of civics teacher in schools were developed and shared with MESCS in 2020 in the reporting period. Recommendations were based on a survey of hundreds of civics teachers and include the following: the need to attract a younger cohort of teachers into civics teaching who could teach civics at different school levels (primary, middle and high school); mandatory number of weekly teaching hours; how to avoid the misuse of civics for filling out “hours” of other subject discipline teachers; what steps shall be undertaken by MESCS for professional development of civics teachers; the need to emphasize the importance of civic education by MESCS; recommendations for changes in the Teachers’ Professional Development Scheme to improve the system of motivation and support for teachers’ professional development; recommendations for the creation of a culture of cooperation at schools; and others.

### 4.2 Local Consultancy to MESCS

During the reporting period, MT continued to provide technical consultancy to MESCS regarding its annual programs in civics. Civics expert Nino Chiabrishvili worked together with MT-selected civics teachers Sopo Bachilava and Bakur Khijakidze. The team of authors developed sample thematic programs - “Environmental Protection” and “Peace Processes” - for the MESCS’s new “Citizenship” course.

At all stages of the work, the Civics Expert at MESCS, Shalva Mekravishvili, provided feedback to the workgroup and at the end of the process approved the thematic program.

With this local consultancy, MT helped to facilitate the introduction of the national civics curriculum in schools, as annual programs help teachers to take concrete steps and activities for achieving the curriculum goals in the classroom.

To address the challenges caused by the pandemic and school closures, in March 2020,MT hired a civics expert to support MESCS’s TV school project and provide technical expertise in preparation of civic education videos for the project. The TV school project was initiated by MESCS in cooperation with the TV Georgian Public Broadcaster to facilitate the distant teaching process during the pandemic. The project was designed to enable all students across the country, regardless of their access to the internet, to listen to lessons while  schools are closed due to the pandemic.

With support of MT, 18 videos on different topics of civic education were broadcasted on TV. These included videos on: Corruption; Domestic Violence; Ecological Problems; Equality And Prevention Of Discrimination; Violent Extremism And Radicalization; Citizenship - Citizens' Rights And Responsibilities; Early Marriage; Promotion Of A Healthy Lifestyle Among Youth; Cultural Heritage; Elections And Importance Of Voting; Georgia's Integration With European And North Atlantic Structures; Charity; Volunteering; Assertiveness; and Freedom Of Expression.

“It’s exciting to realize that in this critical and challenging situation caused by COVID-19, which is often compared to an invisible enemy, you are an ordinary soldier. Together with doctors, police officers, border guards and soldiers, your country needs you. This significantly raises your motivation…I think that civics has become a subject of the special importance for raising citizens” -said Shorena Tabatadze, MT-supported civics teacher from TV school project.

### 4.3 International Consultancy to MESCS

In January, PH posted an announcement for International Civics Consultant at PH International’s website and Linkedin accounts. The announcement was also shared at other relevant organizations’ websites:  Center for Civic Education (www.civiced.org), Close Up (www.closeup.org), American Political Science Association (www.aspsanet.org), Association of American Colleges & Universities (www.aacu.org), and was circulated through professional networks of the German Agency of Civic Education and through its Eastern European Network for Citizenship Education.

By the deadline, a total of 10 applications were submitted. PH, in close coordination with MESCS, shortlisted 4 applicants, which were interviewed online in the month of March. Katherine Cadwell was selected as the best candidate by a mutual consent of PH and MESCS and a civic education consultancy service contract was signed with her.

Ms. Cadwell  was tasked to develop a guide with recommendations to increase the quality of civic education in Georgian schools tailored to the current realities and evolving needs of school-based civic education in Georgia. Recommendations outlined in the guide should  be based on careful analysis of the current situation in Georgia, and should provide practical examples illustrating how the challenges of implementing civics education can be resolved. Ms. Cadwell started her work with the review of the civic curriculum and related materials provided by MESCS and held regular online meetings with Shalva Mekravishvili, civics expert from MESCS, and Marina Ushveridze, MT Chief of Party.

Since travel was not allowed due to COVID-19, Ms. Cadwell, with assistance of MT staff, organized in total 4 online meetings with the heads of Education Resource Center (ERC), school principals, civics teachers and students. Meeting participants shared practical examples of successful civics projects implemented under PH’s civic education programs, discussed current realities in school-based civic education, talked about the challenges and discussed successful models of civic education. In total seven students, four school principals, six civics teachers and four heads of ERC participated in different online meetings.

Ms. Cadwell developed and submitted drafts of the Civics Guide, which were commented on by MESCS civic expert Shalva Mekravishvili and MT Chief of Party Marina Ushveridze. At different stages of the work, Ms. Cadwell made the needed changes per recommendations.

On December 21, 2020, the consultant met with the Deputy Minister of Education, Science, Culture and Sport Ekaterine Dgebuadze. The meeting took place online. Other officials from PH International and MESCS also participated in the meeting. The parties  discussed the progress made up to this point in the  civics international consultancy to MESCS and covered development of the civics guide which will include recommendations for schools and for MESCS for improving quality of teaching of civic education. The parties shared with each other their vision regarding school-based civic education’s future in Georgia and mentioned that the Guide will be finalized in February 2020.

### 4.4. Technical Assistance to MESCS

In the spring of 2020, MT had a meeting with the new Deputy Minister of Education, Ekaterine Dgebuadze, in which the parties discussed the technical support that MT provides to MESCS, including the school initiatives website. The new Deputy Minister expressed readiness to cooperate with MT and agreed to continue the cooperation, which started during the previous management of MESCS.

The PH-contracted company Circle Ltd, in close coordination with the MT team and MESCS, completed the development of the school initiatives website (MESCS grant portal for schools). MT first tested the website, and then, following the request from MT, MESCS tested the website and approved it. The school initiatives website was then handed over to MESCS. PH International, MESCS and Circle Ltd signed a handover letter.

MT started work on the Project Development and Management Manual for MESCS. The Education Development and Employment Center was contracted to develop the manual under close supervision from MT. MT shared draft versions of the manual with MESCS and incorporated recommendations provided by MESCS into the manual.   Narrative of the manual was approved by MESCS in the reporting period. The manual will go through editing, page design and once finalized, will be handed over to MESCS to help schools design new projects and initiatives. The MESCS-PH agreement about cooperation also includes training on project proposal writing and website use for the staff of Educational Resource Centers and/or other designated by MESCS participants.

## 5. Coordination with capacity building and activities of Civics Teachers Forum (CETF)

### 5.1. The role of the Civics Teachers Forum in the development of civic education in Georgia

This task is in progress and will continue over the upcoming quarter.

In the reporting period, MT continued to work with CETF, assisting the organization in expanding its activities to more schools as well as reaching more teachers. The Civic Education Teachers' Forum held two meetings of the Regional Council Chairpersons in the reporting period. Meetings were held in a ZOOM platform and ongoing activities and future plans of MT and CETF were discussed. During these meetings, teachers actively spoke about adjusting the planned activities in an online format.

The participants also discussed the membership packages. It was decided that from 2021, in agreement with the board, the members of the organization will be re-registered and those who do not pay membership fees may no longer be able to keep their membership. Meeting participants also discussed amount of membership fee.

In the reporting period, MT provided constant support to CETF, including staff salaries, office rent and professional networking. Such support empowers CETF in its fundraising efforts. In addition to offering professional development activities to MT teachers, CETF also continued to provide professional development support to other civics teachers in Georgia.

In the reporting period CETF submitted project proposals to different donor organizations. Below is a description of the projects, which were funded and are ongoing:

In March – October 2020, CETF carried out a project „Civic Education against Disinformation about EU-Integration“, funded by the Lithuanian Foreign Ministry.

CETF’s project „Demystifying Gender - for an open classroom debate“, funded by the Roving Ambassador of Finland to the South Caucasus, was extended  due to COVID-19 and will be completed in May, 2021.

CETF implements a project „Joint Initiative Against Radicalization and Violent Extremism“,  supported by the Ministry of Foreign Affairs of the Kingdom of Norway.

CETF, together with the Georgian National Bank and the German Savings Bank Foundation, agreed to start another round of Teacher Trainings in the field of economics and basic financial education. The aim is to train another 300 more civics teachers.

In 2021 and 2022, CETF will host 2 international volunteers (each year) from the European Solidarity Corps „Volunteer Program“. Volunteers will support CETF in its daily activities and in fundraising. They will also meet with teachers and talk with them about volunteering.

Brot für die Welt, through its Complementary Measures Program, will support CETF staff meetings with teachers in different regions of Georgia on simulation methods in teaching. These activities could not be implemented as per COVID-19 related restrictions and are postponed until 2021.  Brot für die Welt will also provide support to CETF in revising and updating its online tools: webpage and e-learning platform in 2021.

In February 2020, CETF started implementation of the project „1+1 Synergy for Democratic Culture“ in cooperation with „Youth for Peace and Equality“ and funded within the Erasmus+ Program of the European Commission. A conference was organized in February at Teachers‘ House, where all the national and international partners (Czech Republic, Norway, Spain) of the project presented their work regarding the „Competences for Democratic Culture“ at schools. In March CETF organized the first Training Course in Rustavi for 29 participants from Czech Republic, Georgia, Norway and Spain. Due to the Covid-19 pandemic and related restrictions, project activities continue at the local level and the project timeframe was prolonged.

CETF established contact with the Teacher Training Department of the University Munich, Germany. Two members of CETF participated as guest speakers in the project „Global Talks“, wich aims to mainstream Education for Sustainable Development within the teacher training.

CETF launched its own Facebook page

https://www.facebook.com/pg/civiceducationteachersforum/ where it shares information about ongoing projects and activities.

### 5.2. Subgrant in support of relevant CETF programs

This task is in progress and will continue over the upcoming quarter.

National Fair-Conference of Civics Teachers

Competition for the Best Civics Teachers was announced in February 2020. Applications from teachers were received and discussed by the selection committee in different meetings. Selection Committee members include Shalva Mekravishvili, civics expert at MESCS, Marina Ushveridze, MT Chief of Party, Maka Bibileishvili, CETF’s Executive Director, Nino Beselia, civics expert, teacher trainer and MT curriculum development team leader, Nino Gvaramadze, civics expert at Teachers’ Professional Development Center and curriculum author, Manana Jincharadze, civics expert and teacher trainer and Tamuna Pruidze, Regional Networking Manager of MT.

The committee discussed teachers’ applications in detail, checked the records of classroom observation visits, mini-grant implementation records, spoke with regional implementing partner NGOs to evaluate initiatives undertaken by civics teachers in facilitation of civics classroom and civics club projects and selected civics teachers for awards in different nominations. Some of the candidates still need to be confirmed after classroom observation visits.

Winner teachers were planned to be awarded at the Annual Conference of Civics Teachers on May 23rd, but the conference was postponed due to COVID-19 related restrictions, announced by the Government of Georgia. MT made efforts to arrange a conference in fall 2020, but epidemiological situation and the due restrictions did now permit holding the  conference. Since MT received time extension from USAID, it was agreed that Civics Teachers National Conference will take place in spring 2021 if COVID-19 related situation allows. If the epidemiological situation does not improve, the conference will be held online.

In December, a competition for civics teachers for their work carried out in 2020 was announced in the framework of MT. The winners will also be awarded at the National Civics Teachers' Conference in Spring 2021.

Open (Model) Lessons

In May open lessons were held in the framework of MT in the following 8 regions of Georgia: Tbilisi, Imereti, Samegrelo, Kakheti, Shida Kartli, Kvemo Kartli, Guria and Adjara.

The goal of the open lessons is to share the best practices among civics teachers, receive recommendations from experts and feedback from colleagues. All eight open lessons took place through Microsoft Teams program. Teachers demonstrated the use of MT supplemental textbooks in a civics class, showed their colleagues different techniques used in distance teaching process and received feedback from experts about the lessons. These open lessons were especially important in times of school closures during spring 2020 as most of the teachers were experiencing many difficulties in the process of online teaching.

A total of 204 civic education teachers attended the model lessons in 8 regions.  MT curriculum authors and civics experts, Nino Gvaramadze, Nino Beselia and Aluda Goglichidze helped teachers in preparation of open lessons and  provided feedback.

"The global pandemic era, which unfortunately has become part of our daily routine, has posed new challenges for the education system, and distance learning has become a tool to deal with these challenges. Many thanks to MT program, to the teacher and expert for providing this opportunity to share professional experiences.“ – said Shakro Kartsivadze, civics teacher from the village Kakuti Public School in Kobuleti municipality.

Another round of civic education online open lessons was organized in December, again by the use of Microsoft TEAMS program.  In these lessons as well, with the help of experts, teachers prepared for the lessons and demonstrated the use of MT supplemental textbooks in lessons. At the end of each lesson, experts provided their feedback and colleague teachers shared their reflections.

A total of 183 civic teachers participated in 7 civics open lessons.

"I attended the open lesson conducted by Nino Beritashvili and am very satisfied with this lesson. The topic of the lesson was discrimination "Everyone is Different, Everyone is Equal". My attention was drawn to the well-defined purpose of the lesson. The main goal of the lesson was to help students understand democratic values and learn about discrimination, also explain about human rights violations. I liked the active involvement of the students, the reasoning, attitude towards the issue and timely and appropriate feedback that the teacher provided. After the open lesson, Ms. Nino Beselia discussed the flow of the lesson and gave her feedback.

I want to thank you for allowing me to attend such an interesting lesson." – said Tamar Aslanishvili, a civics teacher from Tbilisi N129 Public School.

"The management of the teaching process using online platforms is a challenge for teachers.  I think the lesson was a clear confirmation that the teacher has successfully coped with this difficulty. Open lesson was very interesting and impressive. I especially liked the teacher's focus on sharing students’ emotions. Not only online, but in a physical school environment I will devote more of my time to enable children to boldly express their attitudes.”

I really enjoyed watching how students use online space for group work. I have not yet used this method in MS Teams and I will definitely incorporate it into my practice. The topic and goal of the lesson were clear and the process was very flexible."- said Ia Kashia, civics teachers from Kutaisi Public School N36

There is one more open lesson planned, which will take place in Kvemo Kartli Region in the upcoming reporting period.

Professional Learning Community meetings

Based on the interest of teachers, online teaching was selected as a topic for professional learning community meetings, which were held in July 2020 in the framework of MT. In these meetings teachers discussed the challenges, which they face in the process of distance and online teaching. Educational expert, Simon Janashia, who gave teachers recommendations on how to plan and conduct more effective, interesting and interactive online lessons and how to promote students' motivation, engagement and achievements. Regional representatives of CETF facilitated professional learning community meetings. Professional learning community meetings were held for teachers in the following regions: Tbilisi, Kakheti, Guria, Imereti, Samegrelo-Zemo Svaneti, Adjara, Shida Kartli, Kvemo Kartli, Samtskhe-Javakheti and Mtskheta-Mtianeti.

“Professional learning community meeting turned out very important for me. We have discussed the challenges, which teachers face in online teaching. Many of these challenges I face in my daily practice. I heard my colleague teachers’ opinions about distance learning, about student motivation and involvement, about parental attitudes, teacher’s role, knowledge of online teaching tools. I have very much appreciated recommendations of Mr. Simon Janashia about the above issues. The knowledge gained at this meeting will help me to grow professionally. I am thankful to organizers of this event and hope there will be more such events in the future!” – said Tamila Rionidze, civics teacher of the village Chaisubani school.

Annual Bulletin

CETF’s next annual bulletin was published in the reporting period. It covers the work of MT in the interview with MT Chief of Party Marina Ushveridze, news in the field of school-based civic education, an interview with CETF’s Executive Director Maka Bibileishvil and an interview with the newly-appointed Deputy Minister of Education, Science, Culture and Sport, Ekaterine Dgebuadze about school-based civic education.

Annual bulletin can be viewed at https://www.civics.ge/forum-newsletters/

Discussion Meetings for Civics Teachers

Under the framework of MT, CETF in cooperation with Sulkhan Saba Orbeliani University,

held two discussion meetings with civics teachers: 1. Challenging teachers and education workers around the world due to the coronavirus pandemic and 2. Entrepreneurial skills for teachers.

## 6. Applied Learning

### 6.1 NGO partners work to promote implementation of the MT program in regions

This task is in progress and will continue over the upcoming quarter.

On January 16 -17, 2020, MT organized a two-day meeting with regional implementing partner NGOs. Meeting participants discussed ongoing activities, challenges, and best practices in stimulating civic engagement of youth. During the meeting, the MT team, together with partner NGOs, finalized the list of equipment contest winner schools and teachers.

In January-February 2020 MT end-of the semester events were held in 8 regions of Georgia. These events featured presentations of successful projects and initiatives carried out by students and civics teachers. Students and civics teachers were awarded with certificates for their successful participation in the program. Students, civics teachers, parents, school administrators and local government, NGO, and MESCS representatives (regional educational resource center representatives) took part in these events.

Due to the new realities caused by COVID-19 in the country, from March 2020, MT partner NGOs continued to support implementation of planned initiatives and classroom projects of school-based civics clubs in an online format. Civics classroom and civics club projects were carried out online by students in all MT regions through March – June 2020 and continued in the new academic year online in large cities (Tbilisi, Rustavi, Kutaisi, Gori, Zugdidi, Poti) and in Adjara region as per governmental regulations.

In the reporting period, NGO partners supported the work of 230 school-based civics clubs with the participation of 3,304 new member students. In addition, NGO partners supported a total of 426 initiatives implemented by school-based civics clubs to promote civic education among 1,695 beneficiaries. Of these, 1,015 were girls, 680 were boys and 242 were national minorities (4th quarter numbers are: 184 events for 1,221 beneficiaries). The beneficiary number includes duplicates, as very often the same students participate in more than one civics activity during the academic year.

Besides the civics clubs’ initiatives, NGO partners supported the implementation of 718 classroom projects among 2,342 beneficiaries. Of these, 1,296 are girls and 1,046 are boys, and 462 are national minorities (4th quarter numbers are: 322 classroom projects for 2,088 beneficiaries). Events included students’ initiatives to promote healthy lifestyle, healthy nutrition and road safety, students’ activities for gender equality, student actions to promote democracy, voting and human rights, student actions to combat violence against women, student actions against bullying, students’ initiatives to promote media literacy, cyberbullying and  Georgia’s Euro-Atlantic integration,  students’ advocacy efforts to improve the environment, student discussions on early marriage, trafficking and migration, the preventive measures against the spread of COVID-19, contests on COVID -19 prevention, quizzes on civic education topics and online celebration of important international days by students such as World Autism Awareness Day, World Tuberculosis Day, Women’s International Day, International Day for the Protection of Children, World No Tobacco Day, Earth Day, the 25th anniversary of April 9 tragedy, International Day Against Drug Abuse, International Youth Day, Clean the Earth, Illicit Trafficking, European Day Without A Road Death, International Day of Peace, International Day of Older Persons, International day for Eradication of Poverty, Girl’s International Day, 16 Days of Activism Against Gender Based Violence, International Day for Tolerance, World Children’s Day,  International Migrants Day, Global Handwashing Day and International Day of Democracy.

In the reporting period, partner NGOs conducted 129 seminars and trainings on civic education topics for 977 students. This figure contains duplicates. Of the training participants, 608 are girls and 369 are boys (4th quarter numbers are: 37 seminars for 303 beneficiaries). Seminars covered the themes of active citizenship, advocacy for community benefit, effective presentation, problem identification, children’s rights, bullying prevention, media literacy, career planning, effective communication, use of MT toolboxes, SWOT Analyzes, online trainings on discrimination, waste management, the use of modern platforms for effective online presentations, cyberbullying prevention, human rights protection, conflict management, time management, distant learning challenges, healthy nutrition, leadership, social entrepreneurship, election and social responsibility, volunteering, conflict management and debates.

Due to COVID-19 restrictions announced by Georgian government, MT’s partner NGOs  were able to arrange only 18 group visits with the participation of 49 students. Participants of these visits included 30 girls and 19 boys (4th quarter numbers are: 4 group visits for 18 beneficiaries). Students visited the educational resource center in Kareli Municipality, Gori Municipality Office, Public Defender’s branch office, City Gori Occupation Museum and local election committee office in Shida-Kartli region, Batumi State University and Black Sea Colleague in Adjara region and local ambulance in village Ikalto, Kakheti region.

In addition to the group visits, NGO partners facilitated 135 meetings with expert guests with participation of 495 students. This number includes 318 girls and 177 boys (4th quarter numbers are: 43 meetings for 325 beneficiaries). Student online meetings were held with human rights specialists, civic activists, lawyers, Georgian Public Defender’s Office representatives in different regions, journalists, representatives of Media Development Foundation, representatives of local election committees, sports people, writers, representatives of NATO and EU Information Center, local government representatives, psychologists, doctors, representatives of local and international healthcare organizations, cyberbullying specialists, representatives of National Food Agency. Students also met with successful alumni of the civic education program.

MT students identified problems in their local communities. With support of MT’s NGO partners they addressed local governments and other agencies with their requests and became involved in activities to solve identified problems. Such activities were carried out by students in school-based civics clubs and/or through civics classroom projects. Involvement in civics activities helped students to apply into practice the knowledge gained at civics lessons and engage in activities for community benefit. Specific examples of student activities from different locations include:

Guria region

In October 2020, students from Guria region promoted healthy nutrition and increased public awareness about food safety among community members. At the initial stage, students participated in an online meeting with  representatives of the Georgian National Food Agency and received detailed information about food safety issues in Georgia. Based on the received information students developed posters including details on food safety standards, regulations, terminology and recommendations. Students’ posters also included contact information and hotline numbers of organizations working on food safety issues. Students shared their work via social media.

In December 2020, civics students from the village of Kviriketi implemented a civics project on gender-based violence. To determine whether gender-based violence has increased in their own community during the COVID-19 pandemic, school-based civics club members from Kviriketi prepared an online survey and interviewed their family members, parents and peers. The majority of respondents stated that the number of domestic violence cases has significantly increased over the past year during the COVID-19 pandemic. Based on the survey results, students prepared presentations, organized an online discussion with the help of their civics teacher and talked about the possible causes of increased gender-based violence during the pandemic. Students also prepared essays and posters portraying their attitude against gender-based violence and disseminated these via social media.

Tbilisi

In November 2020, 10th-grade students from Tbilisi Public School # 118 worked to raise an awareness of the local community on women’s rights and gender equality. At the initial stage, students surveyed attitudes of community members towards gender-based violence and women’s rights. The majority of respondents named economic conditions and lack of education being the main factors for women’s rights abuse. Based on survey results, students prepared presentations, photos, drawings and videos to demonstrate gender-related stereotypes and gender-based discrimination. They also prepared posters to portray the different examples of violence and explained how to prevent acts of violence or how to respond to them. Students also gathered information about well-known women who made an impact and changed public attitude towards women’s rights. Through their work, students emphasized the role of women in the social and political life of Georgia and made efforts to promote gender equality. The best works of students were shared via social media.

In December 2020, civics club members from Tbilisi #213 public school implemented a civics project on media literacy. In an online discussion, students spoke about identification, causes and covered how to stop the spread of fake news. Students also discussed the role of media in the modern world and covered the activities of the Georgian Charter of Journalistic Ethics. Based on received knowledge students prepared online posters titled ‘’Do not become a troll’, ‘’ Do not trust blindly’’, ‘’Do not mislead others’’, ‘’Check before you share’’ and shared these in social media.

Imereti region

In September 2020, civics students of the village of  Kveda Sazano public school #1 organized an open-air meeting to inform students from elementary school about the necessary measures for COVID-19 prevention. Students explained why it is important to wear masks, keep distance and follow the rules of hygiene. Prior to this meeting, students met with a local doctor and received information about the hygienic norms for both COVID-19 and seasonal virus prevention.

In November 2020, MT students from the village of Koreti took efforts to help economically disadvantaged families. Students found out that these families were in need of facemasks to protect themselves against COVID – 19. Students organized a meeting with the representatives of the local government and discussed with them the needs of economically disadvantaged families. The local government agreed to provide a certain number of facemasks for distribution to families in need of them. Students delivered 250 facemasks to 12 economically disadvantaged families to prevent the spread of COVID- 19 in their village.

Shida Kartli region

In November 2020, MT Students from the village of Sasireti public school in Shida Kartli region arranged a square at the school territory. Students received 20 seedlings of flowering and evergreen trees from the local government and with the support of community members organized cleaning and greening actions at their school. Students also participated in a training on how to make flowerpots from used items and decorated the school square with flowerpots handmade from plastic bottles and wheels.

In October 2020, MT Students from the village of Kekhijvari public school organized mock elections. The students’ initiative aimed to raise peers’ knowledge on the importance of elections and help to introduce a culture of voting. During the mock election students were divided into groups, selected one candidate from each group and prepared their election programs. Each candidate presented their individual election program to the class, students made a ballot box and voted. They also prepared a wall newspaper about COVID-19 prevention measures during the voting process and posted it in the school.

Kvemo Kartli region

In November 2020, students from the village of Sameba public school marked a 16 day campaign against gender-based violence. Students collected information on gender-based violence in Georgia, learned about the organizations working on gender issues and organized online discussion with their peers. Students covered the different forms of gender-based violence, discussed how culture influences gender-based violence as well as. They also spoke about an early and forced marriage (these are common in Azeri ethnic minority communities in Kvemo Kartli) and its prevention. At the end of the discussion students introduced an online platform SAFE YOU, which is created to protect women from violence. Students called on their peers to use this platform in case  they become aware of violence committed against someone  or of themselves.. In the frame of the campaign students also created thematic online posters and videos and shared them via social media.

In October 2020, MT students from different municipalities in Kvemo Kartli region participated in a campaign “Elections and Citizen”. During the campaign, students participated in different activities at their schools to promote voters’ participation in upcoming elections. Through meetings with the representatives of local election committees students received detailed information about the election procedures and the voting system. In civics classes they learned why voting is fundamental for democratic society, who is eligible to vote and what the new regulations are for prevention of COVID-19 during voting. In the frame of the campaign students also organized an essay contest “Voting, Right or Duty?”.The best works were shared via social media.

Kakheti region

In December 2020, civics students from the village of Akhasheni public school successfully finished a civics project for replacing potable water pipes  at school. The poor quality of potable water and the area leading to the water tap was a critical issue for the Akhalsheni school community. Civics students decided to request that the local government repair the potable water pipes and renovate the road leading to the water tap at the school territory. The local government positively responded to the students’ request. As a result of this student initiative, potable water pipes were replaced at school.

In December 2020, civics students from the village of Arashenda public school in Kakheti region, together with local administration and community members, organized cleaning and greening actions for the improvement of their schoolyard. Gurjaani Forestry Agency provided tree seedlings for the greening action.

Adjara region

In October 2020, 10th grade students from the village of Atchkvistavi public school took part in a civics class project to promote a healthy lifestyle among peers. Students started with an online survey and learned what their peers think about unhealthy habits and drugs. Survey results showed that a majority of respondents did not have a clear understanding of how unhealthy habits impact human health. Students also organized an online meeting with representatives of the Drug Prevention Center. At this meeting students learned how unhealthy habits affect human health, what the triggers are of these habits and which diseases these can cause. Based on what they learned students prepared online posters and shared them in social media.

In October 2020, 9th grade students from Batumi #29 public school surveyed the local community to learn about their attitudes towards early marriage. Students learned that a majority of respondents did not know about the negative consequences of early marriage. Students organized an online meeting with a psychologist and lawyer to talk about early marriage and its impact on an individual. Based on what they learned, students prepared an animation featuring the negative consequences of early marriage and  shared it in social media.

Samegrelo region

In December 2020, students from the village of Menji public school implemented a civics online project aimed at the prevention of gambling. First, to identify their peers’ attitude towards gambling/online games, students decided to conduct an online survey. Survey results showed that gambling is quite popular among youth with many teenagers involved in different types of gambling without acknowledging the risks. Students collected information on problems caused by gambling in adolescents, on gambling addiction and on the effective ways to stop it. Students also organized an online meeting with a psychologist and discussed gambling addiction. Based on  what they learned, students prepared an online presentation, posters and shared them with their peers in social media.

In November 2020, 9th grade students from Daba Mestia #2 public school took efforts to promote local tourism through their civics class project. Thinking about how to attract local tourists, students decided to promote local cuisine and to recover the recipes of homemade old Svanetian traditional dishes which are rarely cooked locally. Students interviewed local community members and collected 33 recipes of old dishes. The recipes will be published as a brochure and will be disseminated by students in the local cafes and restaurants.

In November 2020, MT students from village Chkaduashi successfully implemented a civics project on road safety. The school is located next to the central highway with no pedestrian crosswalk. Students studied the opinion of school community members and parents, and used the results of the survey in a letter to local government, requesting an arrangement of a crosswalk. The local government made a positive decision and a crosswalk was painted.

### 6.2. Equipment Contest for Schools and Civics Teachers

This task is in progress and will continue over the upcoming quarter.

In January 2020, MT team and its partner NGOs started to review equipment contest applications from schools and from teachers. Applications from schools provided information about the accomplishments of each school in civic education as reflected in students’ actions and initiatives, which brought positive results to the school and community. Applications included data illustrating involvement of students in different civics projects, their participation in trainings and in volunteer opportunities.

Teachers’ applications provided information about teachers’ involvement in professional development activities, trainings and conferences, as well as information about the process and results of student civics projects, which were facilitated by the teachers.

Applications were first screened by MT’s partner NGOs in the regions. Partner NGO representatives recommended the best schools and teachers for awards. They have provided arguments and facts about the work carried out by the recommended schools and teachers.

On January 16-17, 2020, MT organized a two-day meeting with regional partner NGOs in Batumi, Adjara. During the meeting, MT staff together with regional partner NGO representatives examined and assessed shortlisted applications. The final candidates for awards were confirmed. A total of 45 schools and 30 teachers were selected for equipment awards from among the 112 applications that were received (63 applications from schools and 49 from civics teachers).

Each winner school received a laptop and signed a handover letter stating that the awarded equipment will be solely used for civic education and civics activities of students, and the school is responsible for proper maintenance of the equipment, as well as for its safety. In case any of these rules are violated, the program reserves the right to request the school to return the awarded equipment. Each teacher received a tablet as their personal property, though they were asked (in handover letters) to use it for professional development, to enhance civic education instruction and/or activities.

In November 2020, MT announced the last equipment contest for program’s partner schools and civics teachers. The equipment contest was announced through MT’s social networks and webpage - www.civics.ge. PH’s NGO partners also informed the schools and provided them with application forms. Due date for applications is February 25, 2021.

Applications will be first assessed by MT’s regional partner organization representatives, who will review and recommend the best schools and teachers for awards. Along with recommendations, NGO partners will briefly describe activities implemented by these schools and teachers for improved civic education at school. Later, applications will be examined and assessed by the MT selection committee together with partner NGOs. The final candidates will be confirmed and awarded in May 2021.

## 7. Mini-Grants for Students Activities

### 7.1. Education of students, teachers, and communities on mini-grants program

This task was finished in the previous year.

The calls for mini-grants took place in 2019, and students and teachers carried out activities of those mini-grant projects in 2020 (in the reporting period). Forty-six mini-grant projects in total were carried out in the reporting period.

Regional partner NGOs provided all interested and eligible groups with consultations in the process of project implementation and helped in fundraising or/and in obtaining the matching resources. Mini-grants implementers received consultations on how to develop a project report in PH Data Base/ Virtual Office and received assistance in this process as needed.

### 7.2. Functioning and management of mini-grant program to students and/or

### student-teacher groups

This task is in progress and will continue over the upcoming quarter.

Mini-grants serve as a means to stimulate applied learning in civics by students. Through the mini-grants program, students, teachers, and school administrators are able to open the channels of communication with local government officials and facilitate decision-making processes regarding their communities from the grassroots level. Professional motivation is also created for civics teachers as they are able to get involved in small projects with their students and deliver results that bring benefits to their schools and communities. There are also local resources mobilized for the mini-grant component.

Applicants of mini-grants are students, teachers, school administration officials, or combination of the above individuals.

Forty-six mini-grants projects, ongoing in the reporting period, could not be finalized on time due to the COVID-19 pandemic and due restrictions. The MT Mini-grants coordinator helped project implementers to adjust their activities to an online format. Students announced different contents, met with expert guests and local authorities online, created videos, flyers and posters on civic education topics and shared them in social media. Online presentations of project results were held in each region.  38 mini-grant projects were completed in the reporting period. The remaining 8 projects will be completed in spring, 2021.

Information about some of the mini-grant projects is provided below:

Adjara

Grant receiver: Begleti Village Public school

Project Title: Students for steady development

Project Description:  Village Begleti school students in the mountainous Adjara region decided to take care of the environment and prevent landslides and avalanches in their village. Students discussed their goal with local government and Agro Service Center representatives in Khulo Municipality. They jointly identified what steps could be undertaken to make the local environment safer. Local government helped students to get young trees for the greening action. In November 2020, students mobilized community members and planted the trees in the landslide risk area in the village.

To raise community awareness about the importance of environmental protection, students developed a flyer and a poster describing landslides and avalanches, as well as preventive measures, organized an online meeting with the biology teacher and with a representative of Agro Service Center. Through flyers, students highlighted the importance of keeping the environment clean and reminded locals about the negative impact of scattered trash. Through online training, students learned about rubbish management and the processing of recyclables. Informational materials created in the frame of the project were shared via social media.

Grant receiver: Achkva Village Public school

Project Title: Together for a change

Project Description:  To promote active citizenship among youth, students of Achkva village public school in Adjara region decided to implement a mini-grant project. Students collected information about the importance of civic engagement and called on youth and community members to be involved in community problem-solving processes.

To inform community members about the state programs from which the locals could benefit, students met with city hall representatives and learned more about governmental programs and about the new opportunities for the local residents, especially those for youth.

Students also educated their peers about the importance of volunteering. They prepared a short video and organized online training for MT students in the Adjara region. This training helped youth to learn more about different types of volunteering, why volunteering is important, what volunteers have done in the past and how their volunteering impacted the community.

Guria

Grant receiver: Askana Village Public school

Project Title: Teenagers – Future of the country

Project Description: MT Students from village Askana public school implemented the mini-grants project related to labor rights. Students surveyed the knowledge of their peers about labor rights. The survey results showed that a majority of students did not know what the basic rights of employees are, what should be the standard working conditions and safety rules. Based on the survey results, students prepared  an informational diagram and shared it in social media. Students also collected information about the labor code, organized an online meeting with a lawyer to discuss child labor and visited a professional Union at Ozurgeti municipality. To determine whether employees’ rights are protected, students also visited a local business and interviewed company employees and employers.

Students also organized an online informational campaign to inform their peers about labor rights, introduced the rules of labor safety to the young people who wanted to be employed. They prepared a flyer, posters and presentation on labor law including the hotline numbers of organizations working on labor rights and shared them through social media.

After the completion of the project, students conducted research, which showed an increase in community knowledge regarding the labor rights.

Grant receiver: Tskhemliskhidi Village Public school

Project Title: You are protected by the law

Project Description: Tskhemliskhidi school students decided to promote women’s rights in the community. They started with a survey, aiming to assess the knowledge of the community about women’s rights. Results showed that a majority of community members did not have a clear understanding of what is considered violence towards women. In many cases, community members did not understand that verbal insult is a type of violence. They also did not know to whom to apply in case women’s rights are violated.

The students gathered information about organizations working in the field of women's rights. This information and the results of the survey were shared through social media.

Based on the survey results students also prepared posters, a flyer and a presentation, with the description of different forms of violence towards women. Informational materials also included the hotline numbers and contact info of NGOs working on women’s rights protection.

Imereti

Grant receiver: Sairkhe Village Public school

Project Title: Let’s study democracy

Project Description: Students of the village Sairkhe public school decided to increase awareness of their peers about democracy. Students attended a training, took part in the discussion on the main principles of democracy and announced an essay contest “Why Democracy”. The winner of the contest was awarded by certificate and the best essay was posted on Facebook.

To inform their peers about the main principles of democracy, students prepared a video “Democracy and Me” and a flyer, conducted peer education training for the students from other schools. They explained to their peers what a democratic state is, and the role that youth plays in the development of a democratic country.

The video with all informational materials was shared via social media.

Grant receiver: Rokhi Village Public school

Project Title: Say no to violence – safe school

Project Description: Students of Rokhi village public school consider that violence against women is a critical problem in their community. To inform their peers about women’s rights, students staged a forum theatre and prepared a video about women’s rights.

At an early stage of the project students received a training about the different forms of violence. Later students organized an online meeting and a conference aiming at increasing students’ and community members’ awareness about the prevention of violence against women. They invited Baia Pataraia, the Lawyer and the Head of the “Sapari Union” to speak about women's rights, anti-discrimination law and international human rights mechanisms. Students learned about the measures our government undertakes for the prevention of violence against women.

Based on the information received through the project, students prepared information materials, distributed them in the school community, posted on Facebook and conducted informational meetings for students from the other two schools.

Kvemo Kartli

Grant receiver: Tamarisi Village Public school # 1

Project Title: For us and for our school

Project Description: Students of Tamarisi village public school #1 decided to raise public awareness about the importance of environmental protection and to improve school infrastructure. A survey helped to identify the four main problems, which included need to arrange a school cafeteria, the need for a better sports equipment, the need to renovate school infrastructure and the need of internet access at school. Together with their civics teacher, students worked with school administration to resolve one of these problems.

Students organized cleaning and greening actions in the schoolyard, made a plan for the arrangement of the recreation area, and identified how other students and parents could help with resources. Students mobilized these resources and arranged a recreational area in the schoolyard.

Students also prepared a video about the negative consequences of air pollution. To better protect the environment they shot a video on how to save natural resources by giving second life to already used materials and shared it via internet.

Grant receiver: Sameba Village Public school

Project Title: Promotion of a healthy lifestyle

Project Description: To promote a healthy lifestyle in the community, students from Sameba village implemented a civics class project.

First students conducted a survey. The survey results showed that only 25% of youth followed healthy lifestyle because of the lack of sports infrastructure in the village. To encourage youth, students met with a successful sportsman, prepared a video about the importance of healthy nutrition, developed posters and a flyer and shared them through the social network.

Later, the students mobilized community members and started to rehabilitate the stadium. Students cleaned the territory and renewed the fence. Once the stadium became more organized, students arranged sports competitions with participation of their peers from other schools. These competitions contributed to the promotion of a healthy lifestyle among youth.

In the frame of the project students cooperated with representatives of Tsalka City Hall. A representative of the city hall promised to install outdoor lightening at the stadium.

Samegrelo-Zemo Svaneti

Grant receiver: Obuji Village Public school

Project Title: Take care of nature and nature will take care of you

Project Description: Students of Obuji village public school decided to raise public awareness about the importance of environmental protection. They created drawings, met with expert guests and announced an essay contest "A Massage to Earth". The best essays were posted on the school’s Facebook page.

In addition, students decided to create a recreational area in the village. Their initiative was supported by the local government through the allocation of necessary equipment and human resources. In spring of 2021, students plan to organize a greening action to make the area more attractive.

Grant Receiver: Orulu Village Public School

Project Title: Healthy future generation

Project Description: To promote healthy lifestyle among peers, students of Orulu village public school in Samegrelo region prepared posters on healthy nutrition, active lifestyle and provided  tips for stress management. Promotion of healthy lifestyle became especially important in times of COVID-19 pandemic.

To increase awareness of their peers about the negative consequences of unhealthy habits, students organized online meetings with a doctor, a sportsman and a biology teacher. They prepared posters and a flyer. These informational materials were posted on the school's Facebook page.

Shida Kartli

Grant receiver: Tezeri Village Public school

Project Title: Let’s remind our parents of their childhood

Project Description: Students of Tezeri public school decided to engage their parents in school life. They organized joint activities - arranged a recreational area and painted the wall in the schoolyard. The topics of the paintings were tolerance and equality. Students and their parents participated in these activities together.

In addition, students organized a civics quiz for middle school and high school students. Quiz questions were taken from MT civics supplemental textbooks and covered the topics of democracy, human rights, active citizenship and volunteering. Selection committee announced three winners, who were awarded with certificates.

Students also got involved in fun activities with their parents. They competed each other in cooking, created crafts and arranged an exhibition.

The project was covered by TV Formula.

Tbilisi

Grant Receiver: Tbilisi Public School # 9

Project Title: Healthy life

Project Description: 9th grade students of Tbilisi public school #9 implemented a mini-grant project “Healthy Life". To learn more about a healthy nutrition, students arranged a meeting with a doctor. Participants of the meeting received information/recommendations about organic food and the usefulness of fruits and vegetables.

Students prepared videos and posters emphasizing the benefits of healthy lifestyle and good nutrition. They uploaded these materials on a Facebook page, also organized live discussions with expert guests and received the needed information.

By the end of the project, students created comics, which consisted of recommendations for healthy nutrition, included information about the usefulness of fruits, vegetables and healthy nutrition. The comics were shared via social media.

To summarize, 802 students in total were involved in  implementation of 38 mini-grant projects during the reporting period.  Of these, 486 girls and 316 boys, 70 ethnic minority students and 17 IDP students. A total of 12,818 people benefited from these projects.

### 7.3. Monitoring and evaluation of mini-grant component

This task is in progress and will continue over the upcoming quarter.

During the reporting period, mini-grant allocations were monitored by the MT staff. NGO partners have the responsibility of supervising the grant allocation and implementation process in the field.  Monitoring involved visits of the MT staff as well as written reports from NGO partners, which include project reports and success stories from grant recipients. MT’s Mini-Grants Coordinator maintained regular contact with NGO partners, participated in events and activities carried out by grant recipients, and provided feedback in case the need for change occurred throughout the grant implementation. MT worked with its NGO partners to ensure support from schools for projects from outside sources, such as local governments, businesses, media, etc.

### 7.4. Funding of the mini-grant proposals from sources outside MT program

This task is in progress and will continue over the upcoming quarter.

Fundraising efforts for projects to be supported by non-MT sources were continued in the reporting period. The development of teacher/student-led initiatives was supported by local NGOs to ensure due quality of budget planning, program design, and implementation. This is especially important when schools have to work with new donors and supporters.

The fundraising process of the third year coincided with the COVID pandemic, which made it extremely hard to raise funds for projects. Even though students with the help of the civics teachers and regional partner NGOs still implemented six projects without director support from MT, among these were four projects funded by MAC Georgia. All six projects were reported in the quarterly reports.

A total of 200 students were involved in the planning and implementation of such projects. This number includes 122 girls and 78 boys. These projects benefited 1,117 individuals.

Projects funded by MAC Georgia

In October 2019, MAC Georgia (former McLain Association for Children) selected the following five schools for funding: Katskhi, Merjevi and Salominao public schools in the Imereti region, Benara public school in the Samtskhe-Javakheti region and Kekhijvari public school in the Shida Kartli region. The projects were implemented from October 2019 through June 2020, and supported local, community-led initiatives that contribute to building of inclusive environments. Benara  public school project was finalized during the previous year and the other 4 projects were successfully completed in the reporting period.

## 8. Interactive Website and Social Networking

### 8.1 Program websites and social networks

This task is in progress and will continue over the upcoming quarter.

To support teachers, students, and parents with professional resources and materials, MT’s website www.civics.ge was updated regularly during the reporting period. The website included media coverage of many different civics events and activities, and featured TV and radio programs with the participation of MT beneficiaries and stakeholders. Videos were featured on MT’s civic initiatives Facebook page (www.facebook.com.civicinitiatives), as well as on the civics.ge video gallery. It should be noted that video coverage materials were mostly viewed from Facebook page. Photo and video galleries of the program web portals were regularly updated to reflect the news and recent developments. In addition to www.civics.ge and MT’s Facebook page, the news and stories of the MT program were sometimes also published on www.ph-int.org and the USAID Facebook.

MT’s social network, http://www.facebook.com/civicinitiatives, had 17,627 likes (2,416 new likes in the reporting period).

In the reporting period there were 2,004 users on the civics.ge site and 3,827 page views in total.

### 8.2. Online conference

Due to circumstances caused by COVID-19, online conferences have become increasingly important in MT and a good alternative of former offline meetings of MT students with expert guests. Online conferences provide an excellent opportunity for students to meet with expert guests regardless of their geographic location. With the use of internet technologies, students can openly communicate their questions and ideas to invited guests.

In the reporting period MT organized 10 online conferences through MT's civic initiatives Facebook page https://www.facebook.com/civicinitiatives. Students, parents and teachers took part in MT online conferences and asked their questions to the speakers.

Online conference with a doctor Tea Danelia was held on March 20, 2020, and addressed precautionary measures to prevent the spread of COVID-19 and the importance of a healthy lifestyle. Viewers – students, teachers and community members - were actively engaged. Up to 650 questions/remarks were made by the viewers during the online conference. A total of 2,100 viewers were reached by the time the online conference ended, and the number of viewers increased even more in the following days as the recorded live conference was posted on MT’s civics initiatives Facebook page.

Basic tools of stress management during COVID-19 pandemic were discussed during the online conference held on March 27, 2020, with participation of a phycologist, Maia Tsiramua. Up to 210 questions were asked by the viewers (mostly students, civics teachers, parents) and around 2,400 online viewers were reached by the time the online conference ended. The number of viewers increased significantly in the following days as the recorded live conference was posted on MT’s civic initiatives Facebook page.

A live event with Judge Tamar Chikhladze was held on April 7, 2020, and addressed the work of the judge and court system, civics responsibilities during the challenging times of pandemic, protection of human rights, issues of gender equality and domestic violence. About 280 questions were asked by participants during the online conference and 2,500 online viewers were reached by the time it ended. This live event was organized in collaboration with USAID PROLOG Program.

A live event with basketball player Anatoli Boisa took place on April 24, 2020. It covered the importance of sports and healthy lifestyle among youth. Anatoli spoke about the need of physical activity and healthy nutrition in youth, especially during the times of stay-at home order. He also covered his career as a professional basketball player and a coach. The number of online viewers  reached 2,700 with a total of 262 questions asked by students, teachers and parents.

A live event with TV host Naniko Khazaradze was held on May 13, 2020. The TV host spoke about the role of media during the times of pandemic and other emergency situations. She also shared her own experience of working as a host of various TV programs, spoke about professional motivation and hard work. The number of online viewers reached 3,800 a total of 218 questions asked.

A live meeting of students and teachers with Adam Schmidt, Director of USAID Georgia’s Democracy, Governance and Social Development Office, was held on May 22, 2020. During one hour of the live session, the speaker talked about the life of the American family in Georgia during COVID-19 pandemic and also covered civic activism and volunteering in the US. Adam’s son, Phin, also joined the session and answered many questions of Georgian students related to his experience as a student in the US in times of distant learning. Marina Ushveridze, MT Chief of Party, facilitated the session. It reached 3,100 viewers with a total of 278 questions asked.

The live session with Eka Gigauri, Executive Director of Transparency International Georgia, was held on May 29, 2020. During the live event, the guest spoke about the role of citizens in combatting corruption and nepotism, and shared examples from everyday life. The live event reached 2,300 viewers with 311 comments and questions asked by students, teachers and parents.

A live session with entrepreneur, DIO LTD’s CEO and partner, Tamaz Daushvili, was held on June 5, 2020. The session highlighted corporate social responsibility, why it is important for the company and for the community. The speaker also shared with students tips for starting a new business, spoke about the role of teamwork and leadership in business and answered the questions of students about entrepreneurship and corporate social responsibility. The live session reached 3,000 viewers with 148 comments and questions.

The live session with journalist Zviad Koridze was held on June 23, 2020. During an hour long session, the speaker talked about disinformation, fake news and the role of media and citizens in confronting disinformation. This live session had 1,900 viewers with 82 comments and questions from students, teachers and parents.

A live session with UN Secretary General's Healthcare Adviser, Dr. Giorgi Pkhakadze with Georgian civics teachers was held on December 19, 2020. Dr. Pkhakadze answered the questions of teachers about COVID-19, covered the necessary measures for its prevention and spoke about vaccination. The meeting was livestreamed via Facebook, where many questions were asked by teachers from all regions of Georgia. The event reached 33,000 viewers. MT Chief of Party, Marina Ushveridze facilitated the session.

## 9. Etaloni Competition

This task is in progress and will continue over the upcoming quarter.

“Etaloni” national intellectual competition for students aims to increase students’ interest towards education and their motivation to learn more. It is a highly popular intellectual competition among students in schools of Georgia and is held regularly with participation of middle school and high school students from all municipalities of Georgia. MT agreed with organizers of “Etaloni” to include civic education questions in the competition. Questions were prepared by civics teachers and shared with Etaloni. These questions were asked during one of the stages of the competition in the reporting period. The next stage of the competition took place only in some municipalities and was temporarily suspended due to the COVID-19 related restrictions. MT will donate equipment prizes for the winner students when the competition is over.

## 10. General/Administrative

### 10.1. Cooperation with Media

This task will be in progress in the next reporting period.

MT made plans for media seminar to be held in 2020, which was postponed due to the restrictions associated with COVID-19 pandemic. The event will take place in 2021 if the epidemiological situation allows.

In the reporting period, news on the MT program activities were covered by TV and radio companies, print media, and online resources all across Georgia.  In the reporting period, TV companies covered information about MT activities 17 times, 19 radio broadcasts were held, 22 instances of online coverage also took place and 1 article was published in the newspaper.

In their daily and morning programs, central TV companies promoted the importance of civic education. They invited MT students and teachers, school principals and the MT program and NGO partner representatives to take part in their programs.

The media coverage listed below took place during the 4th quarter of the MT extension year 3. Information about the media coverage of previous quarters is given in the respective quarterly reports.

TV Coverage

On October 21, 2020 TV company “Formula” in its morning program covered information about the civics students’ initiative to improve environment and arrange square in Tezeri village public schoolyard. The initiative was supported by USAID mini-grant project.

https://www.facebook.com/civicinitiatives/posts/3418099411579361

On October 29, 2020 TV company “DIA” covered information about active citizens,  civics students from Sasireti village public school, their civics initiatives implemented for the benefit of school and community (Shida Kartli region).

https://bit.ly/3qJTNJt

Radio

On November 6, 2020, Radio “Adjara” in its program “Gia Eteri” hosted Maia Katamadze, a Head of Batumi Education Development and Employment Center to talk about results of civics projects implemented in the framework of “Momavlis Taoba” program (Adjara region).

https://bit.ly/391z7GO

On November 9, 2020, Radio “Atinati” broadcasted information about contest of drawings announced in the framework of  “Momavlis Taoba” program (Samegrelo-Zemo Svaneti region).

https://bit.ly/3izgjSh

On December 1, 2020, Radio “Atinati” hosted Salome Gardava, program coordinator in Samegrelo region, Marina Paliani, civics teacher and Salome Paliani a student of Mestia public school #2 to talk about students’ initiative to promote cultural heritage in the frame of the “Momavlis Taoba” program (Samegrelo-Zemo Svaneti region).

https://bit.ly/39RvhiD

Online Media

On October 13, 2020, web page www.etaloni.ge published information about mini-grant project implemented by students of Tamarisi village public school #1, which aimed to arrange a square in the schoolyard (Kvemo Kartli region).

https://www.etaloni.ge/geo/main/index/43975

On November 4, 2020,  web page www.etaloni.ge published information about students of Tsereteli village school, who initiated to inform peers about conflict in Abkhazia and its results (Kvemo Kartli region).

https://www.etaloni.ge/geo/main/index/44776

On November 10, 2020,  students of Sadakhlo village public school #1 posted on school Facebook information about results of civics projects: No to Violence against Women, Gender Equality, No to Bullying, Prevention of COVID-19 (Kvemo Kartli region).

https://fb.watch/2dENweIcPC/

https://fb.watch/2dF54WbCLd/

https://fb.watch/2dFfTp2RBl/

https://www.facebook.com/Sadaxli1/posts/687279095557238

On October 30, 2020 Education recourse center of Kaspi posted on its Facebook information about Sasireti village public school covered by TV company “DIA” (Shida Kartli region).

https://www.facebook.com/104662001007676/videos/1383135328703152-

On November 17, 2020 Education recourse center of Khashuri posted on its Facebook information about civics projects implemented by students of Plevi village public school (Shida Kartli region).

https://www.facebook.com/civicinitiatives/photos/pcb.3491673164221985/3491671120888856/-

On October 21, 2020 Education recourse center of Khashuri posted on its Facebook information about mini-grant project implemented by students of Tezeri village public school covered by TV company “Formula” (Shida Kartli region).

https://www.facebook.com/civicinitiatives/photos/pcb.3491673164221985/3491671494222152/

### Attachment:

DVD with photos and media coverage materials of MT events.