## HIDE (hidden)
For Official Use Only (FOUO)
Official Government Estimate
PWS Title: Conservation/Recreation Interns to Perform Recreational Road Inventories
Contract Number TBD
| Tasks | 1 | 2a | 2b | 2c | 2d | 2e | 2f | 2g | 2h |  |  |  | Total
|  | Ops-Log Planning | NWK | MVS | LRL | LRH | NWO | LRP | MVR | MVP | SAS
| est weeks | 6 | 23 | 17 | 16 | 25 | 20 | 15 | 15 | 16 | 12
Labor Categories |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hrs | Rate | Cost
Sr Program Manager |  | 48 | 92 | 68 | 64 | 100 | 80 | 60 | 60 | 64 | 48 | 684 | 125 | 85500
Program Manager |  | 240 | 690 | 510 | 480 | 750 | 600 | 450 | 450 | 480 | 360 | 5010 | 95 | 475950
Team Leader |  | 240 | 920 | 680 | 640 | 1000 | 800 | 600 | 600 | 640 | 480 | 6600 | 70 | 462000
Budget Analyst |  | 24 | 92 | 68 | 64 | 100 | 80 | 60 | 60 | 64 | 48 | 660 | 45 | 29700
Admin Assistant |  | 12 | 46 | 34 | 32 | 50 | 40 | 30 | 30 | 32 | 24 | 330 | 25 | 8250
Crew member/Intern |  | 0 | 883 | 666 | 938 | 1392 | 792 | 592 | 566 | 606 | 463 | 6898 | 30 | 206940
Hours by Task |  | 564 | 2723 | 2026 | 2218 | 3392 | 2392 | 1792 | 1766 | 1886 | 1423 | 20182 |  | 1268340
Materials |  | 40000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 |  |  | 175000
Travel |  | 2500 | 22900 | 16800 | 22600 | 34500 | 19800 | 14800 | 13300 | 14400 | 10000 |  |  | 171600
Cost by Task |  | 42500 | 37900 | 31800 | 37600 | 49500 | 34800 | 29800 | 28300 | 29400 | 25000 |  |  | 1614940 | TOTAL:
Prepared by: | ____________________________________
Approved by: | ____________________________________
Grant Manager: | ____________________________________
Note on B9: Noordhoff, Zachary N CIV USARMY CENAB (US): Receive from Travel Est. Tab.
Note on C12: USACE: est 8 hours per week
Note on C13: USACE: est 40 hours per week
Note on C14: USACE: est 2 weeks @ 40 hours per week
Note on C15: USACE: est 4 hours per week
Note on C16: USACE: est 2 hours per week
Note on A23: USACE: includes equipment and support items: -field tools (mobile phones, computers, etc.) -meals. -service clothing. -PPE.

## Gov Est-Working Copy
For Official Use Only (FOUO)
Official Government Estimate
PWS Title: Conservation/Recreation Interns to Perform Recreational and Road Inventories | [9 empty] | FY22 cost | using costs through FY23
Contract Number TBD | [9 empty] | Period of Performance to include the rest of districts
Trans Lim REC | Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  |  |  | Total
|  | Ops-Log Planning | NWO | NWS | NWW | SPL | SPA | SPN | SWG | MVN | NWK | SAS | SAJ | NAE | LRH | LRP | NAP | LRC | MVP | MVR
| est weeks | 10 | 5.6692 | 1.7553 | 3.6814 | 1.7928 | 1.94 | 1.7348 | 1.6059 | 2.1606 | 7.7996 | 5.9973 | 1.2235 | 5.2728 | 7.9767 | 4.9979 | 1.5742 | 1.8618 | 2.7323 | 4.2367 | 74.013
Labor Categories |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hrs | Rate | # Employee | Cost
Sr Program Manager |  | 80 | 22.6768 | 7.0214 | 14.7256 | 7.171 | 7.7602 | 6.939 | 6.4236 | 8.6424 | 31.1986 | 23.9894 | 4.894 | 21.0912 | 31.907 | 19.9916 | 6.297 | 7.4472 | 10.929 | 16.947 | 336.052 | 125 | 1 | 42006.5
Program Manager |  | 400 | 170.076 | 52.6605 | 110.442 | 53.7825 | 58.2015 | 52.0425 | 48.177 | 64.818 | 233.9895 | 179.9205 | 36.705 | 158.184 | 239.3025 | 149.937 | 47.2275 | 55.854 | 81.9675 | 127.1025 | 2320.39 | 95 | 1 | 220437.05
Team Leader |  | 400 | 226.768 | 70.214 | 147.256 | 71.71 | 77.602 | 69.39 | 64.236 | 86.424 | 311.986 | 239.894 | 48.94 | 210.912 | 319.07 | 199.916 | 62.97 | 74.472 | 109.29 | 169.47 | 2960.52 | 70 | 1 | 207236.4
Budget Analyst |  | 40 | 22.6768 | 7.0214 | 14.7256 | 7.171 | 7.7602 | 6.939 | 6.4236 | 8.6424 | 31.1986 | 23.9894 | 4.894 | 21.0912 | 31.907 | 19.9916 | 6.297 | 7.4472 | 10.929 | 16.947 | 296.052 | 45 | 1 | 13322.34
Admin Assistant |  | 20 | 11.3384 | 3.5107 | 7.3628 | 3.5855 | 3.8801 | 3.4695 | 3.2118 | 4.3212 | 15.5993 | 11.9947 | 2.447 | 10.5456 | 15.9535 | 9.9958 | 3.1485 | 3.7236 | 5.4645 | 8.4735 | 148.026 | 25 | 1 | 3700.65
Crew member/Intern |  | 0 | 226.768 | 70.214 | 147.256 | 71.71 | 77.602 | 69.39 | 64.236 | 86.424 | 311.986 | 239.894 | 48.94 | 210.912 | 319.07 | 199.916 | 62.97 | 74.472 | 109.29 | 169.47 | 25605.2 | 30 | 10 | 768156
|  |  | 2267.68 | 702.14 | 1472.56 | 717.1 | 776.02 | 693.9 | 642.36 | 864.24 | 3119.86 | 2398.94 | 489.4 | 2109.12 | 3190.7 | 1999.16 | 629.7 | 744.72 | 1092.9 | 1694.7 | 31600
Hours by Task |  | 940 | 2947.984 | 912.782 | 1914.328 | 932.23 | 1008.826 | 902.07 | 835.068 | 1123.512 | 4055.818 | 3118.622 | 636.22 | 2741.856 | 4147.91 | 2598.908 | 818.61 | 968.136 | 1420.77 | 2203.11
Materials |  | 40000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 |  |  |  | 310000
Travel/Vehicles |  |  | 13100 | 6500 | 10800 | 6900 | 6300 | 6000 | 5600 | 5100 | 17300 | 13600 | 5000 | 20300 | 18700 | 13100 | 5600 | 6000 | 9000 | 14200 |  |  |  | 183100
Cost by Task |  | 118300 | 132299.896 | 53763.333 | 93464.132 | 54850.745 | 56958.119 | 52884.705 | 50116.442 | 59811.828 | 175657.567 | 138831.293 | 42487.93 | 132214.064 | 180312.665 | 119961.402 | 49534.715 | 55219.884 | 74218.755 | 107071.465 |  |  |  | 1747958.94
|  |  | Period of Performance to include the rest of districts 10 NWK: 848106.767 | [8 empty] | 899852.173
Trans/Lim REC
Estimated hours | 31600
Estimated weeks | 74.013
Estimated months | 18.5033
Estimated cost | 1747958.94
This estimate was generated using the estimated rates based on previous survey work. The estimates for the hours required for each task was developed based on information from government employees familiar with the level of effort as well as previously awarded contracts. This estimate was developed independently and prior to the receipt of any proposals.
Prepared by: | ____________________________________
Approved by: | ____________________________________
Grant Manager: | ____________________________________
Note on B8: Noordhoff, Zachary N CIV USARMY CENAB (US): Receive from Travel Est. Tab.
Note on W8: Andrew Huddleston: Total Weeks. Add 10 weeks for onboarding and training.
Note on C11: USACE: est 8 hours per week
Note on L11: USACE: during data collection est 4 hours per week
Note on C12: USACE: est 40 hours per week
Note on L12: USACE: during data collection est 30 hours per week
Note on C13: USACE: est 2 weeks @ 40 hours per week
Note on L13: USACE: est 40 hours per week
Note on C14: USACE: est 4 hours per week
Note on C15: USACE: est 2 hours per week
Note on L16: USACE: from time estimator
Note on A21: USACE: includes equipment and support items: -field tools (mobile phones, computers, etc.) -meals. -service clothing. -PPE.

## Road Mileage Discrepancy (hidden)
USACE FLTP Road Mileage Comparison
Original Road Mileage/Dist |  |  | SCA Road Mileage/Dist |  |  | NRMA Road Mileage/Dist
District: | Road Mileage | Parking Lots | Road Mileage | Parking Lots | Difference | Paved | Unpaved | Road Mileage | Parking Lots | Difference | SCA Actual Diff
Alaska (POA) | 13 | 0 |  |  | -13 | 6.5 | 6.5 | 13 | 0 | 0
Albuquerque (SPA) | 42.71 | 21 |  |  | -42.71 | 26.09 | 24.47 | 50.56 | 29 | 7.85
Baltimore (NAB) | 77.89 | 127 |  |  | -77.89 | 78.18 | 58.46 | 136.64 | 133 | 58.75
Buffalo (LRB) | 1.9 | 8 |  |  | -1.9 | 1.95 | 1.55 | 3.5 | 7 | 1.6
Chicago (LRC) | 53.82 | 84 |  |  | -53.82 | 39.97 | 13.85 | 53.82 | 84 | 0
Detroit (LRE) | 1 | 0 |  |  | -1 | 1 | 0 | 1 | 2 | 0
Fort Worth (SWF) | 540.93 | 1071 |  |  | -540.93 | 536.05 | 65.04 | 601.09 | 1763 | 60.16
Galveston (SWG) | 48.11 | 12 |  |  | -48.11 | 32.75 | 24.64 | 57.39 | 41 | 9.28
Honolulu (POH) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1015000
Huntington (LRH) | 312.96 | 391 |  |  | -312.96 | 192.3 | 278.04 | 470.34 | 564 | 157.38 |  | Roads budget
Jacksonville (SAJ) | 7.5 | 26 |  |  | -7.5 | 5.75 | 0.55 | 6.3 | 25 | -1.2
Kansas City (NWK) | 502.44 | 832 |  |  | -502.44 | 413.98 | 136.14 | 550.12 | 1021 | 47.68
Little Rock (SWL) | 395.72 | 852 |  |  | -395.72 | 379.35 | 35.65 | 415 | 1119 | 19.28 |  | 508000
Los Angeles (SPL) | 20 | 260 |  |  | -20 | 51.5 | 20.7 | 72.2 | 146 | 52.2 |  | spent on roads alone
Louisville (LRL) | 253.48 | 467 |  |  | -253.48 | 212.43 | 48.19 | 260.62 | 488 | 7.14
Mobile (SAM) | 465.59 | 823 | 617.55 |  | 151.96 | 455.62 | 97.35 | 552.97 | 1214 | 87.38 | -64.58
Nashville (LRN) | 260.98 | 541 | 259.32 |  | -1.66 | 242.95 | 29.08 | 272.03 | 663 | 11.05 | 12.71
New England (NAE) | 95.94 | 184 |  |  | -95.94 | 80.96 | 140.02 | 220.98 | 251 | 125.04
New Orleans (MVN) | 73 | 36 |  |  | -73 | 5.75 | 114.76 | 120.51 | 48 | 47.51 |  | 200.9144
Omaha (NWO) | 361.08 | 776 |  |  | -361.08 | 178.19 | 219.9 | 398.09 | 756 | 37.01
Philadelphia (NAP) | 9.49 | 10 |  |  | -9.49 | 5.11 | 1.82 | 6.93 | 33 | -2.56
Pittsburgh (LRP) | 121.78 | 196 |  |  | -121.78 | 120.57 | 176.14 | 296.71 | 310 | 174.93
Portland (NWP) | 72.41 | 103 | 77.19 |  | 4.78 | 57.08 | 22.37 | 79.45 | 247 | 7.04 | 2.26
Rock Island (MVR) | 135.57 | 684 |  |  | -135.57 | 94.35 | 56.44 | 150.79 | 725 | 15.22
Sacramento (SPK) | 70.78 | 180 |  |  | -70.78 | 59.57 | 45.02 | 104.59 | 182 | 33.81
San Francisco (SPN) | 15.53 | 12 |  |  | -15.53 | 22.92 | 10.2 | 33.12 | 28 | 17.59
Savannah (SAS) | 339.57 | 345 |  |  | -339.57 | 244.07 | 189.8 | 433.87 | 445 | 94.3
Seattle (NWS) | 18.7 | 77 |  |  | -18.7 | 15.54 | 3.49 | 19.03 | 78 | 0.33
St. Louis (MVS) | 231.56 | 515 |  |  | -231.56 | 191.7 | 130.63 | 322.33 | 712 | 90.77
St. Paul (MVP) | 94.84 | 134 |  |  | -94.84 | 36.34 | 26.62 | 62.96 | 175 | -31.88
Tulsa (SWT) | 831.18 | 1501 | 1055.41 |  | 224.23 | 623.03 | 324.52 | 947.55 | 1598 | 116.37 | -107.86
Vicksburg (MVK) | 349.24 | 666 | 367.87 |  | 18.63 | 259.4 | 109.53 | 368.93 | 890 | 19.69 | 1.06
Walla Walla (NWW) | 95.27 | 236 |  |  | -95.27 | 66.89 | 62.01 | 128.9 | 304 | 33.63
Wilmington (SAW) | 173.85 | 350 | 151.1 |  | -22.75 | 136.35 | 87.33 | 223.68 | 475 | 49.83 | 72.58
TOTALS | 6087.82 | 11520 | 2528.44 |  |  | 4874.19 | 2560.81 | 7435 | 14556 | 1347.18
Aggressive Schedule | Road Mileage |  |  |  |  | 493.76
Current Efforts | 818.37 |  | 124.677 |  |  | 179.58
FY 19-20 | 2918.24
FY 20-21 | 1867.93
FY 21-22 | 429.46
TOTAL | 6034
Selection Critieria:
Districts with most road mileage
Finishing partially completed Districts (OCAs)
Lumping Districts geographically
Note on I5: Andrew Huddleston: Service and Public Paved
Note on J5: Andrew Huddleston: Service and Public Unpaved
Note on B10: Andrew Huddleston: Was not included in Zach's initial rollup

## Transport Only Time Estimate (hidden)
TASK | NWK | NWO | NWS | NWW | SPL | SPA | SPN | SWG | MVN |  | SAS | SAJ | NAE | LRH | LRP | NAP | LRC | MVP | MVR
Roads
Paved/Unpaved miles from NRMA | 550 | 398 | 19 | 129 | 72 | 51 | 33 | 57 | 121 |  | 434 | 6 | 221 | 470 | 297 | 7 | 54 | 63 | 151
Rate per hour | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Estimated time | 27.5 | 19.9 | 0.95 | 6.45 | 3.6 | 2.55 | 1.65 | 2.85 | 6.05 |  | 21.7 | 0.3 | 11.05 | 23.5 | 14.85 | 0.35 | 2.7 | 3.15 | 7.55
20% contingency | 5.5 | 3.98 | 0.19 | 1.29 | 0.72 | 0.51 | 0.33 | 0.57 | 1.21 |  | 4.34 | 0.06 | 2.21 | 4.7 | 2.97 | 0.07 | 0.54 | 0.63 | 1.51
Total estimated time (hours) | 33 | 23.88 | 1.14 | 7.74 | 4.32 | 3.06 | 1.98 | 3.42 | 7.26 |  | 26.04 | 0.36 | 13.26 | 28.2 | 17.82 | 0.42 | 3.24 | 3.78 | 9.06
Parking Lots
Count from NRMA | 1021 | 756 | 78 | 304 | 146 | 29 | 28 | 41 | 48 |  | 445 | 25 | 251 | 564 | 310 | 33 | 84 | 175 | 725
Rate per hour | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Estimated time | 102.1 | 75.6 | 7.8 | 30.4 | 14.6 | 2.9 | 2.8 | 4.1 | 4.8 |  | 44.5 | 2.5 | 25.1 | 56.4 | 31 | 3.3 | 8.4 | 17.5 | 72.5
20% contingency | 20.42 | 15.12 | 1.56 | 6.08 | 2.92 | 0.58 | 0.56 | 0.82 | 0.96 |  | 8.9 | 0.5 | 5.02 | 11.28 | 6.2 | 0.66 | 1.68 | 3.5 | 14.5
Total estimated time (hours) | 122.52 | 90.72 | 9.36 | 36.48 | 17.52 | 3.48 | 3.36 | 4.92 | 5.76 |  | 53.4 | 3 | 30.12 | 67.68 | 37.2 | 3.96 | 10.08 | 21 | 87
Verification (Pre/Post)
Total Time for all features (Hours) | 155.52 | 114.6 | 10.5 | 44.22 | 21.84 | 6.54 | 5.34 | 8.34 | 13.02 | 379.92 | 79.44 | 3.36 | 43.38 | 95.88 | 55.02 | 4.38 | 13.32 | 24.78 | 96.06 | 415.62
Data collection + 10% Conservation Project Time | 171.072 | 126.06 | 11.55 | 48.642 | 24.024 | 7.194 | 5.874 | 9.174 | 14.322 | 417.912 | 87.384 | 3.696 | 47.718 | 105.468 | 60.522 | 4.818 | 14.652 | 27.258 | 105.666 | 457.182
Project Count | 17 | 9 | 5 | 8 | 1 | 7 | 3 | 2 | 4 | 56 | 3 | 2 | 32 | 40 | 19 | 4 | 4 | 12 | 5 | 121
Weeks of data collection | 3.888 | 2.865 | 0.2625 | 1.1055 | 0.546 | 0.1635 | 0.1335 | 0.2085 | 0.3255 | 9.498 | 1.986 | 0.084 | 1.0845 | 2.397 | 1.3755 | 0.1095 | 0.333 | 0.6195 | 2.4015 | 10.3905
Weeks in travel estimator | 2.4312 | 1.75 | 1.3438 | 2.075 | 1.0688 | 1.4812 | 1.4688 | 1.1375 | 1.275 | 14.0312 | 2.4937 | 1.1375 | 3.2 | 3.8188 | 2.4375 | 1.4062 | 1.275 | 1.9563 | 1.8687 | 19.5938
Total Weeks Per District | 6.3192 | 4.615 | 1.6062 | 3.1805 | 1.6148 | 1.6447 | 1.6022 | 1.346 | 1.6005 | 23.5292 | 4.4798 | 1.2215 | 4.2845 | 6.2157 | 3.813 | 1.5157 | 1.608 | 2.5758 | 4.2702 | 29.9842
Estimated hours | 252.77 | 184.6 | 64.25 | 127.22 | 64.59 | 65.79 | 64.09 | 53.84 | 64.02 | 941.17 | 179.19 | 48.86 | 171.38 | 248.63 | 152.52 | 60.63 | 64.32 | 103.03 | 170.81 | 1199.37
Adjusted estimated hours | 253 | 185 | 65 | 128 | 65 | 66 | 65 | 54 | 65 | 946 | 180 | 49 | 172 | 249 | 153 | 61 | 65 | 104 | 171 | 1204
Adjusted estimated weeks | 7 | 5 | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 28 | 5 | 2 | 5 | 7 | 4 | 2 | 2 | 3 | 5 | 35
The difference from the travel estimator is allowed as a logistical contingency. The location of projects will impact the pace and quantity of data collection
Note on A3: Andrew Huddleston: NRMA=NRM Assessment, unpaved and paved road mileage on all USACE OWNED roadways
Note on A4: Andrew Huddleston: 20 miles recorded per hour
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Makes up for potential unrecorded mileage
Note on A11: Andrew Huddleston: 10 parking lots recorded per hour
Note on A21: USACE: Project count from FY20 NRMA.
Note on A24: USACE: this comes directly from travel estimator

## Transport_LimREC Time Estimator
TASK | NWK | NWO | NWS | NWW | SPL | SPA | SPN | SWG | MVN |  | SAS | SAJ | NAE | LRH | LRP | NAP | LRC | MVP | MVR
Roads
Paved/Unpaved miles from NRMA | 550 | 398 | 19 | 129 | 72 | 51 | 33 | 57 | 121 |  | 434 | 6 | 221 | 470 | 297 | 7 | 54 | 63 | 151
Rate per hour | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Estimated time | 110 | 79.6 | 3.8 | 25.8 | 14.4 | 10.2 | 6.6 | 11.4 | 24.2 |  | 86.8 | 1.2 | 44.2 | 94 | 59.4 | 1.4 | 10.8 | 12.6 | 30.2
20% contingency | 22 | 15.92 | 0.76 | 5.16 | 2.88 | 2.04 | 1.32 | 2.28 | 4.84 |  | 17.36 | 0.24 | 8.84 | 18.8 | 11.88 | 0.28 | 2.16 | 2.52 | 6.04
Total estimated time (hours) | 132 | 95.52 | 4.56 | 30.96 | 17.28 | 12.24 | 7.92 | 13.68 | 29.04 |  | 104.16 | 1.44 | 53.04 | 112.8 | 71.28 | 1.68 | 12.96 | 15.12 | 36.24
Parking Lots
Count from NRMA | 1021 | 756 | 78 | 304 | 146 | 29 | 28 | 41 | 48 |  | 445 | 25 | 251 | 564 | 310 | 33 | 84 | 175 | 725
Rate per hour | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Estimated time | 68.0667 | 50.4 | 5.2 | 20.2667 | 9.7333 | 1.9333 | 1.8667 | 2.7333 | 3.2 |  | 29.6667 | 1.6667 | 16.7333 | 37.6 | 20.6667 | 2.2 | 5.6 | 11.6667 | 48.3333
20% contingency | 13.6133 | 10.08 | 1.04 | 4.0533 | 1.9467 | 0.38667 | 0.37333 | 0.54667 | 0.64 |  | 5.9333 | 0.33333 | 3.3467 | 7.52 | 4.1333 | 0.44 | 1.12 | 2.3333 | 9.6667
Total estimated time (hours) | 81.68 | 60.48 | 6.24 | 24.32 | 11.68 | 2.32 | 2.24 | 3.28 | 3.84 |  | 35.6 | 2 | 20.08 | 45.12 | 24.8 | 2.64 | 6.72 | 14 | 58
General REC (NOT in R1S)
Count from NRMA | 22 | 16 | 118 | 187 | 0 | 79 | 10 | 37 | 53 |  | 8 | 0 | 204 | 175 | 132 | 50 | 79 | 40 | 10
Rate per hour | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Estimated time | 0.88 | 0.64 | 4.72 | 7.48 | 0 | 3.16 | 0.4 | 1.48 | 2.12 |  | 0.32 | 0 | 8.16 | 7 | 5.28 | 2 | 3.16 | 1.6 | 0.4
20% contingency | 0.176 | 0.128 | 0.944 | 1.496 | 0 | 0.632 | 0.08 | 0.296 | 0.424 |  | 0.064 | 0 | 1.632 | 1.4 | 1.056 | 0.4 | 0.632 | 0.32 | 0.08
Total estimated time (hours) | 1.056 | 0.768 | 5.664 | 8.976 | 0 | 3.792 | 0.48 | 1.776 | 2.544 |  | 0.384 | 0 | 9.792 | 8.4 | 6.336 | 2.4 | 3.792 | 1.92 | 0.48
Verification (Pre/Post)
Total Time for all features (Hours) | 214.736 | 156.768 | 16.464 | 64.256 | 28.96 | 18.352 | 10.64 | 18.736 | 35.424 | 564.336 | 140.144 | 3.44 | 82.912 | 166.32 | 102.416 | 6.72 | 23.472 | 31.04 | 94.72 | 651.184
Data collection + 10% Conservation Project Time | 236.2096 | 172.4448 | 18.1104 | 70.6816 | 31.856 | 20.1872 | 11.704 | 20.6096 | 38.9664 | 620.7696 | 154.1584 | 3.784 | 91.2032 | 182.952 | 112.6576 | 7.392 | 25.8192 | 34.144 | 104.192 | 716.3024
Project Count | 17 | 9 | 5 | 8 | 1 | 7 | 3 | 2 | 4 | 56 | 3 | 2 | 32 | 40 | 19 | 4 | 4 | 12 | 5 | 121
Weeks of data collection | 5.3684 | 3.9192 | 0.4116 | 1.6064 | 0.724 | 0.4588 | 0.266 | 0.4684 | 0.8856 | 14.1084 | 3.5036 | 0.086 | 2.0728 | 4.158 | 2.5604 | 0.168 | 0.5868 | 0.776 | 2.368 | 16.2796
Weeks in travel estimator | 2.4312 | 1.75 | 1.3438 | 2.075 | 1.0688 | 1.4812 | 1.4688 | 1.1375 | 1.275 | 14.0312 | 2.4937 | 1.1375 | 3.2 | 3.8188 | 2.4375 | 1.4062 | 1.275 | 1.9563 | 1.8687 | 19.5938
Total Weeks Per District | 7.7996 | 5.6692 | 1.7553 | 3.6814 | 1.7928 | 1.94 | 1.7348 | 1.6059 | 2.1606 | 28.1396 | 5.9973 | 1.2235 | 5.2728 | 7.9767 | 4.9979 | 1.5742 | 1.8618 | 2.7323 | 4.2367 | 35.8733
Estimated hours | 311.986 | 226.768 | 70.214 | 147.256 | 71.71 | 77.602 | 69.39 | 64.236 | 86.424 | 1125.586 | 239.894 | 48.94 | 210.912 | 319.07 | 199.916 | 62.97 | 74.472 | 109.29 | 169.47 | 1434.934
Adjusted estimated hours | 312 | 227 | 71 | 148 | 72 | 78 | 70 | 65 | 87 | 1130 | 240 | 49 | 211 | 320 | 200 | 63 | 75 | 110 | 170 | 1438
Adjusted estimated weeks | 8 | 6 | 2 | 4 | 2 | 2 | 2 | 2 | 3 | 31 | 6 | 2 | 6 | 8 | 5 | 2 | 2 | 3 | 5 | 39
The difference from the travel estimator is allowed as a logistical contingency. The location of projects will impact the pace and quantity of data. collection
Disclaimer: This information is accurate to the best of the USACE's knowledge. There may be some increases or decreases based on what is found in the field.
Note on A3: Andrew Huddleston: NRMA=NRM Assessment, unpaved and paved road mileage on all USACE OWNED roadways
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to hone in the rate of road collection...how many road miles can be collected in 1 hour?
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes: Shelters, Campsites, and Picnic Sites
Note on A18: Andrew Huddleston: 30 campsites/shelters/picnic sites per hour
Note on A28: USACE: Project count from FY20 NRMA.
Note on A31: USACE: this comes directly from travel estimator

## Travel Estimator
| NWK | NWO | NWS | NWW | SPL | SPA | SPN | SWG | MVN | SAS | SAJ | NAE | LRH | LRP | NAP | LRC | MVP | MVR
Proj Count | 17 | 9 | 5 | 8 | 1 | 7 | 3 | 2 | 4 | 3 | 2 | 32 | 40 | 19 | 4 | 4 | 12 | 5
# Projects with 1-10 PSAs | 15 | 8 | 5 | 4 | 1 | 7 | 1 | 2 | 4 | 1 | 2 | 32 | 40 | 18 | 3 | 4 | 11 | 1
Hours/proj | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75 | 2.75
Total Hours | 41.25 | 22 | 13.75 | 11 | 2.75 | 19.25 | 2.75 | 5.5 | 11 | 2.75 | 5.5 | 88 | 110 | 49.5 | 8.25 | 11 | 30.25 | 2.75 | 437.25
# Projects with 11-25 PSAs | 2 | 1 | 0 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 4
Hours/proj | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Total Hours | 16 | 8 | 0 | 32 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 32 | 128
# Projects with 26-50 PSAs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours/proj | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Total Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
# Projects with 50+ PSAs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hours/proj | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Total Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
Total Hours of Travel Between PSA's and Projects | 57.25 | 30 | 13.75 | 43 | 2.75 | 19.25 | 18.75 | 5.5 | 11 | 59.75 | 5.5 | 88 | 110 | 57.5 | 16.25 | 11 | 38.25 | 34.75 | 622.25 | 1300.41
Hours of Prep and Travel Between Districts | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Total Est Weeks of Prep and Travel | 2.4312 | 1.75 | 1.3438 | 2.075 | 1.0688 | 1.4812 | 1.4688 | 1.1375 | 1.275 | 2.4937 | 1.1375 | 3.2 | 3.75 | 2.4375 | 1.4062 | 1.275 | 1.9563 | 1.8687
Weeks of data collection | 3.91 | 2.881 | 0.3805 | 1.2925 | 0.546 | 0.2425 | 0.1435 | 0.2455 | 0.3785 | 1.994 | 0.084 | 1.2885 | 2.572 | 1.5075 | 0.1595 | 0.412 | 0.6595 | 2.4075
Total Weeks of Data and Travel | 6.3412 | 4.631 | 1.7243 | 3.3675 | 1.6148 | 1.7237 | 1.6122 | 1.383 | 1.6535 | 4.4878 | 1.2215 | 4.4885 | 6.322 | 3.945 | 1.5657 | 1.687 | 2.6158 | 4.2762
Nights of lodging needed | 44.3887 | 32.417 | 12.0698 | 23.5725 | 11.3033 | 12.0663 | 11.2858 | 9.681 | 11.5745 | 31.4143 | 8.5505 | 31.4195 | 44.254 | 27.615 | 10.9603 | 11.809 | 18.3103 | 29.9337
Est nights in paid housing x3 rooms | 133.1662 | 97.251 | 36.2093 | 70.7175 | 33.9098 | 36.1988 | 33.8573 | 29.043 | 34.7235 | 94.2428 | 25.6515 | 94.2585 | 132.762 | 82.845 | 32.8807 | 35.427 | 54.9308 | 89.8012
Hotel rate in region | 115.75 | 120 | 148.5 | 129.8333 | 179.2 | 141.25 | 141.25 | 159.3333 | 117.5 | 123.6667 | 158.3333 | 188.25 | 119 | 134.5 | 136 | 140 | 135.5 | 141.5
Est Lodging/rental costs | 15413.9934 | 11670.12 | 5377.0736 | 9181.4888 | 6076.6272 | 5113.0734 | 4782.3366 | 4627.518 | 4080.0113 | 11654.6868 | 4061.4875 | 17744.1626 | 15798.678 | 11142.6525 | 4471.782 | 4959.78 | 7443.1166 | 12706.8769
Utilities | 121.5625 | 87.5 | 67.1875 | 103.75 | 53.4375 | 74.0625 | 73.4375 | 56.875 | 63.75 | 124.6875 | 56.875 | 160 | 187.5 | 121.875 | 70.3125 | 63.75 | 97.8125 | 93.4375
Rental Car cost | 531.8359 | 382.8125 | 293.9453 | 453.9063 | 233.7891 | 324.0234 | 321.2891 | 248.8281 | 278.9062 | 545.5078 | 248.8281 | 700 | 820.3125 | 533.2031 | 307.6172 | 278.9062 | 427.9297 | 408.7891
Rental Car Gas | 1215.625 | 875 | 671.875 | 1037.5 | 534.375 | 740.625 | 734.375 | 568.75 | 637.5 | 1246.875 | 568.75 | 1600 | 1875 | 1218.75 | 703.125 | 637.5 | 978.125 | 934.375
Total Travel | 17283.0169 | 13015.4325 | 6410.0814 | 10776.645 | 6898.2288 | 6251.7844 | 5911.4381 | 5501.9711 | 5060.1675 | 13571.7571 | 4935.9406 | 20204.1626 | 18681.4905 | 13016.4806 | 5552.8367 | 5939.9362 | 8946.9838 | 14143.4784
Round Up | 17300 | 13100 | 6500 | 10800 | 6900 | 6300 | 6000 | 5600 | 5100 | 13600 | 5000 | 20300 | 18700 | 13100 | 5600 | 6000 | 9000 | 14200
Crew = 10
Cars = 5
1 hour per PSA/1 day per project
Assume mixed gender so three rooms needed
Assume 25% of time can get project lodging
Use perdiem to help estimate hotel costs in region
Enterprise lease program $175/week/vehicle (Sedan/SUV) 2 ppl per vehicle
30 min travel between PSA's
1-10 psa/proj | NWK: 2.75 hours travel per project
11-25 psa/proj | NWK: 8 hours travel per project
26-50 psa/proj | NWK: 17 hours travel per project
50+ psa/proj | NWK: 40 hours travel per project
Note on A21: Andrew Huddleston: This includes intro, pre, and post meetings with dist and proj staff
Note on A23: Andrew Huddleston: Pulled from time estimator
Note on A29: USACE: est $50 per week
Note on A32: Andrew Huddleston: 5 cars $100/week

## District Data
| District | Projects | # PSA's/Proj | PSA's in R1S? | # Campsites in R1S | # Shelters in R1S | # Pic Sites in R1S | 2021 Visitation | 5+ PSA's or >400k vis
FY22-23: | Kansas City | Clinton Lake | 8 | Y |  |  |  | 1300952 | Yes
| 17 | Harlan Lake | 9 | Y |  |  |  | 851667 | Yes
|  | Harry S. Truman | 16 | Y |  |  |  | 1977707 | Yes
|  | Hillsdale | 1 | N | 0 | 1 | 2 | 458602 | Yes
|  | Kanopolis | 5 | Y |  |  |  | 394212 | Yes
|  | Little Blue River | 1 | N | 0 | 0 | 1 | 872995 | Yes
|  | Long Branch | 1 | N | 0 | 0 | 7 | 265748 | No
|  | Melvern Lake | 5 | Y |  |  |  | 526675 | Yes
|  | Milford Lake | 9 | Y |  |  |  | 1395793 | Yes
|  | Perry Lake | 8 | Y |  |  |  | 674571 | Yes
|  | Pomme De Terre | 8 | Y |  |  |  | 1054838 | Yes
|  | Pomona Lake | 9 | Y |  |  |  | 459875 | Yes
|  | Rathbun Lake | 6 | Y |  |  |  | 651732 | Yes
|  | Smithville Lake | 2 | N | 0 | 1 | 10 | 1244147 | No
|  | Stockton Lake | 14 | Y |  |  |  | 914214 | Yes
|  | Tuttle Creek | 6 | Y |  |  |  | 1068742 | Yes
|  | Wilson Lake | 4 | Y |  |  |  | 502573
|  | TOTAL |  |  | 0 | 2 | 20 |  | Yes
| Omaha | Big Bend Dam | 9 | Y |  |  |  | 1096630 | Yes
| 9 | Cold Brook Lake | 1 | Y |  |  |  | 57172 | No
|  | Cottonwood Springs | 1 | Y |  |  |  | 16714 | No
|  | Fort Peck | 26 | Y |  |  |  | 611785 | Yes
|  | Fort Randall | 6 | N | 0 | 0 | 7 | 362994 | Yes
|  | Garrison Dam | 10 | Y |  |  |  | 1878945 | Yes
|  | Gavins Point | 7 | Y |  |  |  | 1081246 | Yes
|  | Oahe Dam | 6 | Y |  |  |  | 1392988 | Yes
|  | Pipestem Lake | 1 | N | 6 | 0 | 3 | 33804 | No
|  | TOTAL |  |  | 6 | 0 | 10
| Seattle | Albeni Falls Dam | 7 | Y |  |  |  | 448892 | Yes
| 5 | Chief Joseph Dam | 10 | N | 3 | 10 | 49 | 277633 | Yes
|  | Ballard Locks | 1 | N | 0 | 0 | 0 | 723563 | Yes
|  | Libby Dam | 7 | N | 24 | 4 | 28 | 111397 | Yes
|  | Mud Mountain | 1 | Y |  |  |  | 16004 | No
|  | TOTAL |  |  | 27 | 14 | 77
| Walla Walla | Dworshak | 12 | Y |  |  |  | 364093 | Yes
| 8 | Ice Harbor | 14 | Y |  |  |  | 265906 | Yes
|  | Little Goose | 10 | N | 49 | 0 | 6 | 298229 | Yes
|  | Lower Granite | 14 | N | 52 | 4 | 33 | 1997385 | Yes
|  | Lower Monumental | 6 | N | 41 | 2 | 0 | 170015 | Yes
|  | Lucky Peak | 8 | Y |  |  |  | 914187 | Yes
|  | McNary Lock and Dam | 11 | Y |  |  |  | 2927322 | Yes
|  | Mill Creek | 1 | Y |  |  |  | 123160 | No
|  | TOTAL |  |  | 142 | 6 | 39
| Los Angeles (SPL) | Sepulveda Dam | 1 | N | 0 | 0 | 0 | 991417 | Yes
|  | TOTAL |  |  | 0 | 0 | 0
| Albuquerque (SPA) | Abiquiu Dam | 5 | Y |  |  |  | 127099 | Yes
| 7 | Cochiti Lake | 3 | Y |  |  |  | 104779 | No
|  | Conchas Lake | 4 | N | 20 | 1 | 40 | 92535 | No
|  | Galisteo Dam | 1 | N | 0 | 0 | 6 | 250 | No
|  | John Martin Resevoir | 1 | N | 0 | 1 | 0 | 499674 | Yes
|  | Santa Rosa Dam | 1 | N | 0 | 0 | 2 | 66616 | No
|  | Two Rivers Dam | 1 | N | 0 | 0 | 9 | 958 | No
|  | TOTAL |  |  | 20 | 2 | 57
| Galveston (SWG) | Buffalo Bayou | 1 | N | 0 | 0 | 2 | 2456445 | Yes
| 2 | Wallisville Lake | 4 | N | 0 | 1 | 34 | 75008 | No
|  | TOTAL |  |  | 0 | 1 | 36
| New Orleans (MVN) | Atch Basin Floodway | 2 | N | 0 | 0 | 2 | 322066 | No
| 4 | Bonnet Carre Spillway | 6 | N | 0 | 0 | 10 | 495369 | Yes
|  | Old River | 2 | N | 30 | 0 | 7 | 34433 | No
|  | Port Allen | 2 | N | 0 | 0 | 4 | 289819 | No
|  | TOTAL |  |  | 30 | 0 | 23
FY23: | Savannah (SAS) | Hartwell Dam | 48 | Y |  |  |  | 8495905 | Yes
| 3 | J Strom Thurmond Dam | 53 | Y |  |  |  | 4529567 | Yes
|  | Richard B. Russel Dam | 3 | N | 0 | 2 | 6 | 669132 | Yes
|  | TOTAL |  |  | 0 | 2 | 6
| Jacksonville (SAJ) | Central and South FL | 4 | Y |  |  |  | 624241 | Yes
| 2 | Okeechobee Waterway | 3 | Y |  |  |  | 584238 | Yes
|  | TOTAL |  |  | 0 | 0 | 0
| New England (NAE) | Ball Mountain Lake | 2 | Y |  |  |  | 67800 | No
| 32 | Barre Falls Dam | 1 | Y |  |  |  | 70436 | No
|  | Birch Hill Dam | 1 | N | 0 | 0 | 7 | 489431 | Yes
|  | Black Rock Lake | 1 | N | 0 | 0 | 0 | 46371 | No
|  | Blackwater Dam | 6 | N | 0 | 0 | 7 | 24674 | Yes
|  | Buffumville Lake | 2 | Y |  |  |  | 134127 | Yes
|  | Cape Cod Canal | 5 | N | 0 | 4 | 108 | 2784074 | Yes
|  | Charles River | 1 | N | 0 | 0 | 0 | 3659 | No
|  | Colebrooke River Lake | 2 | N | 0 | 0 | 3 | 70699 | No
|  | Conant Brook Dam | 1 | N | 0 | 0 | 0 | 19503 | No
|  | East Brimfield Dam | 3 | N | 0 | 0 | 16 | 135435 | No
|  | Edward MacDowell Lake | 2 | Y |  |  |  | 40056 | No
|  | Franklin Falls Dam | 6 | N | 0 | 2 | 29 | 145149 | Yes
|  | Hancock Brook Lake | 2 | N | 0 | 0 | 0 | 21074 | No
|  | Hodges Village Dam | 1 | N | 0 | 0 | 2 | 168927 | No
|  | Hop Brook Lake | 2 | Y |  |  |  | 187868 | No
|  | Hopkinton Everett Lake | 8 | Y |  |  |  | 418235 | Yes
|  | Knightville Dam | 3 | Y |  |  |  | 14190 | No
|  | Littleville Lake | 3 | N | 0 | 0 | 0 | 20261 | No
|  | Mansfield Hollow Lake | 1 | N | 0 | 0 | 0 | 493682 | Yes
|  | North Hartland Lake | 4 | Y |  |  |  | 129357 | No
|  | North Springfield Lake | 5 | Y |  |  |  | 90421 | Yes
|  | Northfield Brook Lake | 1 | Y |  |  |  | 31933 | No
|  | Otter Brook Lake | 3 | Y |  |  |  | 80070 | No
|  | Surry Mountain Lake | 3 | Y |  |  |  | 59442 | No
|  | Thomaston Dam | 1 | N | 0 | 0 | 26 | 98952 | No
|  | Townshend Lake | 3 | Y |  |  |  | 47528 | No
|  | Tully Lake | 1 | Y |  |  |  | 229700 | No
|  | Union Village Dam | 2 | Y |  |  |  | 56888 | No
|  | West Hill Dam | 2 | Y |  |  |  | 73629 | No
|  | West Thompson Lake | 2 | Y |  |  |  | 250539 | No
|  | Westville Lake | 2 | Y |  |  |  | 100394 | No
|  | TOTAL |  |  | 0 | 6 | 198
| Huntington (LRH) | Alum Creek Lake | 2 | Y |  |  |  | 236774 | No
| 40 | Atwood Lake | 1 | N | 0 | 1 | 29 | 29004 | No
|  | Beach City Lake | 1 | N | 0 | 0 | 4 | 7800 | No
|  | Beech Fork Lake | 3 | Y |  |  |  | 116491 | No
|  | Belleville Lock | 2 | N | 0 | 2 | 0 | 33135 | No
|  | Bluestone Lake | 3 | Y |  |  |  | 64507 | No
|  | Bolivar Dam | 1 | N | 0 | 0 | 17 | 7250 | No
|  | Burnsville Lake | 7 | Y |  |  |  | 128487 | Yes
|  | Capt. Anthony Meldahl | 2 | N | 0 | 2 | 8 | 47905 | No
|  | Charles Mill Lake | 1 | N | 0 | 0 | 25 | 30674 | No
|  | Clendening Lake | 1 | N | 0 | 0 | 10 | 12270 | No
|  | Deer Creek Lake | 1 | Y |  |  |  | 215790 | No
|  | Delaware Lake | 1 | Y |  |  |  | 84248 | No
|  | Dewey Lake | 3 | Y |  |  |  | 76795 | No
|  | Dillon Lake | 1 | Y |  |  |  | 54998 | No
|  | Dover Dam | 1 | N | 0 | 0 | 6 | 10788 | No
|  | East Lynn Lake | 6 | Y |  |  |  | 114094 | Yes
|  | Fishtrap Lake | 5 | Y |  |  |  | 167010 | Yes
|  | Grayson Lake | 2 | Y |  |  |  | 103857 | No
|  | Greenup Lock | 3 | N | 0 | 8 | 2 | 56820 | No
|  | John Flannagan Dam | 7 | Y |  |  |  | 73788 | Yes
|  | London Lock | 1 | N | 0 | 0 | 3 | 4789 | No
|  | Marmet Lock | 1 | N | 0 | 2 | 0 | 15615 | No
|  | Mohicanville Dam | 1 | N | 0 | 0 | 0 | 5756 | No
|  | NB Kokosing River Lake | 2 | N | 0 | 0 | 0 | 5857 | No
|  | NF of Pound Lake | 1 | N | 0 | 0 | 3 | 15262 | No
|  | Paint Creek Lake | 1 | Y |  |  |  | 47906 | No
|  | Paintsville Lake | 2 | N | 0 | 0 | 0 | 111945 | No
|  | Pleasant Hill Lake | 1 | N | 0 | 1 | 5 | 16731 | No
|  | RD Bailey Lake | 5 | Y |  |  |  | 144374 | Yes
|  | Racine Lock | 1 | N | 0 | 2 | 0 | 6694 | No
|  | Robert Byrd Lock | 2 | N | 0 | 5 | 20 | 31235 | No
|  | Summersville Lake | 6 | Y |  |  |  | 409987 | Yes
|  | Sutton Lake | 4 | Y |  |  |  | 186205 | No
|  | Tappan Lake | 1 | N | 0 | 0 | 3 | 16618 | No
|  | Tom Jenkins Dam | 1 | N | 0 | 2 | 8 | 14068 | No
|  | Willow Island Lock | 1 | N | 0 | 2 | 0 | 9761 | No
|  | Wills Creek Lake | 1 | N | 0 | 0 | 0 | 27886 | No
|  | Winfield Lock | 2 | N | 0 | 5 | 0 | 20169 | No
|  | Yatesville Lake | 1 | N | 0 | 0 | 0 | 37499 | No
|  | TOTAL |  |  | 0 | 32 | 143
| Pittsburgh (LRP) | Berlin Lake | 3 | N | 316 | 2 | 60 | 788759 | Yes
| 19 | Conemaugh River Lake | 3 | Y |  |  |  | 239036 | No
|  | Crooked Creek Lake | 6 | Y |  |  |  | 248927 | Yes
|  | E. Branch Clarion Lake | 4 | Y |  |  |  | 18010 | No
|  | Hannibal Locks | 1 | N | 0 | 1 | 11 | 114103 | No
|  | Kinzua and Allegheny Resevoir | 4 | N | 0 | 0 | 10 | 175105 | No
|  | Loyalhanna Lake | 2 | Y |  |  |  | 260027 | No
|  | Mahoning Creek Lake | 1 | N | 0 | 3 | 35 | 60054 | No
|  | Michael Kirwan Dam | 3 | N | 0 | 1 | 3 | 568335 | Yes
|  | Mosquito Creek Lake | 4 | N | 0 | 1 | 57 | 882639 | Yes
|  | New Cumberland Locks and Dam | 1 | N | 0 | 0 | 3 | 14016 | No
|  | Pike Island Locks and Dam | 1 | N | 0 | 0 | 0 | 37465 | No
|  | Shenango River Lake | 21 | Y |  |  |  | 560017 | Yes
|  | Stonewall Jackson Lake | 1 | N | 0 | 0 | 3 | 233848 | No
|  | Tionesta Lake | 7 | Y |  |  |  | 112514 | Yes
|  | Tygart Lake | 1 | N | 0 | 1 | 1 | 441992 | Yes
|  | Union City Lake | 1 | N | 0 | 0 | 2 | 28763 | No
|  | Woodcock Creek | 5 | Y |  |  |  | 222149 | Yes
|  | Youghigheny River Lake | 4 | Y |  |  |  | 485049 | Yes
|  | TOTAL |  |  | 316 | 9 | 185
| San Francisco (SPN) | Lake Mendocino | 16 | Y |  |  |  | 267288 | Yes
| 3 | Lake Sonoma | 14 | Y |  |  |  | 497677 | Yes
|  | San Francisco Bay | 1 | N | 0 | 0 | 10 | 101269 | No
|  | TOTAL |  |  | 0 | 0 | 10
| Philadelphia (NAP) | Beltzville Lake | 1 | N | 0 | 0 | 1 | 670708 | Yes
| 4 | Blue Marsh Lake | 23 | Y |  |  |  | 934679 | Yes
|  | Francis Walter Dam | 6 | N | 0 | 0 | 47 | 130644 | Yes
|  | Prompton Lake | 2 | N | 0 | 0 | 2 | 48463 | No
|  | TOTAL |  |  | 0 | 0 | 50
| Chicago (LRC) | J. Edward Roush Lake | 3 | N | 0 | 3 | 29 | 233811 | No
| 4 | Mississinewa Lake | 3 | N | 0 | 3 | 29 | 565690 | Yes
|  | Salamonite Lake | 2 | N | 0 | 2 | 13 | 334611 | No
|  | Sturgeon Bay | 1 | N | 0 | 0 | 0 | 31277 | No
|  | TOTAL |  |  | 0 | 8 | 71
| St. Paul (MVP) | Cross Lake | 5 | Y |  |  |  | 162372 | Yes
| 12 | Eau Galle River Lake | 5 | Y |  |  |  | 64403 | Yes
|  | Gull Lake | 2 | Y |  |  |  | 89425 | No
|  | Lac Qui Parle Lakes | 2 | N | 0 | 2 | 16 | 32718 | No
|  | Lake Ashtabula | 7 | Y |  |  |  | 146109 | Yes
|  | Lake Traverse | 3 | N | 0 | 0 | 13 | 18713 | No
|  | Leech Lake | 1 | Y |  |  |  | 32567 | No
|  | Mississippi River | 16 | Y |  |  |  | 226347 | Yes
|  | Orwell Lake | 1 | N | 0 | 2 | 7 | 7616 | No
|  | Pokegema Lake | 1 | Y |  |  |  | 25177 | No
|  | Sandy Lake Resevoir | 1 | Y |  |  |  | 12899 | No
|  | Winnibigosh Lake | 1 | Y |  |  |  | 14768 | No
|  | TOTAL |  |  | 0 | 4 | 36
| Rock Island (MVR) | Coraville Lake | 28 | Y |  |  |  | 1163057 | Yes
| 5 | Illinois Waterway | 4 | N | 0 | 1 | 9 | 109072 | No
|  | Mississippi River | 32 | Y |  |  |  | 2459035 | Yes
|  | Red Rock Dam | 37 | Y |  |  |  | 1130255 | Yes
|  | Saylorville Lake | 19 | Y |  |  |  | 2374042 | Yes
|  | TOTAL |  |  | 0 | 1 | 9
|  | Total Projects | 177 | [5 empty] | Revised Total Projects
|  | Total PSA's | 907 | [5 empty] | Revised Total PSA's
|  | AVG PSA's | 5.1243
|  | AVG Visitation | [5 empty] | 435172.339
|  | # PSA Assets NOT in R1S |  |  | 541 | 87 | 970
Note on F201: Andrew Huddleston: Campsites NOT in R1S
Note on G201: Andrew Huddleston: Shelters NOT in R1S
Note on H201: Andrew Huddleston: Picnic Sites NOT in R1S

## Final Mile_Lot Count
Full Capability - Anticipated - Add FHWA Request:
| District | Number of PSA's | Day Use Car Spaces | Developed Single User Campsites | Number Parking Lots | Paved Miles | Unpaved Miles | Total Mileage | Month of Completion | # Weeks | $/month/rental car | Number Rental Cars | Rental Car Mo Cost | ~Hours per PSA | ~Days per Project
FY22: | Omaha | 220 | 22129 | 4837 | 756 | 178.19 | 219.9 | 398.09 | SEPT 22 | 6 | 700 | 5 | 3500 | 1 | 1
FY23: | Seattle | 34 | 1160 | 235 | 78 | 15.54 | 3.49 | 19.03 | OCT 22 | 2 | 700 | 5 | 3500 | 1 | 1
| Walla Walla | 107 | 9318 | 1129 | 304 | 66.89 | 62.01 | 128.9 | NOV 22 | 4 | 1400 | 5 | 7000 | 1 | 1
| Los Angeles | 16 | 25691 | 454 | 146 | 51.5 | 20.7 | 72.2 | DEC 22 | 2 | 700 | 5 | 3500 | 1 | 1
| Albuquerque | 31 | 1668 | 718 | 29 | 26.09 | 24.47 | 50.56 | DEC 22 | 2 | 700 | 5 | 3500 | 1 | 1
| San Francisco | 32 | 1583 | 473 | 28 | 22.92 | 10.2 | 33.12 | JAN 23 | 2 | 700 | 5 | 3500 | 1 | 1
| Galveston | 14 | 6452 | 0 | 41 | 32.75 | 24.64 | 57.39 | JAN 23 | 2 | 700 | 5 | 3500 | 1 | 1
| New Orleans | 14 | 1675 | 0 | 48 | 5.75 | 114.76 | 120.51 | FEB 23 | 2 | 700 | 5 | 3500 | 1 | 1
| Kansas City | 208 | 19829 | 9853 | 1021 | 413.98 | 136.14 | 550.12 | MAR 23 | 8 | 700 | 5 | 3500 | 1 | 1
|  | 644 | 87922 | 17226 | 2423 | 790.69 | 606.11 | 1396.8
FY24: | Savannah | 254 | 8192 | 2894 | 445 | 244.07 | 189.8 | 433.87 | APR 23 | 6 | 700 | 5 | 3500 | 1 | 1
| Jacksonville | 8 | 437 | 109 | 25 | 5.75 | 0.55 | 6.3 | MAY 23 | 2 | 700 | 5 | 3500 | 1 | 1
| New England | 98 | 7934 | 930 | 251 | 80.96 | 140.02 | 220.98 | JUNE 23 | 6 | 700 | 5 | 3500 | 1 | 1
| Huntington | 184 | 16432 | 3798 | 564 | 192.3 | 278.04 | 470.34 | JULY 23 | 8 | 700 | 5 | 3500 | 1 | 1
| Pittsburgh | 163 | 10552 | 1887 | 310 | 120.57 | 176.14 | 296.71 | AUG 23 | 5 | 700 | 5 | 3500 | 1 | 1
| Philadelphia | 36 | 2312 | 0 | 33 | 5.11 | 1.82 | 6.93 | SEPT 23 | 2 | 700 | 5 | 3500 | 1 | 1
| Chicago | 25 | 2283 | 830 | 84 | 39.97 | 13.85 | 53.82 | OCT 23 | 2
| St. Paul | 100 | 1953 | 1256 | 175 | 36.34 | 26.62 | 62.96 | NOV 23 | 3 | 700 | 5 | 3500 | 1 | 1
| Rock Island | 227 | 10433 | 2962 | 725 | 94.35 | 56.44 | 150.79 | DEC 23 | 5
|  | 1127 | 62111 | 15139 | 2640 | 842.34 | 893.48 | 1735.82
Note on C2: Huddleston, Andrew J CIV USARMY CENWS (USA): TOTAL PSA's, USACE managed PSA's is much less
Note on M2: Andrew Huddleston: 2 ppl per vehicle…11 ppl on the team

## Sheet2 (hidden)
USACE FLTP Road Mileage Comparison
Original Road Mileage/Dist |  |  | SCA Road Mileage/Dist |  |  | NRMA Road Mileage/Dist
District: | Road Mileage | Parking Lots | Road Mileage | Parking Lots | Difference | Paved | Unpaved | Road Mileage | Parking Lots | Difference | SCA Actual Diff
Alaska (POA) | 13 | 0 |  |  | -13 | 6.5 | 6.5 | 13 | 0 | 0
Albuquerque (SPA) | 42.71 | 21 |  |  | -42.71 | 26.09 | 24.47 | 50.56 | 29 | 7.85
Baltimore (NAB) | 77.89 | 127 |  |  | -77.89 | 78.18 | 58.46 | 136.64 | 133 | 58.75
Buffalo (LRB) | 1.9 | 8 |  |  | -1.9 | 1.95 | 1.55 | 3.5 | 7 | 1.6
Chicago (LRC) | 53.82 | 84 |  |  | -53.82 | 39.97 | 13.85 | 53.82 | 84 | 0
Detroit (LRE) | 1 | 0 |  |  | -1 | 1 | 0 | 1 | 2 | 0
Fort Worth (SWF) | 540.93 | 1071 |  |  | -540.93 | 536.05 | 65.04 | 601.09 | 1763 | 60.16
Galveston (SWG) | 48.11 | 12 |  |  | -48.11 | 32.75 | 24.64 | 57.39 | 41 | 9.28
Honolulu (POH) | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1015000
Huntington (LRH) | 312.96 | 391 |  |  | -312.96 | 192.3 | 278.04 | 470.34 | 564 | 157.38 |  | Roads budget
Jacksonville (SAJ) | 7.5 | 26 |  |  | -7.5 | 5.75 | 0.55 | 6.3 | 25 | -1.2
Kansas City (NWK) | 502.44 | 832 |  |  | -502.44 | 413.98 | 136.14 | 550.12 | 1021 | 47.68
Little Rock (SWL) | 395.72 | 852 |  |  | -395.72 | 379.35 | 35.65 | 415 | 1119 | 19.28 |  | 508000
Los Angeles (SPL) | 20 | 260 |  |  | -20 | 51.5 | 20.7 | 72.2 | 146 | 52.2 |  | spent on roads alone
Louisville (LRL) | 253.48 | 467 |  |  | -253.48 | 212.43 | 48.19 | 260.62 | 488 | 7.14
Mobile (SAM) | 465.59 | 823 | 617.55 |  | 151.96 | 455.62 | 97.35 | 552.97 | 1214 | 87.38 | -64.58
Nashville (LRN) | 260.98 | 541 | 259.32 |  | -1.66 | 242.95 | 29.08 | 272.03 | 663 | 11.05 | 12.71
New England (NAE) | 95.94 | 184 |  |  | -95.94 | 80.96 | 140.02 | 220.98 | 251 | 125.04
New Orleans (MVN) | 73 | 36 |  |  | -73 | 5.75 | 114.76 | 120.51 | 48 | 47.51 |  | 200.9144
Omaha (NWO) | 361.08 | 776 |  |  | -361.08 | 178.19 | 219.9 | 398.09 | 756 | 37.01
Philadelphia (NAP) | 9.49 | 10 |  |  | -9.49 | 5.11 | 1.82 | 6.93 | 33 | -2.56
Pittsburgh (LRP) | 121.78 | 196 |  |  | -121.78 | 120.57 | 176.14 | 296.71 | 310 | 174.93
Portland (NWP) | 72.41 | 103 | 77.19 |  | 4.78 | 57.08 | 22.37 | 79.45 | 247 | 7.04 | 2.26
Rock Island (MVR) | 135.57 | 684 |  |  | -135.57 | 94.35 | 56.44 | 150.79 | 725 | 15.22
Sacramento (SPK) | 70.78 | 180 |  |  | -70.78 | 59.57 | 45.02 | 104.59 | 182 | 33.81
San Francisco (SPN) | 15.53 | 12 |  |  | -15.53 | 22.92 | 10.2 | 33.12 | 28 | 17.59
Savannah (SAS) | 339.57 | 345 |  |  | -339.57 | 244.07 | 189.8 | 433.87 | 445 | 94.3
Seattle (NWS) | 18.7 | 77 |  |  | -18.7 | 15.54 | 3.49 | 19.03 | 78 | 0.33
St. Louis (MVS) | 231.56 | 515 |  |  | -231.56 | 191.7 | 130.63 | 322.33 | 712 | 90.77
St. Paul (MVP) | 94.84 | 134 |  |  | -94.84 | 36.34 | 26.62 | 62.96 | 175 | -31.88
Tulsa (SWT) | 831.18 | 1501 | 1055.41 |  | 224.23 | 623.03 | 324.52 | 947.55 | 1598 | 116.37 | -107.86
Vicksburg (MVK) | 349.24 | 666 | 367.87 |  | 18.63 | 259.4 | 109.53 | 368.93 | 890 | 19.69 | 1.06
Walla Walla (NWW) | 95.27 | 236 |  |  | -95.27 | 66.89 | 62.01 | 128.9 | 304 | 33.63
Wilmington (SAW) | 173.85 | 350 | 151.1 |  | -22.75 | 136.35 | 87.33 | 223.68 | 475 | 49.83 | 72.58
TOTALS | 6087.82 | 11520 | 2528.44 |  |  | 4874.19 | 2560.81 | 7435 | 14556 | 1347.18
Aggressive Schedule | Road Mileage |  |  |  |  | 493.76
Current Efforts | 818.37 |  | 124.677 |  |  | 179.58
FY 19-20 | 2918.24
FY 20-21 | 1867.93
FY 21-22 | 429.46
TOTAL | 6034
Selection Critieria:
Districts with most road mileage
Finishing partially completed Districts (OCAs)
Lumping Districts geographically
Note on I5: Andrew Huddleston: Service and Public Paved
Note on J5: Andrew Huddleston: Service and Public Unpaved
Note on B10: Andrew Huddleston: Was not included in Zach's initial rollup

## OCA Time Estimator (hidden)
TASK | NWK | NWO | NWS | NWW | SPL | SPA | SPN | SWG | MVN |  | SAS | SAJ | NAE | LRH | LRP | NAP | LRC | MVP | MVR
Roads
Paved/Unpaved miles from NRMA | 550 | 398 | 19 | 129 | 72 | 51 | 33 | 57 | 121 |  | 434 | 6 | 221 | 470 | 297 | 7 | 54 | 63 | 151
Rate per hour | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Estimated time | 27.5 | 19.9 | 0.95 | 6.45 | 3.6 | 2.55 | 1.65 | 2.85 | 6.05 |  | 21.7 | 0.3 | 11.05 | 23.5 | 14.85 | 0.35 | 2.7 | 3.15 | 7.55
20% contingency | 5.5 | 3.98 | 0.19 | 1.29 | 0.72 | 0.51 | 0.33 | 0.57 | 1.21 |  | 4.34 | 0.06 | 2.21 | 4.7 | 2.97 | 0.07 | 0.54 | 0.63 | 1.51
Total estimated time (hours) | 33 | 23.88 | 1.14 | 7.74 | 4.32 | 3.06 | 1.98 | 3.42 | 7.26 |  | 26.04 | 0.36 | 13.26 | 28.2 | 17.82 | 0.42 | 3.24 | 3.78 | 9.06
Parking Lots
Count from NRMA | 1021 | 756 | 78 | 304 | 146 | 29 | 28 | 41 | 48 |  | 445 | 25 | 251 | 564 | 310 | 33 | 84 | 175 | 725
Rate per hour | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Estimated time | 40.84 | 30.24 | 3.12 | 12.16 | 5.84 | 1.16 | 1.12 | 1.64 | 1.92 |  | 17.8 | 1 | 10.04 | 22.56 | 12.4 | 1.32 | 3.36 | 7 | 29
20% contingency | 8.168 | 6.048 | 0.624 | 2.432 | 1.168 | 0.232 | 0.224 | 0.328 | 0.384 |  | 3.56 | 0.2 | 2.008 | 4.512 | 2.48 | 0.264 | 0.672 | 1.4 | 5.8
Total estimated time (hours) | 49.008 | 36.288 | 3.744 | 14.592 | 7.008 | 1.392 | 1.344 | 1.968 | 2.304 |  | 21.36 | 1.2 | 12.048 | 27.072 | 14.88 | 1.584 | 4.032 | 8.4 | 34.8
Campsites
Count from NRMA | 9853 | 4837 | 235 | 1129 | 454 | 718 | 473 | 0 | 0 |  | 2894 | 109 | 930 | 3798 | 1887 | 0 | 830 | 1256 | 2962
Rate per hour | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Estimated time | 98.53 | 48.37 | 2.35 | 11.29 | 4.54 | 7.18 | 4.73 | 0 | 0 |  | 28.94 | 1.09 | 9.3 | 37.98 | 18.87 | 0 | 8.3 | 12.56 | 29.62
20% contingency | 19.706 | 9.674 | 0.47 | 2.258 | 0.908 | 1.436 | 0.946 | 0 | 0 |  | 5.788 | 0.218 | 1.86 | 7.596 | 3.774 | 0 | 1.66 | 2.512 | 5.924
Total estimated time (hours) | 118.236 | 58.044 | 2.82 | 13.548 | 5.448 | 8.616 | 5.676 | 0 | 0 |  | 34.728 | 1.308 | 11.16 | 45.576 | 22.644 | 0 | 9.96 | 15.072 | 35.544
Other features (point only)
Total Count from NRMA | 1901 | 1790 | 374 | 1446 | 980 | 306 | 362 | 1233 | 132 |  | 2521 | 103 | 1474 | 1968 | 1189 | 527 | 400 | 651 | 1144
Rate per hour | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
Estimated time | 38.02 | 35.8 | 7.48 | 28.92 | 19.6 | 6.12 | 7.24 | 24.66 | 2.64 |  | 50.42 | 2.06 | 29.48 | 39.36 | 23.78 | 10.54 | 8 | 13.02 | 22.88
30% Contingency | 11.406 | 10.74 | 2.244 | 8.676 | 5.88 | 1.836 | 2.172 | 7.398 | 0.792 |  | 15.126 | 0.618 | 8.844 | 11.808 | 7.134 | 3.162 | 2.4 | 3.906 | 6.864
Total estimated time (hours) | 49.426 | 46.54 | 9.724 | 37.596 | 25.48 | 7.956 | 9.412 | 32.058 | 3.432 |  | 65.546 | 2.678 | 38.324 | 51.168 | 30.914 | 13.702 | 10.4 | 16.926 | 29.744
OCA Data Collection Additional Weeks | 10 | 6 | 3 | 5 | 1 | 4 | 2 | 2 | 3 |  | 2 | 2 | 19 | 24 | 11 | 3 | 3 | 7 | 3
Total Time for all features (Hours) | 249.67 | 164.752 | 17.428 | 73.476 | 42.256 | 21.024 | 18.412 | 37.446 | 12.996 |  | 147.674 | 5.546 | 74.792 | 152.016 | 86.258 | 15.706 | 27.632 | 44.178 | 109.148
Data collection + 10% Conservation Project Time | 274.637 | 181.2272 | 19.1708 | 80.8236 | 46.4816 | 23.1264 | 20.2532 | 41.1906 | 14.2956 |  | 162.4414 | 6.1006 | 82.2712 | 167.2176 | 94.8838 | 17.2766 | 30.3952 | 48.5958 | 120.0628
Project Count | 17 | 9 | 5 | 8 | 1 | 7 | 3 | 2 | 4 |  | 3 | 2 | 32 | 41 | 19 | 4 | 4 | 12 | 5
Weeks of data collection | 6.2418 | 4.1188 | 0.4357 | 1.8369 | 1.0564 | 0.5256 | 0.4603 | 0.93615 | 0.3249 |  | 3.6919 | 0.13865 | 1.8698 | 3.8004 | 2.1565 | 0.39265 | 0.6908 | 1.1044 | 2.7287
Weeks in travel estimator | 2.4312 | 1.75 | 1.3438 | 2.075 | 1.0688 | 1.4812 | 1.4688 | 1.1375 | 1.275 |  | 2.4937 | 1.1375 | 3.2 | 3.8188 | 2.4375 | 1.4062 | 1.275 | 1.9563 | 1.8687
Total Weeks Per District | 18.673 | 11.8688 | 4.7794 | 8.9119 | 3.1252 | 6.0069 | 3.9291 | 4.0736 | 4.5999 |  | 8.1856 | 3.2761 | 24.0698 | 31.6191 | 15.5939 | 4.7989 | 4.9658 | 10.0607 | 7.5975 | 176.1353
Estimated hours | 746.92 | 474.752 | 191.178 | 356.476 | 125.006 | 240.274 | 157.162 | 162.946 | 183.996 |  | 327.424 | 131.046 | 962.792 | 1264.766 | 623.758 | 191.956 | 198.632 | 402.428 | 303.898 | 7045.41
Adjusted estimated hours | 747 | 475 | 192 | 357 | 126 | 241 | 158 | 163 | 184 |  | 328 | 132 | 963 | 1265 | 624 | 192 | 199 | 403 | 304 | 7053
Adjusted estimated weeks | 19 | 12 | 5 | 9 | 4 | 7 | 4 | 5 | 5 |  | 9 | 4 | 25 | 32 | 16 | 5 | 5 | 11 | 8 | 185
Adjusted estimated months | 4.75 | 3 | 1.25 | 2.25 | 1 | 1.75 | 1 | 1.25 | 1.25 | 0 | 2.25 | 1 | 6.25 | 8 | 4 | 1.25 | 1.25 | 2.75 | 2 | 46.25
The difference from the travel estimator is allowed as a logistical contingency. The location of projects will impact the pace and quantity of data collection
Note on A3: Andrew Huddleston: NRMA=NRM Assessment, unpaved and paved road mileage on all USACE OWNED roadways
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to hone in the rate of road collection...how many road miles can be collected in 1 hour?
Note on A24: Andrew Huddleston: Traffic Counters Dump Stations Trail Heads Amph Fish Features Restrooms Boat Ramp Swim Beach Picnic Site Group Picnic Site Group Camp Shelter
Note on A30: Andrew Huddleston: Add 4 days to each project for OCA collection, rating, etc.
Note on A35: USACE: Project count from FY20 NRMA.
Note on A38: USACE: this comes directly from travel estimator