	PDO
	Project Outcome Indicators
	Use of Project Outcome Information

	Students enrolled in all streams of pre-tertiary education in Jordan will have increased levels of skills necessary for participation in the knowledge economy.

	Increase in scores on national assessments aligned with knowledge economy skills (Target: an average increase of 3 score points for Maths, Science and Arabic)
Increase in enrollment rates. (Target: maintain current high NER (97.6%) for Basic Cycle, and increase NER to 63% for the Secondary Cycle.

	These indicators will be used to monitor overall progress under ERfKE II and to inform general project implementation and refinement. Performance on these indicators will be reviewed through supervision missions and through discussions with GOJ and other stakeholders.

	Intermediate Outcomes
	Intermediate Outcome Indicators
	Use of Intermediate Outcome Monitoring

	Establishment of a National School-based Development System: 

National education reform is being delivered through local school development processes focused on improving student learning outcomes and supported by community, field directorates, and the central administration.

	Development and implementation of enabling policies, guidelines, and procedures.
Number/percentage of schools that are implementing improvement plans. (Target: 100%)
A single School Evaluation Instrument, focused on ERfKE outcomes, agreed and being used for school self-evaluation and for public and professional accountability.

Stakeholder views on extent to which decision-making authority and associated resources are being allocated and utilized to enable implementation of school improvement plans. 

Stakeholder views on extent to which mechanisms for professional and public accountability, linked to the school improvement cycle, have been established and are functioning.
School principals’ and teachers’ views on quality of field directorate and central administration support toward achievement of school development plans.

External stakeholder assessment of graduate knowledge economy skills.


	These indicators will be used to monitor progress on the National School-based Development System component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. Data will be disaggregated by gender and location with a strong focus on equity. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GoJ and other stakeholders. 


	Policy, Planning, and Organizational Development:

Organizational realignment has taken place in order to support a school-based approach to improving the delivery of education services. 

Organizational effectiveness at all levels of the system has been improved by the adoption of a results-based approach to policy, planning, accountability, incentives, and M&E.

	Review and realignment of mandate and responsibilities of MoE organizational structures relevant to the school improvement process. 

Number of non school staff participating in ongoing professional development programs to support the delivery of the school improvement program. (Target: 1,100)
Review and development of mechanisms for professional and public accountability. (Target: 80 % of schools)
Stakeholder perceptions of relevance of M&E reports for informing policy and planning.

Stakeholder views on extent to which SIS/EMIS is producing data for continuous monitoring of the 32 key performance indicators.
	These indicators will be used to monitor progress on the Policy, Planning, & Organizational Development component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GOJ and other stakeholders. 


	Teaching & Learning Resource Development:

Student learning outcomes relevant to the acquisition of knowledge economy skills have been improved through realigned curriculum, authentic assessment, appropriate teaching and learning resources, and interactive classroom practices.


	Teacher policies revised to support application of national teacher standards.
Percentage of newly appointed teachers completing post-recruitment initial training. (Target: 80%)
Number/percentage of subjects by grade reviewed and fine-tuned to ensure alignment with knowledge economy skills. (Target: All subjects in all grades)
The present Tawjihi examination reviewed in the context of the ERfKE II curriculum and knowledge economy skills.
The content and design of NAfKE is reviewed for overall technical soundness and alignment with the ERfKE curriculum, and arrangements put in place for any necessary revisions.
Extent of e-Learning/ICT utilization in the teaching and learning process (by subject, grade) as revealed by nationally representative classroom observation studies. (Target: increase from 67% to 73%)
	These indicators will be used to monitor progress on the Teaching & Learning Resource Development component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GoJ and other stakeholders. 


	Special Focus Program Development:

Early Childhood Education:

Access to quality early childhood education has been increased through further development of facilities, learning resources, and parental and community involvement.
	Percentage of eligible children enrolled in KG. (Target: Increase from 51.8% to 60%)
Percentage of KG teachers/supervisors successfully completing prescribed training program for early childhood education. (Target: 100%)
Number of parents of KG students enrolled in volunteer programs.(Target: increase from 2,000 to 3,500)
	These indicators will be used to monitor progress on the Early Childhood Education component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GOJ and other stakeholders. 

	Vocational Education:

Programs and resources have been rationalized and improved to establish a quality secondary-level program that is consistent with, and aligns to, demand-driven service provision in the technical and vocational sector and further education and training.
	Percentage of programs aligned with vocational/technical guidelines/standards for curriculum, equipment, and facilities.
Completion rates for vocational/technical programs. (Target: 100%)
Increase in employer satisfaction with the skills and abilities of labor market entrants holding vocational education certificates awarded by the MoE.
	These indicators will be used to monitor progress on the Vocational Education component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GoJ and other stakeholders. 

	Special Education:

Access to quality education programs and services relevant to students with special needs has been increased.
	Revision and approval of policies to support special education programs and services.
Number of teachers trained and qualified according to national standards for special education. (Target: 300 for teachers of gifted students; 300 teachers of disabled students)
Number of students enrolled in special education programs. (Target: 6,500 gifted students; 15,500 disabled students)
	These indicators will be used to monitor progress on the Special Education component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GoJ and other stakeholders. 

	Physical Learning Environment:

School buildings are provided and maintained in a cost-effective manner so that more students have access to learning in safe and well-managed physical environments.
	Number of students with access to learning in a safe and well-managed physical environment. (Target: Increase from 859,867 to 920,000)
Decrease in number of underutilized classrooms in all field directorates (Target: decrease by 20 schools)
Decrease in number of overcrowded classrooms in all field directorates. (Target: decrease by 20 schools)

Number of additional classrooms/lab spaces for science and ICT. (Target: 1,000 classrooms; 120 ICT Labs; 120 Science Labs)
Policies for continuous building maintenance in place.
	These indicators will be used to monitor progress on the Physical Learning Environment component of ERfKE II and to inform project implementation and refinement specifically in relation to this component. The indicators will be reviewed through supervision missions and also used as focal points for discussion with GOJ and other stakeholders. 



