INL DRAFT Change Map Template

Draft Goals, Indicators, Targets for:

Strengthening Capacity of the Costa Rican Judicial Authority's Institutional Anti-Corruption Mechanisms

INL22CA0032-WHPCOSRIC-CORRMAPPNG-03282022

The Draft Change Map for this project is below.  This was developed in collaboration with country counterparts, and implementers are expected to follow the goals, objectives,  activities and indicators outlined therein.  Applicants should use this as a guide in developing their Change Map for this NOFO, and should feel free to add and/or propose additional data sources, activities, indicators and targets that they perceive may help better achieve the stated objectives.

It is understood that all activities will be designed in close collaboration with the Oficina de Planificación del Poder Judicial de Costa Rica and its Modelo de Gestión de Riesgos, Cumplimiento y Anticorrupción, and any other key agencies or offices identified by Poder Judicial.

(Fill out Blank Change Map on the next page, and see Appendix A for Instructions and Definitions; see Appendix B for the Design Work Aid)

| Strategic Policy Alignment (To be completed by INL) | FBS Objective(s): Strategic Goal # 2 ICS Objective(s): Mission Goal 1.1 Other: INLCosta Rica Strategic Plan Sub Objective 3.1.Incidents of Corruption and Conflicts of Interest Within Poder Judicial are Decreased |  |
| --- | --- | --- |
| VISION (Optional) | Indicator (Optional): Target (Optional): | Data Source (Optional): |
| Goal 1: Poder Judicial Strengthens Internal Mechanisms to Reduce the Risk of Corruption | Indicator: Internal Risk Reduction Mechanisms Created Target: # of Internal Mechanisms Created | Data Source: |
| Objective 1.1: Poder Judicial Implements Strategies Designed to Close Entry Points for Corruption | Indicator 1.1: Poder Judicial Implements Anti-Corruption Strategies Target 1.1: # Strategies Implemented |  |
| YEAR ONE Sub-Objective 1.11: Poder Judicial Implements a Comprehensive Institutional Systems Mapping Process to Identify Entry Points for Corruption | Indicator 1.11: Poder Judicial Completes Institutional (Systems) Mapping Process Target 1.11: Yes/No |  |
| Activity 1.111: Identify the Actors Responsible to Administer, Plan and Implement the Mapping Process - The "Poder Judicial (PJ) Mapping Team" Technical Assistance to the Planning Office (Dirección de Planificación Institucional) and other PJ actors, and the implementer, to identify Poder Judicial individuals who will be responsible for the planning, administration and oversight of the institutional mapping process. | Indicator 1.111 Poder Judicial Mapping Team Created Target 1.111 Yes/No |  |
| Activity 1.112: Create an Implementation Plan for the Mapping The Poder Judicial Mapping Team, together with the Planning Office (Dirección de Planificación Institucional) and its Mapping Tool/Guide, develops an action plan for institutional systems mapping based on Poder Judicial's priorities as expressed in the oficios and documents noted above. Note: The action plan should include, but is not limited to, these components: - Identify key agencies, offices, systems within Poder Judicial to be mapped (taking into account the information required by the Auditoria & Control Interno; this should include offices identified within the Judiciary, Ministerio Publico, Public Defense, OIJ) - Identify key counterparts, together with POCs that should be responsible for facilitating contacts, information gathering, and data collection; - Identify data and information necessary for collection; - Create a "mapping tool" that Poder Judicial can use for this process, and for any additional institutional systems mapping in the future - Establish roles and responsibilities for each Mapping Team Member as needed - The components of the plan should take into account priority areas & systems already identified by Poder Judicial in the above-referenced documents, including: - Internal communication mechanisms; - Risk Detection & Management Mechanism(s), Policies & Procedures - Data Management systems - Case Management systems - Human Resources policies, procedures, practices - AgencyTraining Departments policies, practices, procedures | Indicator 1.112: Institutional Mapping Plan Created for Poder Judicial Target 1.112: Yes/No |  |
| Activity 1.113: Conduct Institutional Mapping of Poder Judicial Systems and Components Technical assistance to the Mapping Team to implement the Mapping Plan | Indicator 1.113: Institutional Systems Mapping Conducted According to Mapping Plan Target 1.113: Yes/No |  |
| Activity 1.114: Mapping Report - Provide technical assistance to write a complete report identifying gaps, risks, breaches, procedures, inefficiencies, and provide specific recommendations | Indicator 1.114: Mapping Report Completed Target 1.114: Yes/No |  |
| Activity 1.115: Validation of Mapping Recommendations Provide technical assistance to validate specific recommendations with agencies/offices of Poder Judicial that participated in the mapping | Indicator 1.115: Mapping Report Recommendations Validated by Poder Judicial counterparts Target 1.115: Yes/No |  |
| YEARS TWO AND THREE Sub Objective 1.21: Poder Judicial Implements Recommendations Identified in the Mapping Assessment Report | Indicator 1.21: Mapping Assessment Recommendations Implemented Target 1.21: # Recommendations Implemented (disagg by type/agency/office) |  |
| Activity 1.201: Implementation Planning Meetings Technical assistance for a series of planning meetings with POCs responsible for each of the offices/agencies identified in the Recommendations in order to develop specific action plan for implementing recommendations. | Indicator 1.201: Planning Meetings held with Counterparts to Develop Plans for Implementing Recommendations Target 1.201: # of Meetings held (disagg by counterpart) |  |
| Activity 1.202: Implementation Plan Developed Action plan for implementing recommendations developed and validated | Indicator1.202 Implementation Plan developed for Mapping Recommendations Target 1.202: Yes/No |  |
| Sub-Objective 1.31 Poder Judicial Implements Comprehensive, Integrated Risk Management Measures (Note, the Activities listed in 1.31 are what have been identified by Poder Judicial as important, but these may be changed, eliminated or expanded upon depending upon the Results of the Mapping) | Indicator 1.31: Comprehensive, Integrated Risk Management Measures Implemented Target: 1.31: Yes/No (disagg by type/agency) |  |
| Activity 1.301: Technical Assistance to Develop Universal Glossary of Terms for Identifying Risks Technical assistance to develop a consistent glossary of terms to identify risk factors for corruption and conflicts of interest to ensure consistent data analysis and collection. This glossary shall be aligned with a glossary of terms created for identifying risks (as applicable) developed in Activity 1.403, under Sub Objective 1.41, below | Indicator 1.301: Universal Glossary of Terms Developed Target 1.301: Yes/No |  |
| Activity 1.302: Risk Catalogue Developed Technical assistance to develop a catalogue of protocols and processes associated with risks of conflicts of interest and corruption for the Poder Judicial Auditor's Office | Indicator 1.302: Risk Catalogue developed Target 1.302: Yes/No |  |
| Activity 1.303: Risk Management System Developed for the Auditor's Office Technical assistance to develop a risk management system for the Auditor's office. This system should also include a mechanism for ongoing monitoring and follow up so that new forms of corruption can be detected in a timely manner. | Indicator 1.303: Risk management system developed Target 1.303: Yes/No |  |
| Activity 1.304: Risk Management Training Program Developed Develop a training program for Poder Judicial personnel on risk management strategies and protocols developed under this subobjective | Indicator 1.304: Training program developed Target 1.304: Yes/No |  |
| Activity 1.305: Conduct Risk Management Trainings Conduct trainings on risk management strategies and protocols developed under this Subobjective | Indicator 1.3.4.1: Trainings conducted Target 1.3.4.1: # Trainings disagg by subject/PJ agency/office |  |
| Subobjective 1.41: Poder Judicial Implements Improved Data Collection, Management, Sharing, and Dissemination Systems Designed to Curb Corruption | Indicator 1.4 Poder Judicial Implements Data Management Systems Target 1.4 Yes/No |  |
| Activity 1.401: Judicial Observatory Improves Data Management Provide technical assistance to the Judicial Observatory to strengthen its systems for collecting, analyzing, using and reporting data, with the goal of reducing opportunities for corruption and increasing Poder Judiciary’s public credibility | Indicator 1.401: Poder Judicial Observatory creates systems and protocols for collecting, analyzing, using & reporting data Target 1.401: # systems/protocols developed (disagg by type/agency/office) |  |
| Activity 1.402: Judicial Observatory - Development of Methodologies for Managing data types Technical assistance to the Judicial Observatory to implement methods & policies to manage various forms of data, including extrapolating & analyzing data from the Compliance Office | Indicator 1.402: Poder Judicial Implements data management methods & policies Target 1.402: # methods /protocols implemented (disagg by type/agency/office) |  |
| Activity 1.403: Universal Glossary of Terms for Case Data Reporting Technical assistance to create a universal glossary of terms and protocols for PoderJudicial, OIJ, Ministerio Publico for the entry, reporting, and sharing of data related to investigations, prosecutions and adjudications. This glossary shall be aligned with a glossary of terms created for identifying risks (as applicable) developed in Activity 1.301 | Indicator 1.403: Poder Judicial creates universal glossary of terms for data entry, sharing, reporting & applicable protocols Target 1.403: Yes/No (disagg glossary/protocols) |  |
| Activity 1.404: Implementation of Information Management Policies & Protocols Technological assistance to implement data reporting & information sharing developed in Activity 1.402 with the Obervatory, OIJ and Ministerio Publico offices in charge of cases of corruption and organized crime. | Indicator 1.404: Poder Judicial implements data management policies & protocols Target 1.404: Yes/No (disagg glossary/protocols) |  |
| Activity 1.405: Evaluate Judicial Effectiveness Tools Provide technical assistance to evaluate the possible use of data collection tools, such as "Jurimetria", to map the effectiveness of judicial sentences | Indicator 1.405: Poder Judicial evaluates data collection tools related to effectiveness of judicial sentences Target 1.405: Yes/No (disagg by tool type) |  |
| Activity 1.406: Establish a Data Dissemination & Public Communications Strategy Provide technical assistance to the Observatory to create a public communication strategy that will provide inclusive and informative access to data | Indicator 1.406: The Poder Judicial Observatory implements a data dissemination & public communications strategy Target 1.406: Yes/No |  |
| Activity 1.407: Develop a Training Program Technical assistance to develop a training program for Poder Judicial personnel on data management strategies and protocols developed under this subobjective | Indicator 1.407: Poder Judicial develops a training program on data management strategies and protocols Target 1.407: Yes/No |  |
| Activity 1.408: Conduct Trainings Conduct trainings on strategies and protocols developed under this Subobjective for Poder Judicial personnel | Indicator 1.408: Poder Judicial conducts staff trainings on data management strategies & protocols Target 1.408: # Trainings (disagg by type) |  |
| Sub Objective 1.51 Poder Judicial Has Increased Capacity to Manage Corruption Risk Through Effective Internal Communication Strategies | Indicator 1.51: Poder Judicial Implements Internal Communications Strategies Target 1.51: Yes/No |  |
| Activity 1.501: Action Plan to Establish Internal Communication Policies Technical assistance to develop an action plan establishing policies and strategies that facilitate and improve internal communication between Poder Judicial offices and regional offices | Indicator 1.501: Action plan establishing policies and strategies to facilitate and improve internal communication developed Target 1.501: Yes/No |  |
| Activity 1.502: Establish Strategies to Engage and Educate Staff on Poder Judicial Anti-Corruption Efforts Technical assistance to develop strategies for increasing staff understanding of institutional expectations regarding anti-corruption protocols, & staff interest and capacity in contributing to the fight against corruption | Indicator 1.502: Strategies implemented for increasing staff understanding of, interest in, and capacity to contribute to institutional anti-corruption efforts Target 1.502: Yes/No |  |
| Activity 1.503: Strengthen Institutional Internal Communication Methods Technical assistance to strengthen institutional internal communication methods, such as trainings, audio-visual material, documentaries, etc. | Indicator 1.503: Internal anti-corruption communication methods developed Target 1.503: Yes/No |  |
| Activity 1.504: Develop Communication Training Program Develop a training program for Poder Judicial personnel on internal communication strategies and protocols developed under this subobjective | Indicator 1.504: Training program on internal communication strategies developed Target 1.504: Yes/No |  |
| Activity 1.505: Conduct Trainings Conduct trainings on communication strategies and protocols developed under this Subobjective | Indicator 1.505: Internal communications trainings conducted Target 1.505: #t Trainings conducted (disagg by agency/office) |  |
| Sub Objective 1.61: Poder Judicial Develops Human Resources Systems and Practices to Reduce the Risk of Corruption | Indicator 1.61: Poder Judicial Implements Human Resources Systems to Reduce Corruption Risk Target 1.61: Yes/No |  |
| Activity 1.601: Technical Assistance to Strengthen Human Resources Systems and Policies - Technical assistance to: Create standardized position descriptions that guarantee accurate position profiles that correspond to agency/unit/office required skills, capacities & knowledge; - Create and strengthen staff recruitment, selection, retention, promotion & disciplinary protocols & procedures that promote and enforce institutional ethics & values - Create protocols and practices that promote stability and reduce position turnover - Create and strengthen rigorous protocols for selection, promotion, training & disciplinary protocols & practices for judges that ensure high judicial competence & promote & enforce institutional ethics & values. | Indicator 1.601: Poder Judicial Human Resources Office implements protocols and strategies to reduce the risk of corruption Target 1.601: # protocols/strategies implemented (disagg by type/office) |  |
| Activity 1.602: Create Protocol that Facilitates Integrated Processes between Poder Judicial Training Units & Human Resources Provide technical assistance to create & strengthen systems integration and information sharing between Human Resources & Poder Judicial training units, including tracking personnel training & training needs that correspond to staff positions | Indicator 1.602: Poder Judicial Implements Protocols & systems that facilitate integrated processes between the Human Resources Office and the Training Offices of Poder Judicial, OIJ and Ministerio Publico Target 1.602: #protocols/systems developed (dissag by agency/office/type) |  |
| Activity 1.603: Personnel Management Training Design a training program for managers in Poder Judicial Offices that promote staff retention and adherence to institutional ethics and values | Indicator 1.603: Training program created to promote staff retention/adherence to ethics and values Target 1.603: Yes/No |  |
| Activity 1.604: Risk Detection Training Design a training program for managers based on risk detection and reduction and management of risks | Indicator 1.604: Training program created on risk detection, reduction, and manaagement Target 1.604: Yes/No |  |
| Activity 1.605: Conduct Management Trainings Conduct trainings for managers on personnel management & risk detection in programs designed in activities 1.603 & 1.604 | Indicator 1.605 Poder Judicial conducts trainings Target 1.605: #Trainings conducted (disagg by type/agency/office) |  |
| Activity 1.606: Develop Judicial, Administrative Processes that Improve Justice Services Provide technical assistance to develop and/or improve existing management processes and standards that will reduce opportunities for corruption | Indicator 1.606: Poder Judicial develops administrative processes that reduce opportunities for corruption Target 1.606: Yes/No |  |
| Sub Objective 1.71 Poder Judicial Has the Capacity to Assess Institutional Corruption Risks | Indicator 1.71: Poder Judicial implements risk assessment mechanisms Target 1.71: Yes/No |  |
| Activity 1.701: Conduct Final Assessment Conduct a final program assessment and report (with Findings & Recommendations) of the Implementation of Mapping Report Recommendations | Indicator 1.701: Final Assessment Conducted Target 1.701: Yes/No |  |
| Activity 1.702: Validation Conduct a validation of the Assessment Findings & Recommendations | Indicator 1.702: Assessment Findings Validated Target 1.702: Yes/No |  |
| Activity 1.703: Adopt and Implement Findings and Recommendations Provide Technical Assistance to adopt and implement Findings/Recommendations | Indicator 1.703: Poder Judicial Adopts Findings/Recommendations from Assessment Measure 1.703: Yes/No |  |

Date:

Project Name:

Project Award Number:

INL Point of Contact (Name/Email):

Implementing Organization Name:

Implementer Organization Point of Contact (Name/Email):

Start Date: (N/A if unknown)

End Date: (N/A if unknown)

| Strategic Policy Alignment (To be completed by INL) | FBS Objective(s): ICS Objective(s): Other: (For example, note alignment to Integrated Bureau Strategic Guidance here.) |  |
| --- | --- | --- |
| VISION (Optional) | Indicator (Optional): Target (Optional): | Data Source (Optional): |
| Goal 1: | Indicator: Target: | Data Source: |
| Objective 1.1: |  |  |
| Sub-Objective 1.11: |  |  |
| Activity 1.111: |  |  |
| Activity 1.112: |  |  |
| Objective 1.2: |  |  |
| Activity 1.201: |  |  |
| Activity 1.202: |  |  |
| Continue as above, adding as many goals, objectives, sub-objectives, and activities as relevant. |  |  |

APPENDIX A:  INSTRUCTIONS and DEFINITIONS

- Instructions for INL Staff

The primary purpose of the Change Map is to link the work plan (goals, objectives, sub-objectives, and activities) to the monitoring plan (indicators).  We emphasize “Change” in the title because the work plan should describe what changes the project intends to achieve (i.e., the goals and objectives) and how the project will achieve them (i.e., the activities).  There should be more detailed information about the work plan in the project proposal; and more details about the indicators in the Performance Indicator Reference Sheet (PIRS).  This document serves as a “mapping” between the two, by showing which indicators will be used to monitor progress toward which goals, objectives, and activities.  It also functions as a high-level summary or “cover sheet” of your project that describes the specific results the project intends to achieve and how it will achieve them.

As a quick guide “map” of the project, the document also links the project to strategic objectives (required); includes an optional vision statement (with or without indicators); and includes additional indicator information (namely targets and data sources) that are optional in this template but required in the PIRS.

Roles and Responsibilities:  INL staff are responsible for filling in the strategic alignment section.  Implementing partners generally create the initial draft of the main Change Map table.  INL staff provide feedback and eventually approve a final version.  INL staff and dedicated M&E specialists at Post or in Washington can work with implementers in a consultative capacity to ensure that goals, objectives, and indicators meet bureau standards.

Requirements:  The change map must include the strategic alignment section; goals, objectives, sub-objectives (if applicable), and activities—all in the first column; and indicators in the second column.  The vision section and associated indicators, targets, and data sources are optional.  Note that it is possible to include a vision statement without requiring indicators, targets, or data sources.  If you choose not to include a vision statement, remove the section.

A note on indicators:  More is not necessarily better.  Data are costly to collect and analyze; and too many indicators can result in focusing on minutiae at the expense of answering the most important monitoring questions, namely:  1) are major project activities going to plan; and 2) is the project achieving the desired results.

INL/KM therefore recommends that INL staff and implementing partners develop indicators and collect data only for the main project outputs and outcomes.  In other words, many activities, objectives, and sub-objectives may not have associated indicators, and that is fine.  The only requirements are as follows:

- A project must have at least one valid outcome indicator, associated with a project goal.

- Progress against at least one outcome indicator should be expected at least once every six months;

- All training activities should track the number trained, disaggregated by gender;

- Include all standard indicators for required reporting, if applicable.  (Consult your Design, Monitoring & Evaluation specialist to determine whether any standard indicators for required reporting apply to your project.)

Note that while indicators for objectives and sub-objectives are not required, they may be necessary to meet requirement (2), that progress against at least one outcome indicator should be expected at least once every six months.  In other words, it must be possible to monitor progress toward expected results while the project is in progress.

Options:  Targets for each indicator are optional in the Change Map.  The third column (data sources) is also optional.  Remove references to targets and/or the Data Source column if you do not wish to include them.  For targets and data sources, you may include one, both, or neither.  Note that information about targets and data sources will be collected in the Performance indicator Reference Sheet (PIRS).  Including them in the Change Map is up to you:  they may be handy for reference if you do not wish to consult the PIRS regularly; or you may find that they make the Change Map too cluttered.

- Definitions and Examples

Strategic Alignment:  INL will complete this section.  All INL projects should align to strategic goals and objectives laid out in strategy documents such as the Functional Bureau Strategy (FBS), an Integrated Country Strategy (ICS), or an Issue-Based Strategy.  The Strategic Alignment section indicates which strategic objectives the project is intended to advance.

Vision:  A vision statement describes the results that a project contributes to but is not expected to achieve during its period of performance.  The vision may be broad (“reduce the flow of illicit narcotics through Freedonia”) or more specific (“increase arrests related to methamphetamine production sites in Freedonia”).  The vision statement is optional because achieving a vision-level change is often the result of multiple interventions and lines of effort, over an extended period of time, in which INL is not the only actor.

Goal:  A goal describes the highest level of change that a project seeks to achieve as the result of its activities.  The change should be external to INL.  Projects may have multiple goals.  Note that goals should be achievable during the life of the project, not aspirational or larger than the changes that the project seeks to effect.  They must meet the “change” and “clarity” design standards.  See Appendix B below (Design Work Aid) for more explanation and examples.

Objective / Sub-Objective:  Similar to goals, objectives and sub-objectives describe changes that the project seeks to effect—changes external to INL that are achievable during the life of the project.  Objectives are mid-level changes that, if achieved, should result in the achievement of a project goal.  Sub-objectives are the smallest level of change that, if achieved, should result in the achievement of an objective.  Note that many objectives may not require sub-objectives.

Activity:  An activity refers to the things that INL or the implementing partner are doing to cause the changes described in the goal, objective, and sub-objective statements, such as training, development of guidance documents, and equipment donations.

Indicator:  An indicator is a statistic (or metric) used to measure progress toward accomplishing the activities or changes described in the goal, objective, and sub-objective statements.  Indicators should answer the question:  to what extent was the associated activity, goal, or objective achieved?  Note that indicators associated with activities are generally output indicators (e.g., # trained, $ value of equipment donated), while indicators associated with goals, objectives, and sub-objectives are outcome indicators (e.g., changes in knowledge or behavior as a result of training).  See Appendix B (Indicator Work Aid) of the Performance Indicator Reference Sheet for more explanation and examples.

Target:  A target is the value of the indicator if the activity is fully accomplished, or the changed described in the goals, objectives, and sub-objectives are fully achieved.

Indicator and Target Examples:

- Activity/Output: The activity is to train forensics specialists; the indicator is the number of forensics specialists trained, and the target is 50.

- Sub-objective/Outcome:  The sub-objective is that those who complete the forensics training are able to collect fingerprints in several specific scenarios; the indicator is the percentage of those who have completed the training that successfully collect fingerprints in at least 4 out of 5 simulated scenarios immediately following the training; and the target is 90%.

Data Source:  The data source describes how or from where the data for the associated indicator will be generated.  It is not necessary to go into great detail in the Change Map because details are included in the Performance Indicator Reference Sheet (PIRS)

- Examples of where: National Bureau of Prisons, Training attendance sheets created by sub-implementer

- Examples of how: Sample survey of police, to be administered by Implementer; satellite imagery of agriculture fields, to be analyzed by Sub-implementer

APPENDIX B:  Design Work Aid

Introduction:

For FY22, INL is focused on two of our design standards:  change and clarity.  To meet the change standard, goals and objectives should be expressed as the expected results, or desired end states, of the project, not as the activities that INL or its implementing partners undertake to achieve those results.  To meet the clarity standard goals and objectives should be expressed such that anyone reading them will have a similar understanding of what the project seeks to accomplish.

This document provides quick tips on how to meet each of these standards, examples of what meeting them and not meeting them looks like, and why meeting them matters.

How to Meet the Change Standard:

The key to the change standard is the actor:  are we describing what will be true for our partners at the end of the project or are we describing what INL or our implementers will do during the project?  The first is a change, the second an activity.  For example, INL might train police.  Running the training is our activity.  The desired change is what the police learn or, in combination with other activities, the change in their behavior.  A training project’s goal should be about what the police learn or do.

To be sure you’ve met the change standard, always write goals to include the subject (the person performing the action) and check that the subject is not INL or our implementing partner.

Examples of Common Mistakes and How to Fix Them:

| Original | Explanation of the Problem | Improvement |
| --- | --- | --- |
| Develop Freedonian corrections officials’ capabilities to confiscate contraband. | It is unclear who is doing the developing. Presumably, it is INL or our implementing partner. If our goal is just that we execute our activities, then all we will monitor is whether we executed our activities. This will not tell us if the officials learned anything or not. If we do not know if our training is effective, we run the risk of investing in a lot of ineffective training and not realizing we need to adjust how we deliver the training. | Freedonian corrections officials have the knowledge and skills to confiscate contraband. |
| INL delivers a series of trainings and targeted equipment that assists border enforcement and justice sector officials to interdict illegal drugs. | This makes the actor explicit but because the actor is us, this is an activity. | Border enforcement and justice sector officials know how to interdict illegal drugs and have the equipment to do so. |

Why Change-based Goals Matter:

Congress entrusts INL with taxpayer funds for the purpose of making a difference on the ground, not funding the existence of foreign assistance implementing organizations.  Setting change-based goals and objectives is important for two reasons.  First, what a project monitors depends on its goal.  If we want to know if our projects are making a difference on the ground, we need to set goals focused on that external difference.  Second, it sends an important message about what we are collectively responsible for accomplishing.  It is not enough to execute an activity.  We are also responsible for understanding if that activity resulted in the desired change so we can adjust future activities if needed.

How to Meet the Clarity Standard:

There are three components to clarity:  (1) be consistent in describing the most significant change the project seeks to achieve, i.e., the goal; (2) the goal and objectives should be precise about what will be different as a result of the project; and (3) project documents should define ambiguous terms.

Each is elaborated below.

- Consistent goal:  When projects are described in narrative form without a change map, they often articulate a range of aspirations, some of which the project actually intends to bring about and others to which the project might contribute in a small way but that are much bigger than what one project can reasonably expect to accomplish.  It is not always clear, however, which the project seeks to catalyze and which are aspirational.  A good way to avoid this problem is to use a change map and to be clear that a goal is a change the project expects to achieve, not a visionary purpose for pursuing a project.  (Note:  different organizations use terms in different ways.  Some use the word goal to mean visionary purpose.  That is fine so long as the project document clearly identifies the most significant change the project expects to achieve.)

- Precise changes:  It is very common for a project to know a desired end state but one that is not attainable as the result of a particular intervention.  In these cases, INL often articulates goals that indicate progress toward that desired end state but do not specify how much progress to expect from the particular project.  Goals like this use words like build, enhance, increase, or strengthen.  This can mask a superficial understanding of what is causing the problem INL seeks to address and how much of that can be addressed given context and resources.  When working on challenging issues with limited resources, it is imperative that we understand all the main causes of the issue in question, which of those are the most important to address and in what sequence, and who has the power to address them.  Being disciplined about writing goals and objectives that state who will be different in what way as a result of our activities drives deeper analysis that allows us to design more effective interventions.  One tip for avoiding the fuzzy thinking pitfall is to design with a partner.  It’s fine to start with the general statement that we want to, for example, improve border security.  Then talk with a partner about follow up questions like:  what are the main problems with Freedonia’s border security now?  What’s causing those problems?  What would it take to address those causes?  How much of that can we afford to take on?  In most cases this will lead to identifying a particular way in which the project will improve border security.  Occasionally, however, INL is truly seeking to chip away at a problem it does not make sense to break into its component parts.  In these cases the goal/objective can call for “improving” but should include a target to make clear by how much.

- Define terms:  There can be a surprising number of words that mean different things to different people.  Two common categories that benefit from definitions are target groups and words that describe doing something to a certain quality marker.  On the former, for example, a project might state that it seeks to target police leadership.  If someone said INL leadership, would you understand that to mean the Front Office, Office Directors, or some other grouping?  Similarly, police leadership can mean different things to different people and knowing which we’re talking about is important for how we scope and approach activities.  On the latter, words like “appropriate” or “effective” can mean different things.  If our implementing partner has a very different understanding of what an “effective” prosecution looks like, they are likely to execute activities that emphasize points we don’t prioritize.  As with articulating precise changes, a good approach for making sure we define ambiguous terms is to talk about our project plans with others.  It’s fine to have short goal statements (e.g., the police investigate effectively) and provide the necessary definitions as footnotes.

Examples of Common Mistakes and How to Fix Them:

| Original | Explanation of the Problem | Improvement |
| --- | --- | --- |
| This project will work with the government of Freedonia to: (1) develop the rule of law; and (2) combat transnational crime. Building a stable, transparent, and effective legal system will prevent extra judicial activities. The project aims to fight corruption. | Which statement is the goal? As written, it is not clear what would constitute success. Each of the possible goals is also at the aspirational level. The specific way in which Freedonia would be different at the end of this project is unknown. | Vision: Freedonia has a stable, transparent, and effective legal system. Goal: Freedonian judges impartially apply the law to cases. Impartial means deciding issues based on the facts, not other factors such as preferred executive branch outcomes. |
| Freedonia improves its prisoner classification. | How much and what kind of improvement needs to happen for this project to consider itself a success? It would be easy to imagine a scenario in which INL and our implementing partner had different answers to this question but did not realize that in time to address it. | Freedonian prison authorities assign inmates to appropriate levels of security and custody. Appropriate means the least restrictive regime with the most services possible given the risk the inmate poses to staff, other inmates, and the public. |

Why Clear Goals Matter:

We are more likely to make steady, if incremental, progress if we are clear about what each project seeks to change.  INL has funded versions of the same project for years in part because each iteration only articulated a vague goal, such as promote the rule of law.  In such cases, it is easy to identify a success story or two to justify continuation of the project.  It’s hard to know if the project is actually resulting in meaningful change.