Issuance Date:  July 23,  2008

Closing Date:   September 18, 2008

Closing Time:  12:00 p.m., Haiti local time

To all Applicants:

Reference:  Integrated HIV/AIDS Community Care Program.

Subject:  Request for Applications (RFA) Number 521-08-0006

The United States Agency for International Development (USAID) is seeking an application from your organization for a Cooperative Agreement for funding a program for 6 years in Haiti.  The authority for the RFA is found in the Foreign Assistance Act of 1961, as amended.

The Recipient will be responsible for ensuring achievement set forth in the Program Description.

Please let us have your application which will set forth in detail the conceptual approach, methodology and techniques for the accomplishment of the stated objectives in the Program Description.  To this end, it must include the general strategy and specific approach to implement the program, including a schedule of achievement indicators on a timeline that covers a six (6) year program period.  Please refer to Section A, Instructions to the Applicant, for detailed information regarding the content of your Application.

Subject to the availability of funds, USAID intends to provide up to $125 million in total USAID funding to be allocated over the approximately six- (6) year period.

For the purposes of this program, this RFA is being issued and consists of this cover letter and the following:

1.  Section A:		Instructions to the Applicant;

2.  Section B:		Selection Criteria

3.  Section C:		Program Description:

4.  Section D		Representations/Certifications Required for Cooperative Agreement to a U.S. NGO

5.  Section E		Award Format

Attachment 1:		AAPD 05-11 Marking under Assistance Instruments

Attachment 2:		Application for Federal Assistance (SF 424)

For the purposes of this RFA, the term "Grant" is synonymous with "Cooperative Agreement"; "Grantee" is synonymous with "Recipient"; and "Grant Officer" is synonymous with "Agreement Officer".

Your application should be received via e-mail attachment (oaahaiti@usaid.gov) by the closing date and time indicated at the top of this RFA Cover Letter.  The subject line of the email should read RFA 521-08-0006.  A hard copy of your application and five copies should be postmarked by the RFA closing date and submitted to the place designated as follows:

(By courier service)

Office of Acquisition and Assistance

USAID/Haïti

AMERICAIN EMBASSY

BOULEVARD 15 OCTOBRE

TABARRE  41

TABARRE , Haití

Applicants are requested to submit technical and cost portions of their applications in clearly marked separate document folders. Award(s) will be made to the responsible applicant(s) whose application(s) offers the greatest value.

Issuance of this RFA does not constitute an award commitment on the part of the Government, nor does it commit the Government to pay for costs incurred in the preparation and submission of your Application. Your Application is submitted at your own risk.  Should circumstances prevent award of a cooperative agreement, all preparation and submission costs are at the applicant's expense.

Any questions concerning this RFA should be submitted in writing to Linda McElroy or Stéphane C.Bright, via e-mail at oaahaiti@usaid.gov (include RFA #). You should retain for your records one copy of all enclosures which accompany your application.

Sincerely,

Linda McElroy

Agreement Officer

Enclosures:  a/s

# SECTION A – INSTRUCTIONS TO APPLICANT

GRANT APPLICATION FORMAT AND SUBMISSION GUIDELINES

All applications received by the deadline will be reviewed for responsiveness to the specifications outlined in these guidelines and the application format.  Preparation of Technical Application addresses the technical evaluation procedures for the applications.  Applications which are submitted late or are incomplete run the risk of not being considered in the review process.   Late applications will be considered for award if the Agreement Officer determines it is in the U.S Government's interest.

Applications shall be submitted electronically and in hard copy.  Electronic copies shall be attached to an e-mail sent to the electronic address indicated in the Cover Letter of this RFA and hard copies shall be sent to the office address indicated in the Cover Letter of this RFA.  Applications shall be submitted in two separate parts: (a) technical and (b) cost or business application. Hard copies of both the technical and cost portions of applications shall be submitted in an original and five copes.  All submissions shall indicate the time specified for receipt, the RFA number, and the name and address of the applicant.

The applications should be prepared according to the structural format set forth below.  Applications must be submitted no later than the date and time indicated in the Cover Letter of this RFA, to the location indicated on the Cover Letter accompanying this RFA.

Applicants should retain for their records one copy of the application and all enclosures which accompany their application.  Erasures or other changes must be initialed by the person signing the application.  To facilitate the competitive review of the applications, USAID will consider only applications conforming to the format prescribed below.

PREPARATION OF TECHNICAL APPLICATION

The technical application will be the most important item of consideration in determining the successful application(s) and issuing award(s).   The technical application shall be specific, complete, and presented in a concise manner. The application should demonstrate the applicant's capabilities and expertise with respect to achieving the goals of this program.  The application should take into account the Technical Evaluation Criteria.   It is recommended that the applicant conduct an in-depth review of all information contained in this RFA prior to preparing an application.  The application will be evaluated on the basis of its comprehensiveness, creativity, and cost-effectiveness.

Technical applications must include:

1.  Program Management Approach

The application must include a clear and concise description of the overall objective, anticipated measurable results to be achieved and how the proposed program will achieve these results, as well as the proposed management and programmatic approach. The applicant is encouraged to propose innovative implementation designs to reach the desired results, in keeping with existing U.S. Government (USG) strategic approaches and programmatic guidance, and an aggressive but realistic schedule of performance milestones as steps towards reaching those results. The applicant may include as an attachment a detailed implementation plan with proposed inputs and activities and associated time lines for the life of the program in addition to the required first year work plan.  The applicant may consider ensuring that the program approach answers the following specific questions:

- What is the overall strategic vision for the entire program and the proposed outcome and/or impact level results to be achieved at the end of the program?

- How is the program integrated with the USG Title II food assistance program?

- How is the program integrated with USG HIV/AIDS programs administered by the Centers for Disease Control (CDC) and other USG agencies in Haiti?

- How will the program achieve maximum integration of HIV/AIDS activities with maternal and child health, family planning and tuberculosis interventions?

- Who are the other organizations (organizations under other USG programs, other donor or private sector partners) that the proposed program will coordinate with and how will coordination occur?

- How will the program be coordinated within and help support the Government of Haiti’s health sector decentralization efforts through their Departmental Strategy?

- If applicable, how will matching funds and/or program-funded income from the Recipient and/or NGO sub-recipients be used?

- What is the approach for building capacity of those sub-recipients that may need additional technical assistance to programmatically and/or administratively manage and implement community- and/or clinic-based programs?

- What are the geographic intervention areas and the rationale for selecting them?

- What are the specific HIV, tuberculosis, maternal and child health and family planning activities proposed for implementation that will achieve the vision and results?

2. Administrative Management Approach

Guidance from the Office of the Global AIDS Coordinator (OGAC), the US Government entity that oversees the implementation of the President’s Emergency Plan for AIDS Reduction (PEPFAR), stipulates that no one recipient can receive more than 8% of a country’s annual HIV/AIDS budget, unless that recipient is the host government, is primarily procuring and distributing ARVs and other essential HIV/AIDS commodities, is operating under a contract, or has a grant or cooperative agreement to be a “grants management partner to identify and mentor sub-recipients” under an “umbrella award.”  In the case of such umbrella awards, no more than 25% of the HIV/AIDS funds received by the management partner can be used for administration of the grants program and technical assistance to be considered eligible for the waiver of the 8% limit.  For fiscal year (FY) 2008, 8% of the PEPFAR budget for Haiti was approximately $7,600,000.  Based on planning figures and subject to final U.S. Congression approval, 8% of the FY 2009 PEPFAR budget for Haiti will be approximately $7,400,000.  While HIV/AIDS budget amounts for fiscal years 2010 through 2013 are unkown, guidance from OGAC indicates that the levels will be similar to FY 2009 levels.  Applicants are responsible for proposing an administrative management approach that takes into account this guidance from OGAC for the HIV/AIDS funded portion of the proposed program.

The application must include a detailed description of the management approach for implementing the proposed program, which includes specifying the composition and organizational structure of the entire implementation team (including home office support); describing each team member's role, with a more detailed description of proposed key personnel (description, proposed person and a summary of their technical, programmatic and administrative management expertise).  Applicants should describe the rationale for selecting the initial list of proposed partner organization and/or sub-recipients and the method for identifying new sub-recipients during the life of the program. The applicant may consider ensuring that the administrative management approach answers the following specific questions:

- What is the management approach for strategically selecting partner and/or sub-recipient NGOs and coordinating their activities to avoid duplication of effort and maximize results?

- What is the management approach for ensuring partner organization and/or sub-recipient responsibility?

- How will the proposed partner organizations and/or sub-recipients have a management “voice” in the overall strategic management and coordination of NGO activities?

- What is the management approach for administration of sub-recipient agreements to ensure a time efficient sub-awarding process with minimal burden to the NGO sub-recipients?

- What is the management approach for financial administration to ensure timely funds flow to the sub-recipients and financial controls and accountability?

- What is the organizational structure of the management approach?

- What are the positions and who are proposed to fill those positions on the management team for the program?

- How does the management approach minimize administrative costs of the program and maximize the level of funding going to support actual program delivery via the sub-recipients?

- What is the time frame for start up and how quickly can administrative mechanisms be put in place to start funding NGO activities at the community level?

- What is the strategy for development, review and approval of sub-recipient work plans and budgets?

- What is the approach, design and methodology for impact assessment?

- What is the plan for having sub-recipients document and monitor their performance?

- What is the plan and strategy for collecting data to measure achievement of results and impact?

- What is the plan for implementation of data collection, analyses, and reporting, including timeliness?

- What is the proposed plan for reporting programmatic progress and administrative and financial updates to USAID, such as the submission of progress reports, annual reports, financial reports, accruals, etc., or the proposed timing of regular meetings to verbally discuss progress and address issues?

3.  Monitoring, Evaluation and Reporting Approach

The application must include as an attachment a draft monitoring and evaluation (M&E) plan.  At a minimum, the M&E plan should  include the relevant indicators to measure performance annually and at the end of the program, baselines (or estimated baselines) for each indicator, annual and end of program targets for each indicator, a narrative describing in detail a) the entire data collection process (including plans for conducting data quality assessments, timing of data collection, method of data collection, data storage, data reporting, etc), b) proposed plans for periodic evaluations during the agreement period (such as additional baseline studies, management assessments, mid-term evaluations, final evaluations, and/or “one time” studies to fill in information gaps) and c) strategy and procedures to ensure that periodic reporting to USAID is timely, accurate and efficient.  Indicators relevant to this RFA have been identified and included below in the results section. Additional indicators and targets proposed to be used to monitor progress should also be included, such as program management indicators or cross cutting indicators related to community-based activities.   As applicable, indicators should be disaggregated by gender, age cohorts, and geographical location (i.e. Haiti Departments), and if applicable, by sub-recipient.

4.  Organizational Capability

The applicant must offer evidence of ability to efficiently manage and administer the proposed program.  Applicants must offer evidence of their technical, programmatic and administrative resources and expertise in administration of an NGO grants program, in addressing problems and issues related to community-based integrated programming in the health sector, particularly related to care and support for individuals living with HIV/AIDS and their affected families. This includes evidence of a successful record of implementing similar programs; organizational strengths as represented by breadth and depth of prior experiences managing large-scale integrated community-based umbrella NGO health programs, with a strong emphasis on HIV and AIDS (i.e. technical and programmatic coordination, procurement and grants administration; financial administration), and monitoring and evaluation expertise.

TECHNICAL APPLICATION FORMAT

The technical application shall be concise, no more than 30 pages - excluding the cover page and required attachments - and give a clear and measurable description of what the applicant organization proposes to achieve as well as where, why, and how.

The technical application shall follow the following format:

- Cover Page

- Executive Summary (up to 3 pages)

- Program Approach (up to 12 pages)

A.  Overall program vision, objective and expected results

B.  Geographic intervention zones and coordnation with other USG programs

C.  Narrative describing briefly the proposed activities in:

- HIV and AIDS

- Tuberculosis

- Maternal and Child Health

- Family Planning

- Other proposed community-based activities or cross-cutting activities

IV.	Management Approach (up to 12 pages)

A. Management Approach

- Program management strategy

- Administrative management approach

- Monitoring and evaluation management approach

B. Management team and key personnel

C. Proposed partner organizations and/or sub-recipients

V.	Organizational capability (up to 3 pages)

A.  Brief description of organizational history/expertise

B.  Relevant experience in Haiti

C.  Relevant experience with proposed approaches

Required Technical Application Attachments:

Attachment A – Draft Year 1 Work Plan

Attachment B – Geographic Intervention Areas

Attachment C – Organizational Chart, Position Descriptions for Key Positions, C.V.s for Proposed Key Personnel

Attachment D – Draft Monitoring and Evaluation Plan

## PREPARATION OF COST APPLICATION

The Cost or Business Application is to be submitted under separate cover from the Technical Application.  Certain documents are required to be submitted by an applicant in order for a Grant Officer to make a determination of responsibility.  However, it is USAID policy not to burden applicants with undue reporting requirements if that information is readily available through other sources.

The following sections describe the documentation that applicants for an Assistance award must submit to USAID prior to award.   Applicants are encouraged to be as concise as possible, but still provide the following:

A.  A copy of the program description that was detailed in the applicant’s program description, on a CD using Word Format .

B.  A budget with an accompanying budget narrative which provides in detail the total costs for implementation of the program your organization is proposing.  The budget must be submitted using Standard Form 424 and 424A which is included as Attachment 2 to this RFA and can also be downloaded from the USAID web site, http://www.usaid.gov/procurement_bus_opp/procurement/forms/sf424/.  The budget shall include:

- The breakdown of all costs associated with the program according to costs of, if applicable, headquarters, regional and country offices;

- The breakdown of all costs according to each partner organization involved in the program;

- The costs associated with external, expatriate technical assistance and those associated with local in-country technical assistance;

- The breakdown of the financial and in-kind contributions of all organizations involved in implementing this Cooperative Agreement;

C.  A current Negotiated Indirect Cost Rate Agreement;

D.  Required certifications and representations (as attached):

E.  Cost share - Applicant to propose.

F.  Applicants who do not currently have a Negotiated Indirect Cost Rate Agreement (NICRA) from their cognizant agency shall also submit the following information:

1.  copies of the applicant's financial reports for the previous 3-year period, which have been audited by a certified public accountant or other auditor satisfactory to USAID;

2.  projected budget, cash flow and organizational chart;

3.   A copy of the organization's accounting manual.

G.   Any additional evidence of responsibility deemed necessary for the Grant Officer to make a determination of responsibility.  The information submitted should substantiate that the Applicant:

1.   Has adequate financial resources or the ability to obtain such resources as required during the performance of the award.

2.   Has the ability to comply with the award conditions, taking into account all existing and currently prospective commitments of the applicant, nongovernmental and governmental.

3.   Has a satisfactory record of performance.  Past relevant unsatisfactory performance is ordinarily sufficient to justify a finding of non-responsibility, unless there is clear evidence of subsequent satisfactory performance.

4.   Has a satisfactory record of integrity and business ethics; and

5.   Is otherwise qualified and eligible to receive a grant under applicable laws and regulations (e.g., EEO).

H.   Applicants that have never received a grant, cooperative agreement or contract from the U.S. Government are required to submit a copy of their accounting manual.  If a copy has already been submitted to the U.S. Government, the applicant should advise which Federal Office has a copy.

## ADDITIONAL INSTRUCTIONS TO THE APPLICANT

In addition to the aforementioned guidelines, the applicant is requested to take note of the following:

I.  Unnecessarily Elaborate Applications - Unnecessarily elaborate brochures or other presentations beyond those sufficient to present a complete and effective application in response to this RFA are not desired and may be construed as an indication of the applicant's lack of cost consciousness.  Elaborate art work, expensive paper and bindings, and expensive visual and other presentation aids are neither necessary nor wanted.

J.  Acknowledgement of Amendments to the RFA - Applicants shall acknowledge receipt of any amendment to this RFA by signing and returning the amendment.  The Government must receive the acknowledgement by the time specified for receipt of applications.

K.  Receipt of Applications - Applications must be received at the place designated and by the date and time specified in the cover letter of this RFA.

L.  Submission of Applications:

1.  Applications and modifications thereof shall be submitted electronically as attachments to an e-mail sent  to the electronic address specified in the Cover Letter of this RFA as well as in sealed envelopes or packages (1) addressed to the office specified in the Cover Letter of this RFA, and (2) showing the time specified for receipt, the RFA number, and the name and address of the applicant.

2.  Faxed applications will not be considered; however, applications may be modified by written  notice, either electronically or in hard copy,  if that notice is received by the time specified for receipt of applications.

M.  Preparation of Applications:

1.  Applicants are expected to review, understand, and comply with all aspects of this RFA.  Failure to do so will be at the applicant's risk.

2.  Each applicant shall furnish the information required by this RFA.  The applicant shall sign the application and print or type its name on the Cover Page of the technical and cost applications.  Erasures or other changes must be initialed by the person signing the application.  Applications signed by an agent shall be accompanied by evidence of that agent's authority, unless that evidence has been previously furnished to the issuing office.

3.  Applicants who include data that they do not want disclosed to the public for any purpose or used by the U.S. Government except for evaluation purposes, should:

(a) Mark the title page with the following legend:

"This application includes data that shall not be disclosed outside the U.S. Government and shall not be duplicated, used, or disclosed - in whole or in part - for any purpose other than to evaluate this application.  If, however, a grant is awarded to this applicant as a result of - or in connection with - the submission of this data, the U.S. Government shall have the right to duplicate, use, or disclose the data to the extent provided in the resulting grant.  This restriction does not limit the U.S. Government's right to use information contained in this data if it is obtained from another source without restriction. The data subject to this restriction are contained in sheets ; and

(b) Mark each sheet of data it wishes to restrict with the following legend:

"Use or disclosure of data contained on this sheet is subject to the restriction on the title page of this application."

N.  Explanation to Prospective Applicants - Any prospective applicant desiring an explanation or interpretation of this RFA must request it in writing within three weeks of receipt of the application to allow a reply to reach all prospective applicants before the submission of their applications.  Oral explanations or instructions given before award of a Grant will not be binding.  Any information given to a prospective applicant concerning this RFA will be furnished promptly to all other prospective applicants as an amendment of this RFA, if that information is necessary in submitting applications or if the lack of it would be prejudicial to any other prospective applicants.

O.   Grant Award:

1.  The Government may award one or more Grants resulting from this RFA to the responsible applicant(s) whose application(s) conforming to this RFA offer(s) the greatest value (see also Section B of this RFA). The Government may (a) reject any or all applications, (b) accept other than the lowest cost application, (c) accept more than one application  (d) accept alternate applications, and (e) waive informalities and minor irregularities in applications received.

2.  The Government may award one or more Grant(s) on the basis of initial applications received, without discussions.  Therefore, each initial application should contain the applicant's best terms from a cost and technical standpoint.

3.  Neither financial data submitted with an application nor representations concerning facilities or financing, will form a part of the resulting Grant(s).

P.  Authority to Obligate the Government - The Grant Officer is the only individual who may legally commit the Government to the expenditure of public funds.  No costs chargeable to the proposed Grant may be incurred before receipt of either a fully executed Grant or a specific, written authorization from the Grant Officer.

Q.  The Recipient is reminded that U.S. Executive Orders and U.S. law prohibit transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the legal responsibility of the recipient to ensure compliance with these Executive Orders and laws.  This provision must be included in all subcontracts/subawards issued under this agreement.

R.  Foreign Government Delegations to International Conferences - Funds in this agreement, and in any amendments may not be used to finance the travel, per diem, hotel expenses, meals, conference fees or other conference costs for any member of a foreign government's delegation to an international conference sponsored by a public international organization, except as provided in ADS Mandatory Reference "Guidance on Funding Foreign Government Delegations to International Conferences [http://www.info.usaid.gov/pubs/ads/300/refindx3.htm] or as approved by the [CO/AO/CTO].

PRE-AWARD APPROVAL OF THE BRANDING STRATEGY AND MARKING PLAN

I.  Pre-award Review and Approval of the Branding Strategy:  22 C.F.R. 226.91(f) requires that, after the evaluation of the applications, the USAID Agreement Officer will request the Apparently Successful Applicant to submit a Branding Strategy that describes how the program, project, or activity is named and positioned; how it is promoted and communicated to beneficiaries and cooperating country citizens; and identifies all donors and explains how they will be acknowledged. USAID will not competitively evaluate the proposed Branding Strategy. The Agreement Officer will review the proposed Branding Strategy for adequacy to ensure that it:

- contains the required information on naming and positioning the USAID-funded program, project, or activity,

- promotes and communicates to cooperating country beneficiaries and citizens that the USAID-funded program, project, or activity is “from the American People”,

- is consistent with the stated objectives of the award; the Apparently Successful Applicant’s cost data submissions; the Apparently Successful Applicant’s project, activity, or program performance plan; and the regulatory requirements set out in 22 C.F.R. 226.91.

During the review of the Apparently Successful Applicant(s)’s Branding Strategy, the Agreement Officer will coordinate as necessary with the Activity Manager, the Technical Evaluation Panel and the communications specialist.  Following completion of the review, the Agreement Officer will negotiate any required changes to the Branding Strategy with the Apparently Successful Applicant(s), approve the Branding Strategy, and include the Branding Strategy as part of the assistance award.

When requesting a Branding Strategy, the Agreement Officer will establish a reasonable time frame for submittal, review, and negotiation. If the Apparently Successful Applicant(s) fail(s) to submit or negotiate an acceptable Branding Strategy within the time specified by the Agreement Officer, that/those Applicant(s) become(s) ineligible for award.

II. Pre-award Review and Approval of the Marking Plan:  22 C.F.R. 226.91(f) also requires that, after evaluation of the applications, the USAID Agreement Officer will request the Apparently Successful Applicant(s) to submit a Marking Plan that will detail the public communications, commodities, and program materials intended to visibly bear the USAID Identity. USAID must not evaluate the Marking Plan competitively. The Agreement Officer will review the proposed Marking Plan for adequacy, coordinating as necessary with the Activity Manager, Technical Evaluation Panel and the communications specialist. Following completion of the review, the Agreement Office will negotiate any required changes to the Marking Plan with the Apparently Successful Applicant, approve the Marking Plan, and include the Marking Plan as part of the assistance award. The Agreement Officer will ensure that any estimated costs associated with branding and marking are included in the Total Estimated Amount of the grant or cooperative agreement or other assistance award.

When requesting a Marking Plan, the Agreement Officer will establish a reasonable time frame for submittal, review, and negotiation. If the Apparently Successful Applicant(s) fail(s) to submit or negotiate an acceptable Marking Plan within the time specified by the Agreement Officer, that/those Applicant(s) become(s) ineligible for award.

The Marking Plan may include requests for approval of a Presumptive Exception or Exceptions identified at 22 C.F.R. 226 (h). Presumptive Exceptions exempt a general marking requirement for a particular USAID-funded public communication, commodity, or program material or other deliverable, or a category of USAID-funded public communications, commodities, and program materials, or other deliverables that would otherwise be required to visibly bear the USAID Identity.

The Agreement Officer will negotiate and accept or reject the Apparently Successful Applicant(s)’s request for a Presumptive Exception as part of the overall negotiation of the Marking Plan and include any Presumptive Exceptions granted in the final negotiated Marking Plan. A list of the Presumptive Exceptions is found in the Provision “Marking Plan – Assistance,” contained in the enclosed sample award format.

During the review and approval of Presumptive Exceptions, the Agreement Officer should coordinate and consult with the Activity Manager, communication specialist, and other personnel as needed (including, if necessary, the Principal Officer). The Agreement Officer may request advice and recommendations from these personnel if necessary.

The Agreement Officer’s approval of the marking plan will include a list of the approved Presumptive Exceptions and the public communications, commodities, and program materials, or other deliverables exempted.

# SECTION B - SELECTION CRITERIA

The criteria presented below have been tailored to the requirements of this particular RFA.  Applicants should note that these criteria serve to: (a) identify the significant matters which applicants should address in their applications and (b) set the standard against which all applications will be evaluated.

The technical applications will be evaluated in accordance with the Technical Evaluation Criteria set forth below.  Thereafter, the cost application of the apparently successful applicant(s) will be analyzed for realism, reasonableness, allowability, and allocability of proposed costs.

Negotiations will be conducted with the Apparently Successful Applicant(s).   Award(s) will be made to the responsible applicant(s) whose application(s) offers the greatest value, cost and other factors considered.

The technical applications will be screened by a technical review panel at USAID/Haiti.  Following the review of the applications, a letter will be sent to all applicants detailing the outcome of the review.  USAID reserves the right to determine the final funding level of the resultant award(s).

The criteria set forth below will be used by the technical review panel to evaluate applications submitted in response to this RFA.  The three main selection criteria below are listed in relative order of importance with the maximum number of points to be assigned to each in the selection process.  The sub-criteria listed under each main criterion are of equal importance under that criterion and will be assigned equal weight under that criterion in the selection process.  The Instructions to the Applicant (SECTION A) provide a detailed list of questions which serve as notification of USAID expectations in terms of application content.  Applicants are encouraged to propose performance outputs and results beyond those indicated if they are appropriate measures of the implementation approach proposed.

Technical Evaluation Criteria are as follows:

I. Management approach 								(45 points)

A. Management approach

- Program management strategy

- Administrative management strategy and structure

- Monitoring, evaluation and reporting management strategy and draft monitoring and evaluation plan

- Draft first year work plan

B. Management team and key personnel

II. Technical approach 									(35 points)

A.  Overall program vision, objective and expected results

B.  Geographic intervention areas and complentarity with other USG funded programs

C.  Specific program objectives and activities to achieve the expected results in:

- HIV/AIDS

- Tuberculosis

- Maternal and child health

- Family planning

- Other	proposed community-based activities or cross-cutting activities

D. Proposed partner organizations and/or sub-recipients

III. Organizational capability								(20 points)

A.  Organizational history and expertise

B.  Relevant experience in Haiti

C.  Relevant experience with proposed approaches

SECTION C - PROGRAM DESCRIPTION

C.1. BACKGROUND

A.  Problem Statement

Haiti occupies one third of the Hispaniola Island it shares with the Dominican Republic. The population density is 300 inhabitants per square kilometer. In certain areas of Port-au-Prince this density reaches 2,500.  Haiti’s GNP per capita in 2003 was $332, down from $632 in 1980, a decline of 90% over 23 years, whereas the GNP per capita for the Latin America and Caribbean (LAC) region for 2005 was $3,580. Two-thirds of Haiti’s population lives in abject poverty.  Life expectancy at birth is 50.0 years, compared to 70.5 years for the LAC region, and the infant mortality rate is 57 per 1,000 (31.2 per 1,000 for the LAC region).  Fifty percent of the population is below 24 years of age, and over 50% of them have never attended or did not complete primary school. UNESCO 2005 data indicate that only 66.2 % of youth 15 to 24 years of age are literate, compared to 95.5% for the LAC region.

Nearly 40% of Haitians have no access to basic primary health care.  Haiti’s health indicators reveal that the country’s health system is weak.  Haiti has the highest under-five mortality in the Western Hemisphere with approximately 12.5% of children dying before reaching the age of 5 years, followed by Bolivia with 9.0%.  Haiti has the highest maternal mortality rate in the region at approximately 630 deaths/ 100,000 live births—close to the maternal mortality rates in some regions of Africa.  Close to 200,000 people are HIV positive, with approximately 3,000 dying annually.  While the recent 2005 Demographic Health Survey (DHS 2005) suggests that trends in mortality and morbidity are going down, they are still worrisome.

The dismal state of key health indicators is a result of lack of access to quality health care services and to potable water and chronic food insecurity.  Access to quality health care across the country is challenged due to poor health infrastructure and disruption of services (notably within the capital of Port-au-Prince, which has struggled with insecurity and violence in several neighborhoods over the last several years). Insecurity and violence have also contributed to a deterioration of services: lack of equipment, inadequately trained staff, and poor management of health facilities, especially by the public sector.  Although there is engagement of communities and civil society, notably NGO support, to participate in addressing health issues, both the supply and demand sides of health services need to be strengthened in both the public and non-public health care delivery sectors.

The NGO sector has been the stable provider of social services both in urban and rural settings, despite the cycles of civil and political unrest in Haiti. Several international PVOs and local Haitian NGOs are present in Haiti and have a breadth of experience in delivering clinic and community-based social sector and support services.   While the Government of Haiti is building its own capacity to strategically lead and manage on a national scale the delivery of health care services, the NGO sector remains a strong partner to the Government of Haiti and provides a solid foundation for the entire social sector.

The objective of the “Integrated HIV/AIDS CommunityCare Program”, through this award, is to strengthen, expand and coordinate NGO community-based HIVAIDS services, integrating child health, reproductive health (maternal, family planning), tuberculosis detection and treatment,  and other social sector assistance, where applicable, to improve the quality of livelihoods of vulnerable Haitian families.

B. Government of Haiti and Other Donor Programs

Government of Haiti

The Government of Haiti aims to strengthen governance and health service delivery capacity in order to respond to the needs of its citizens.  In November 2005, the MSPP published its “Plan Stratégique National pour la Reform du Secteur de la Santé”, which lay out the Ministry’s new approach toward integration of health services and its strategy to deliver a basic minimum package of health services closer to the people.  The Prime Minister further outlined major government priorities in a speech before the Haitian Parliament in June 2006.  As a major long-term goal, he emphasized the modernization of the State and the deployment of State functions to all regions of Haiti, i.e. deconcentration and decentralization of State functions and services.  Between June 2006 and September 2007, a process was completed to have each Department develop a department-level health plan with a budget.  These Department Health Plans were integrated into one national costed health plan for Haiti, which was officially approved by the Government of Haiti.  Since October 2007, each Department has been empowered to implement and manage their respective health plans, while the central level focuses on strengthening its executive function oversight of each of the Departments.  To support the Government of Haiti’s efforts to decentralize health care services and governance, department-level donor coordination meetings have been initiated.

Other Donor Programs

The United States is the single largest donor in the health sector with Canada, the Global Fund for HIV/AIDS, Tuberculosis and Malaria, and the Inter-American Development Bank (IDB) making substantial investments in Haiti’s health sector.  The Global Fund is the second largest HIV/AIDS donor ($20 million per year) and a major donor in Haiti for tuberculosis and malaria, providing about $6 million dollars for each annually. The current Global Fund HIV/AIDS grants will continue through 2014; the tuberculosis and malaria grants will continue through 2011. Canada and Brazil provide significant resources to the MSPP for immunization. Canada recently launched a five-year $100 million program in four departments which supports public sector services, university training in public health, and pilot projects in commune-level service delivery with a specific focus on maternal care within hospital settings.  The IDB funds a four-year $38 million health project with the Government of Haiti which will end in 2008 to work at the commune level to construct, renovate and equip commune level health care facilities and train clinic staff.   The WHO/PAHO, UNFPA, UNICEF, French Cooperation, and the EU are providing technical assistance and commodities in selected departments and equipment support to the public sector.

C.  USAID/Haiti’s Health Strategy

The U.S. Government (USG) focuses its foreign assistance on five priority objectives to meet the goal of “Helping to build and sustain democratic, well-governed states that will respond to the needs of their people and conduct themselves responsibly in the international system”. Refer to http://www.state.gov/f for extensive information and details on the new Foreign Assistance Framework, objectives, program elements and sub-elements.

- Peace and Security: recognizing these as platforms for further political, economic and social progress;

- Governing Justly and Democratically: recognizing that effective, accountable, democratic governance is a vital foundation for sustainable progress;

- Investing in People: recognizing that human capacity must be strengthened in order to promote and sustain success;

- Economic Growth: recognizing that economic progress and poverty reduction are critical underpinnings of sustainable development; and

- Humanitarian Assistance: recognizing the United States’ commitment to alleviate human suffering and respond to destabilizing humanitarian disasters.

The USAID country strategy for Haiti builds on over 40 years of USG humanitarian relief, health, economic growth, and democracy development experience. The strategy focuses development assistance through the analytic lens of these five objectives described above within the U.S. Government defined country category of “Rebuilding Countries” (i.e. states in or emerging from and rebuilding after internal or external conflict).  The USAID country strategy has three types of geographic targeted areas:  1) conflict-vulnerable areas ( Petit Goave, Port-au-Prince, St. Marc, Gonaives, Cap Haitian and Les Cayes), especially the cities and rural sending areas and the hotspots they surround; 2) targeted watersheds (Limbe, Montrouis), where interventions will stabilize environmental conditions, mitigate the impact of natural disasters, and create assets and employment; and 3) other locations that are self-targeting by activity (e.g., regional and district courts, departmental health offices, mango processing centers) or provide particular opportunities for impact, such as food insecure and vulnerable populations and families  living with HIV/AIDS.

This RFA focuses on implementing U.S. Government development assistance primarily but not exclusively, when applicable, under Objective 3  Investing in People, 3.1 Health Program Area, specifically on these five program elements:

- Program element 3.1.1:  HIV/AIDS

- Program element 3.1.2:  Tuberculosis

- Program element 3.1.6:  Maternal and Child Health

- Program element 3.1.7 : Family Planning

- Program element 3.1.8: Water and Sanitation

The overall aim of USG development assistance within these program elements is to reduce the transmission and mitigate the impact of HIV/AIDS, increase the detection and treatment of tuberculosis, increase the use of basic reproductive and child health services, increase access to potable water, and to overall improve livelihoods at the community and household level.   Annually, the U.S. Government provides approximately US$120 million to Haiti to support the achievement of results under the Investing in People Objective, of which approximately US$100 million is for HIV/AIDS, $9 million for maternal and child health, $9 million for family planning, and $1 million for tuberculosis.  USAID is currently developing a new multi-year water and sanitation program that will be approximately $8 million over three years.

Haiti is a U.S. Government focus country for HIV/AIDS under the U.S. Presidential HIV/AIDS Initiative, commonly referred to as PEPFAR.  The Centers for Disease Control and Prevention (CDC) and USAID are the two primary U.S. Government agencies responsible for implementing HIV/AIDS development assistance in Haiti, through a comprehensive program covering HIV prevention, care and support for those infected and affected by the disease and antiretroviral (ARV) treatment for eligible patients.  The HIV/AIDS activities and implementing partners are further described in detail below.

USAID manages all of the maternal and child health, family planning, tuberculosis and water and sanitation development assistance to Haiti.  A majority of this funding is programmed into one integrated health services program called Sante et Developpement pour la Stabilite en Haiti – SDSH Pwoje Djanm.  Management Sciences for Health (MSH) is the primary implementing partner responsible for achieving results through this bilateral health program.  SDSH Pwoje Djanm has three main focuses – (1) deliver a basic package of health care services to approximately 50% of the population in Haiti through 80 NGO clinics and 72 public sector clinics; (2) provide support to the Government of Haiti to increase their capacity to carry out the executive function of management of a national health care system as well as reform and strengthen three health management systems - financial management, information management, and health commodities management and logistics; and (3) mobilize private sector partners for the health sector in Haiti.

While other donors are providing major inputs to the national health system, little investment is being made to ensure adequate drug and consumable supplies.  USAID is the major supplier of contraceptives and supports the logistics and distribution of these contraceptives to USAID target areas.  UNFPA also provides commodities, which includes condoms and other contraceptives; UNICEF provides vaccines for maternal and child immunization.   In addition, the U.S. Government, through USAID, purchases HIV/AIDS commodities which include anti-retroviral drugs, HIV rapid tests and other diagnostic reagents, laboratory supplies and drugs for opportunistic infections and provides technical assistance to strengthen commodities logistics and distribution for these HIV commodities in each of the 10 Departments.  HIV/AIDS commodities are also supplied by the Global Fund for AIDS, Tuberculosis and Malaria.

The following are specific U.S. Government-supported programs with which applicants should strongly consider close coordination, integration and/or inclusion of activities within the overall proposed technical approach.

HIV/AIDS

Haiti has one of the oldest HIV epidemics in the western hemisphere.  Although the prevalence rate has decreased over the past 10 years, it is still a generalized epidemic with a national HIV prevalence rate of over 2% and approximately 3,000 deaths from the disease annually.  The U.S. Government HIV/AIDS program covers AIDS prevention, care and treatment implemented through the Ministry of Health’s healthcare system and through approximately 45 international and local NGO partners. Medical prevention is addressed through the MOH and Haitian Red Cross blood safety program and through a safe injection program at major public hospitals.  HIV prevention activities are carried out through information, education and communication programs, encouraging behavior change and addressing AIDS-related stigma and discrimination. A significant portion of the US Government support is used for HIV detection (counseling and testing), providing health care and anti-retroviral treatment for HIV positive individuals and preventing the transmission of the virus from HIV positive mothers to their infants (PMTCT.)  Support to hospitals, clinics and health centers that provide these services includes renovation, equipment, drugs and laboratory supplies, provider training and supervision and mentoring of clinicians to ensure they are providing quality of care.  Care for persons infected and affected by HIV and AIDS is also channeled through community programs where support is provided to orphans and vulnerable children (OVC) and people living with HIV/AIDS (PLWHA) and their families in a family-centered approach. The community–based interventions also help to ensure that PLWHA adhere to their health care and treatment programs as well as create demand for HIV testing and PMTCT services.

The USG PEPFAR program supports clinical services through eight implementing partners, each with its own network of HIV/AIDS service delivery sites:

- the Government of Haiti’s Ministry of Health, funded through CDC

- GHESKIO, funded through CDC

- Partners in Health (PIH), funded through CDC

- MSH, funded through USAID (SDSH Pwoje Djanm briefly described above),

- The AIDS Relief Consortium, funded through the USG’s Human Resources and Services Administrtion (HRSA)

- FOSREF, funded through CDC

- POZ, funded through CDC and

- Family Health International, funded through CDC.

The last three of these partners provide only HIV counseling and testing and health care for PLWHA that does not involve ARV therapy.   (See the list of individual sites included as a document in the list of additional background documents for Applicants in preparation for applications, Section C.3. ADDITIONAL BACKGROUND INFORMATION).

To ensure that all PLWHA enrolled in clinical services also have support and care at the home and community level and that all OVC have adequate support, PEPFAR funds are currently channeled through five NGO partners, each responsible for OVC and PLWHA care at the community and family level as well as overall coordination of USG support in community care in one or more regional departments.  These include:

- CRS/Haiti, funded through USAID, for the Grand’Anse, South, Nippes, Artibonite and Northwest Departments

- Family Health International, funded through CDC, for the Southeast and North departments

- Partners in Health, funded through CDC, for the Central Department

- Plan International, funded through USAID, for the Northeast Department

- World Concern, funded through USAID, for the West Department

It is expected that continuity of services provided by the three USAID partners, CRS, Plan International and World Concern, will be ensured by the program(s) proposed in response to this RFA.   Additionally, the program(s) proposed in response to this RFA will ensure the continuity of HIV/AIDS community care services currently provided by FOSREF and Maison Arc-en-Ciel in Cite Soleil.

The current USAID-funded agreements, with their end dates are:

- Plan International agreement ends September 30, 2009

- World Concern agreement ends September 30, 2009.

- CRS agreement ends in January 31 2009.

- World Vision agreement ends December 31, 2008.

- FOSREF-Cite Soleil agreement ends September 30, 2009.

- Arc-en-Ciel Cite agreement ends September 30, 2009.

In addition to ensuring the continuity of the services provided by the above USAID-funded NGOs, opportunities exist to expand HIV/AIDS support and care to larger numbers of PLWHA and OVC in collaboration with the Title II food assistance activities (see brief description below) and other NGOs that provide assistance to PLWHA and OVC in geographical areas not already covered by USAID-funded projects.

Tuberculosis

Haiti has the highest TB incidence rate in the Latin America and Caribbean (LAC) Region with an estimated incidence of 306 cases per 100,000 population (2004).  There is still a considerable way to go to achieve the national and global targets of 70% case detection and 85% treatment success.  Only 55% of the country is covered by the Directly Observed Therapy-short course (DOTS).   There is a 40% co-infection rate for HIV and TB and the lack of integrated detection and treatment programs hinders care and treatment.   The National Tuberculosis Program has a Global Fund grant.  There are three primary NGOs – ICC, CARE and CDS - that implement several elements of the Global Fund TB program in Haiti.  USAID’s main health bilateral program, SDSH Pwoje Djanm, within the clinics it supports targets TB assistance to further expand case detection and treatment referral in support of the National Tuberculosis Program objectives.  Several opportunities exist to expand USG results in TB through those Title II food assistance activities (see brief description below) implemented by partners that may already be doing TB activities or by further expanding successful community- and/or clinic-based TB services of existing NGOs in Haiti, such as International Child Care, Centre de Developpement et Sante (CDS), CARE, GHESKIO and Partners in Health.

Maternal and Child Health

Although the infant and child mortality rate has decreased slightly, most of the full range of indicators underlying the rate have either stagnated or worsened over the last five years.  Breastfeeding has fallen to unacceptably low levels.  Immunizations range from 10% to 40% nationwide.  The incidence of diarrhea and acute respiratory infections (ARI) have held steady, but rates of treatment of ARI have been nearly halved.  Malnutrition among children and pregnant women remain high.  Over 75% of women are delivering at home unassisted by a trained health care provider.  The USAID health bilateral program, SDSH Pwoje Djanm, is focusing USAID maternal and child health assistance on increasing the use of basic health services within SDSH Pwoje Djanm’s target population, specifically prenatal and post-partum care, assisted deliveries, treatment of diarrheal disease and acute respiratory infections in children, nutrition counseling and education (including breastfeeding) and vitamin A supplementation.   This U.S. maternal and child health development assistance will continue through SDSH Pwoje Djanm until the end of the agreement in August 2010.  Several opportunities exist to expand USG results in maternal and child health through Title II food assistance activities (see brief description below) or by further expanding successful community- and clinic-based services of existing NGOs in Haiti, such as the Haiti Health Foundation, Centre de Developpement et Sante, Medishare and CityMed.

Family Planning

The 2005 DHS concluded that the fertility rate (the average number of children per woman of reproductive age) fell from 4.7 children per woman in 2000 to an average of 4 children per women. The rapidly dropping rates of fertility do not correspond with the stagnant levels of contraceptive use.  The contraceptive prevalence rate (the numbers of women of reproductive age using contraception) increased only slightly from 22% in 2000 to 24.8% in 2006— and remains one of the lowest rates in the Western Hemisphere.   The USAID health bilateral program, SDSH Pwoje Djanm, is focusing USAID family planning assistance on increasing the use of voluntary modern contraception by men and women living within Pwoje Djanm’s target areas.   USAID also provides family planning commodities to all US Government supported sites that are delivering family planning services and who are incompliance with the U.S. Government Tiahrt regulations.  This U.S. Government family planning development assistance will continue through SDSH Pwoje Djanm until the end of the agreement in August 2010.  Several opportunities exist to expand USG results in family planning through those Title II food assistance activities (see brief description below) that include family planning or by further expanding successful community- and clinic-based services of existing NGOs in Haiti, such as the Foundation for Reproductive and Family Health (FOSREF), Profamil and DASH (Development of Health Activities in Haiti).

Food Program

USAID/Haiti has a Title II food assistance program through three multi-year assistance program (MYAP) Title II food program mechanisms with World Vision (WV), Catholic Relief Services (CRS), and ACDI-VOCA.   World Vision is geographically covering communities in the Central and West Departments CRS is covering communities in the South and Grand’Anse Departments, and ACDI-VOCA is covering communities in the South East Department   Each of these MYAP Title II partners is planning on using the funding from monetized food programming to deliver clinic- and/or community-based health care services.  Several opportunities exist to expand USG results in HIV/AIDS, maternal and child health, family planning and tuberculosis through these Title II food assistance partner activities.

C.2. ACHIEVING PROGRAM RESULTS

The overall objective of the “Integrated HIV/AIDS Community Care Program”, through this RFA, is to strengthen, expand and coordinate NGO community-based HIV services, integrating child health, reproductive health (maternal health and family planning), tuberculosis detection and treatment, and other social sector services, where applicable, to improve livelihoods and the overall quality of lives of vulnerable Haitian families at the community level.

USAID/Haiti has budgeted approximately up to $125 million for program activities ending September 30, 2014.  The following table provides an illustrative budget per Fiscal Year (FY) of the total amount and type of funding to be allocated each fiscal year, pending actual Congressionally approved funding levels for development assistance in Haiti on an annual basis.  Recipient(s) will be required to program and report on funds based on the funding amount vis-a-vis type of funding received each year.  FY2007 and FY2008 will be combined to support the first year of activities under this agreement.

Illustrative Fiscal Year Funding (000)

| Program Funding Source | FY 2007 (year 1) | FY 2008 (year 1) | FY 2009 (year 2) | FY2010 (year 3) | FY2011 (year 4) | FY2012 (year 5) | FY2013 (year 6) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HIV/AIDS | 1000 | 5,000 | 10,000 | 10,000 | 15,000 | 15,000 | 16,000 |
| Tuberculosis | 0 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 |
| Maternal and Child Health | 0 | 3,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 |
| Family Planning | 0 | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 | 3,000 |
| Other | 0 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 | 1,000 |
| APPROX. TOTAL | 1000 | 13,000 | 19,000 | 19,000 | 24,000 | 24,000 | 25,000 |

USAID encourages applicants to design and propose a community-based program, consistent with USAID regulations, that:

- Creates a strategic vision and platform for integrating and coordinating on a large geographic scale HIV community-based activities through NGOs within the parameters of the PEPFAR Program’s community care and support strategic approach and guidance (refer to additional background documents for Applicants in preparation for applications, Section C.3. ADDITIONAL BACKGROUND INFORMATION).;

- integrates, where applicable, maternal and child health, family planning, and tuberculosis community- and clinic-based activities with the HIV activities;

- strategically selects NGO partners and/or sub-recipients who currently already have strong community- and clinic-based programs in Haiti and would succeed in providing both HIV and other health services, as well as food security interventions, in an integrated manner;

- strategically designs grant application processes for bringing on new NGO partners, as appropriate and applicable, to achieve results;

- leverages and expands results currently being achieved by other U.S. Government implementing partners and other donors in support of the Government of Haiti’s national health strategy and poverty reduction strategy (PRSP);

- further strengthens the institutional capacity of those NGOs that need to strengthen their abilities to design, implement, coordinate, manage and monitor community- and/or clinic-based activities;

- puts in place a cost efficient and programmatically and administratively strong management team and systems that will efficiently perform three overall functions – (1) provide the strategic guidance to coordinate and integrate sub-recipient NGO activities under one cohesive technical approach; 2) efficiently manage the financial “funds flow” and sub-granting processes to NGOs; and (3) monitor, evaluate and report on program effectiveness and results achieved annually.

Specific HIV community-based activities should include:

- working closely with HIV/AIDS care and treatment sites (hospitals, clinics), particularly those of the MOH, to ensure community follow-up of all enrolled HIV patients;

- providing support to people living with HIV and AIDS (PLWHA) and their families, including home visits, provision of commodities and services in the basic package of home services (potable water system, treated bed nets, condoms, personal hygiene items);

- facilitating access to cash-for-work, micro-credit and job skills programs to assist with income generation for families affected by HIV/AIDS;

- providing support to HIV post-test clubs and PLWHA support groups at the community level;

- referring all partners and children of PLWHA to a designated site for HIV counseling and testing;

- conducting follow-up with enrolled PLWHA to ensure they do not miss their clinic appointments for care and treatment;

- referring all pregnant women in the community to a designated site for HIV testing and counseling;

- following up with all HIV positive pregnant women to encourage adherence to the PMTCT plan laid out for them, including the provision of preventive drugs for the new-born infants;

- referring community members  to designated sites for diagnosis and treatment of TB and sexually transmitted infections, as needed;

- providing support to orphans and vulnerable children (OVC), both infected and affected by HIV and AIDS, in one or more of the six intervention areas identified in the PEPFAR OVC guidance (refer to additional background documents for Applicants in preparation for applications, Section C.3. ADDITIONAL BACKGROUND INFORMATION).

Specific maternal and child health community- and/or clinic-based activities, where applicable within the Applicant’s strategic approach, should include:

- raising awareness of the importance of pregnant women receiving prenatal and post partum care, and assisted deliveries with a skilled birth attendant;

- improving behavioral practices to address malnutrition, respiratory and diarrheal diseases at the community and house-hold level;

- increasing access to and use of child health services to prevent disease and treat common childhood illness.

Specific family planning community- and/or clinic-based activities, where applicable within the applicant’s strategic approach, should include:

- raising awareness of the reproductive and child health as well as economic benefits of voluntary family planning;

- increasing access to and use of modern family planning counseling and services.

Specific tuberculosis community- and/or clinic-based activities, where applicable within the applicant’s strategic approach, should include:

- expanding the reach of the current National Tuberculosis Program’s Directly Observed Treatment (DOTS) through NGOs that carry out community and/or clinic-based TB activities.

Pending on Congressionally approved appropriations and earmarks, there may be other social sector activities related to improving livelihoods at the community and household level to be implemented.

In the case of an umbrella award, applicants should estimate the dollar amount of a typical sub-grant envisioned under this program and any minimum or maximum amounts envisioned; the approximate number of sub-grants to be awarded per year and the approximate total amount of the program that will be awarded as sub-grants; and the distribution of sub-grants by geographic intervention area and high-risk population.  USAID expects the award(s) under this RFA to promote gender equity and support a range of activities that will lead towards the achievement of the overall objective.

In carrying out the program, the recipient will:

- ensure that all USAID funds, including funds provided to sub-grantees, are managed and disbursed per USAID regulations and cost principles;

- develop for the approval of the USAID/Haiti Mission Environmental Officer (MEO) a Medical Waste Disposal Program, including medical waste resulting from HIV testing, that is in compliance with 22 CFR 216, Environmental Procedures; and,

- ensure compliance with the Medical Waste Disposal Program for all program-funded activities.

Geographic Areas of Intervention

Applicants should propose a logical and rational geographic focus approach, taking into account HIV/AIDS, child survival, family planning and tuberculosis activities funded through other USG agencies and possible linkages with other USG implementing partner activities in other sectors as well as opportunities to further results in areas where there is a gap in community- and/or clinic-based services.  The program should be of sufficient scale, concentration and geographic extent to cover significant portions of the target populations.

EXPECTED RESULTS

Within the applicant’s proposed geographic target area(s), the following are the HIV/AIDS results to be achieved and the minimum list of indicators to be used to measure the successful achievement of the program’s results.

Result #1 - Increased provision of care and support services to people living with HIV and AIDS and to HIV/AIDS related orphans and vulnerable children and to their families.

Indicators:

(1) number and percent of people known to have HIV/AIDS in target intervention areas who receive integrated care and support services, including the basic package of community services for PLWHA and their families;

(2) number and percent of sexual partners and children of people known to have HIV/AIDS who are referred for HIV screening;

(3) number and percent of people known to have HIV/AIDS in target intervention areas referred for TB screening and treatment ;

(4) number and percent of people known to have HIV/AIDS in target intervention areas referred for STI screening and treatment;

(5) number and percent of expected pregnant women in target intervention areas referred for HIV screening;

(6) number and percent of known HIV positive pregnant women who receive community-based care and support through to the post-partum period, including accompanying them for drug prophylaxis for themselves and their new-born infants;

(7) number of HIV/AIDS-related orphans and vulnerable children (OVC) who benefit from one or two of the services in the basic OVC package of services.

(8) number of HIV/AIDS-related orphans and vulnerable children (OVC) who benefit from three or more of the services in the basic OVC package of services.

(9) number and percent of households of PLWHA and/or OVC who receive regular food rations (Title II, World Food Program or other sources.)

(10) number of groups (support group/post-test club) organized to respond to the needs of PLWHA which meet regularly

(11) number of providers/caregivers trained to provide home-based care and support to PLWHA and their families;

(12) number of providers/caregivers trained in caring for OVC

Means of Verifying Indicators:  Applicant’s program monitoring and evaluation system

In addition, based on the applicant’s approach to integrating tuberculosis, maternal and child health, and family planning activities, the possible results to be achieved and annual indicators to measure the successful achievement of the program’s results are listed below.   Applicants may elect to omit some of the indicators under Results 2, 3 and 4 below that may not be applicable to the applicant’s proposed approach as well as propose additional indicators.

Result #2 - Increased detection and treatment of tuberculosis.

Indicators:

(1) number of people trained in DOTs with USG funding

(2) case notification rate in new sputum smear positive pulmonary TB cases in USG-supported supported communities and/or clinics

(3) percent of USG-supported laboratories performing TB microscopy with over 95% correct microscopy results

(4) percent of category IV patents that were cured and completed treatment under USG funded DOTS plus program

Means of Verifying Indicators:  Applicant’s program monitoring and evaluation system.

Result #3 - Increased use of basic maternal and child health care services.

Indicators:

(1) number of antenatal care visits by skilled providers through a USG-supported program (disaggregated by matrons and clinic-based skilled providers)

(2) number  and percentage of assisted deliveries with a skilled birth attendant through a USG-supported program (disaggregated by assisted deliveries in a health facility and assisted deliveries by a trained birth attendant -referred to as a matrone in Haiti - in the home)

(3) number and percentage of newborns receiving essential newborn care through a USG-supported program

(4) number of and percentage of postpartum and newborn visits within three days of birth in USG-assisted program

(5) number and percentage of children under the age of one year fully immunized (per the WHO definition of fully immunized child) from a USG-supported program

(6) number and percentage of children under the age of five years treated for diarrheal disease from a USG-supported program

(7) number of cases of child acute respiratory infection and diarrheal disease treated (disaggregated by acute respiratory infection and diarrehal disease)

(8) number and percentage of children under the age of five years who received vitamin A from a USG-supported program

(9) number of people trained (disaggregated by type of training) from a USG-supported program

(10) number of people and percentage of target population that have heard behavior change messages related to infant, child, and reproductive health

Means of Verifying Indicators:  Applicant’s program monitoring and evaluation system.

Result #4 - Increased voluntary use of modern family planning methods.

Indicators:

(1) number of people trained (disaggregated by type of training)

(2) number of counseling visits for family planning / reproductive health in the USG-supported program

(3) couple years of protection (CYP) in the USG-supported program

(4) contraceptive prevalence rate (CPR) in the USG-supported program

(5) number of service delivery points reporting stock-outs of contraceptive commodities

(6) number of people and percentage of target population that have heard behavior change messages on voluntary use of modern contraception and reproductive health

Means of Verifying Indicators:  Applicant’s program monitoring and evaluation system.

Pending on Congressionally approved appropriations and earmarks, there may be other social sector results and indicators to be used to measure those results that are related to improving livelihoods at the community and household level to be implemented.

C.3.	ADDITIONAL BACKGROUND INFORMATION

The following documents are available electronically at http://www.hausaid.info/index.jsp as a wide variety of background information available to all interested applicants.

- USAID Documents

1.	Haiti Demographic and Health Survey 2005-2006.  Available at www.measuredhs.com

2.	HIV/AIDS Behavior Surveillance Survey Summary Report (USAID, FHI, Center for Evaluation and Applied Research and Haitian Child Health Institute) 2006

3.	USAID/Haiti Mission Strategy Statement FY 2007-2009, July 5, 2006. Public Version

4.      USAID/Haiti  Map of Geographic Coverage of Services for HIV-AIDS related Orphans and Vulnerable Children, March 2008.

5.         USAID/Haiti List of NGO and Zones Cibleés Service Delivery Sites, December 2007.

6. 	USG Haiti PEPFAR List of HIV/AIDS Service Delivery Sites, January 2008.

7.      Office of Global AIDS Coordinator (OGAC), Guidance documents for programs in ABC Prevention, Food and Nutrition, Preventive Care, Palliative care and Orphans and Vulnerable Children

B.  Government of Haïti Documents

- Minisetre de la Santé Publique, Plan Stratégique National pour la Reforme du Secteur de la Santé, Novembre, 2005.

- Programme National de Lutte contre le VIH/SIDA, Plan Strategique Intersectoriel, 2007-2009

- Document de Stratégie Nationale pour la Croissance et la Réduction de la Pauvreté  (2008-2010)

C4.  SUBSTANTIAL INVOLVEMENT UNDERSTANDING

USAID/Haiti shall approve all specified key personnel.

C,5   SPECIAL PROVISIONS

Continuation Application: The program period and program amount covers the full program period of seventy-two (72) months; during the first year of the program, the Recipient shall proceed in accordance with the first year work-plan that forms part of its application for funding.  Thereafter, performance of the agreement shall be in accordance with a non-competing continuation application, submitted, reviewed, and approved as follows:

1)  The due date for the first Non-Competing Continuation Application shall be nine months following the award of the agreement.  The Application shall consist of a report of progress from the time of award to the present, expenditures incurred during that period, a work-plan for the second full year of the program and a budget to support the second year work-plan.  Subsequent Non-Competing Applications shall be due on the anniversary date of the first Non-Competing Continuous Application of each program year.  Subsequent Non-Competing Applications shall contain the same information as specified above.

- USAID/Haiti will review Non-Competing Continuation Applications according to formal or informal procedures that it will establish and will advise the Recipient of the results of that review no later than 30 days prior to the end of the current program year.  If the program is approved for another year and subject to funds availability, the Recipient will be advised officially via the CTO.

D.

# REPRESENTATIONS/Certifications required for Cooperative Agreement TO U.S. NGO

# ______________________________________________

# CERTIFICATIONS, ASSURANCES, AND OTHER STATEMENTS OF THE RECIPIENT (MAY 2006)

NOTE: When these Certifications, Assurances, and Other Statements of Recipient are used for cooperative agreements, the term "Grant" means "Cooperative Agreement".

PART I - CERTIFICATIONS AND ASSURANCES

- ASSURANCE OF COMPLIANCE WITH LAWS AND REGULATIONS GOVERNING NON-DISCRIMINATION IN FEDERALLY ASSISTED PROGRAMS

Note: This certification applies to Non-U.S. organizations if any part of the program will be undertaken in the United States.

(a)   The recipient hereby assures that no person in the United States shall, on the bases set forth below, be excluded from participation in, be denied the benefits of, or be otherwise subjected to discrimination under, any program or activity receiving financial assistance from USAID, and that with respect to the Cooperative Agreement for which application is being made, it will comply with the requirements of:

(1)  Title VI of the Civil Rights Act of 1964 (Pub. L. 88-352, 42 U.S.C. 2000-d), which prohibits discrimination on the basis of race, color or national origin, in programs and activities receiving Federal financial assistance;

(2)  Section 504 of the Rehabilitation Act of 1973 (29 U.S.C. 794), which prohibits discrimination on the basis of handicap in programs and activities receiving Federal financial assistance;

(3)  The Age Discrimination Act of 1975, as amended (Pub. L. 95-478), which prohibits discrimination based on age in the delivery of services and benefits supported with Federal funds;

(4)  Title IX of the Education Amendments of 1972 (20 U.S.C. 1681, et seq.), which prohibits discrimination on the basis of sex in education programs and activities receiving Federal financial assistance (whether or not the programs or activities are offered or sponsored by an educational institution); and

(5)  USAID regulations implementing the above nondiscrimination laws, set forth in Chapter II of Title 22 of the Code of Federal Regulations.

(b)  If the recipient is an institution of higher education, the Assurances given herein extend to admission practices and to all other practices relating to the treatment of students or clients of the institution, or relating to the opportunity to participate in the provision of services or other benefits to such individuals, and shall be applicable to the entire institution unless the recipient establishes to the satisfaction of the USAID Administrator that the institution's practices in designated parts or programs of the institution will in no way affect its practices in the program of the institution for which financial assistance is sought, or the beneficiaries of, or participants in, such programs.

(c)  This assurance is given in consideration of and for the purpose of obtaining any and all Federal grants, loans, contracts, property, discounts, or other Federal financial assistance extended after the date hereof to the recipient by the Agency, including installment payments after such date on account of applications for Federal financial assistance which was approved before such date.  The recipient recognizes and agrees that such Federal financial assistance will be extended in reliance on the representations and agreements made in this Assurance, and that the United States shall have the right to seek judicial enforcement of this Assurance.  This Assurance is binding on the recipient, its successors, transferees, and assignees, and the person or persons whose signatures appear below are authorized to sign this Assurance on behalf of the recipient.

2.  CERTIFICATION REGARDING LOBBYING

The undersigned certifies, to the best of his or her knowledge and belief, that:

(1)  No Federal appropriated funds have been paid or will be paid, by or on behalf of the undersigned, to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the awarding of any Federal contract, the making of any Federal Cooperative Agreement, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment or modification of any Federal contract, grant, loan, or cooperative agreement.

(2)  If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned shall complete and submit Standard Form-LLL, "Disclosure of Lobbying Activities,"  in accordance with its instructions.

(3)  The undersigned shall require that the language of this certification be included in the award documents for all subawards at all tiers (including subcontracts, subgrants, and contracts under grants, loans, and cooperative agreements) and that all subrecipients shall certify and disclose accordingly.

This certification is a material representation of fact upon which reliance was placed when this transaction was made or entered into. Submission of this certification is a prerequisite for making or entering into this transaction imposed by section 1352, title 31, United States Code.  Any person who fails to file the required certification shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

Statement for Loan Guarantees and Loan Insurance

The undersigned states, to the best of his or her knowledge and  belief, that:  If any funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this commitment providing for the United States to insure or guarantee a loan, the undersigned shall complete and submit Standard Form-LLL, "Disclosure Form to Report Lobbying," in accordance with its instructions. Submission of this statement is a prerequisite for making or entering into this transaction imposed by section 1352, title 31, U.S. Code. Any person who fails to file the required statement shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

3.  Prohibition on Assistance to Drug Traffickers for Covered Countries and Individuals (ADS 206)

USAID reserves the right to terminate this Agreement, to demand a refund or take other appropriate measures if the Grantee is found to have been  convicted of a narcotics offense or to have been engaged in drug trafficking as defined in 22 CFR Part 140. The undersigned shall review USAID ADS 206 to determine if any certifications are required for Key Individuals or Covered Participants.

If there are COVERED PARTICIPANTS: USAID reserves the right to terminate assistance to or take other appropriate measures with respect to, any participant approved by USAID who is found to have been convicted of a narcotics offense or to have been engaged in drug trafficking as  defined in 22 CFR Part 140.

4.  CERTIFICATION REGARDING TERRORIST FINANCING IMPLEMENTING EXECUTIVE ORDER 13224

By signing and submitting this application, the prospective recipient provides the

certification set out below:

1. The Recipient, to the best of its current knowledge, did not provide, within the

previous ten years, and will take all reasonable steps to ensure that it does not and will not knowingly provide, material support or resources to any individual or entity that commits, attempts to commit, advocates, facilitates, or participates in terrorist acts, or has committed, attempted to commit, facilitated, or participated in terrorist acts, as that term is defined in paragraph 3.

2. The following steps may enable the Recipient to comply with its obligations under paragraph 1:

a. Before providing any material support or resources to an individual or entity, the Recipient will verify that the individual or entity does not (i) appear on the master list of Specially Designated Nationals and Blocked Persons, which list is maintained by the U.S. Treasury’s Office of Foreign Assets Control (OFAC) and is available online at OFAC’s website : http://www.treas.gov/offices/eotffc/ofac/sdn/t11sdn.pdf, or (ii) is not included in any supplementary information concerning prohibited individuals or entities that may be provided by USAID to the Recipient.

b. Before providing any material support or resources to an individual or entity, the Recipient also will verify that the individual or entity has not been designated by the United Nations Security (UNSC) sanctions committee established under UNSC Resolution 1267 (1999) (the “1267 Committee”) [individuals and entities linked to the Taliban, Usama bin Laden, or the Al Qaida Organization]. To determine whether there has been a published designation of an individual or entity by the 1267 Committee, the Recipient should refer to the consolidated list available online at the Committee’s website: http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.

c. Before providing any material support or resources to an individual or entity, the Recipient will consider all information about that individual or entity of which it is aware and all public information that is reasonably available to it or of which it should be aware.

d. The Recipient also will implement reasonable monitoring and oversight

procedures to safeguard against assistance being diverted to support terrorist activity.

3. For purposes of this Certification-

a. “Material support and resources” means currency or monetary instruments or

financial securities, financial services, lodging, training, expert advice or assistance, safehouses, false documentation or identification, communications equipment, facilities, weapons, lethal substances, explosives, personnel, transportation, and other physical assets, except medicine or religious materials.”

b. “Terrorist act” means-

(i) an act prohibited pursuant to one of the 12 United Nations Conventions and Protocols related to terrorism (see UN terrorism conventions Internet site: http://untreaty.un.org/English/Terrorism.asp); or

(ii) an act of premeditated, politically motivated violence perpetrated against noncombatant targets by subnational groups or clandestine agents; or

(iii) any other act intended to cause death or serious bodily injury to a civilian, or to any other person not taking an active part in hostilities in a situation of armed conflict, when the purpose of such act, by its nature or context, is to intimidate a population, or to compel a government or an international organization to do or to abstain from doing any act.

c. “Entity” means a partnership, association, corporation, or other organization, group or subgroup.

d. References in this Certification to the provision of material support and resources shall not be deemed to include the furnishing of USAID funds or USAID-financed commodities to the ultimate beneficiaries of USAID assistance, such as recipients of food, medical care, micro-enterprise loans, shelter, etc., unless the Recipient has reason to believe that one or more of these beneficiaries commits, attempts to commit, advocates, facilitates, or participates in terrorist acts, or has committed, attempted to commit, facilitated or participated in terrorist acts.

e. The Recipient’s obligations under paragraph 1 are not applicable to the

procurement of goods and/or services by the Recipient that are acquired in the ordinary course of business through contract or purchase, e.g., utilities, rents, office supplies, gasoline, etc., unless the Recipient has reason to believe that a vendor or supplier of such goods and services commits, attempts to commit, advocates, facilitates, or participates in terrorist acts, or has committed, attempted to commit, facilitated or participated in terrorist acts.

This Certification is an express term and condition of any agreement issued as a result of this application, and any violation of it shall be grounds for unilateral termination of the agreement by USAID prior to the end of its term.

5.  CERTIFICATION OF RECIPIENT

By signing below the recipient provides certifications and assurances for (1) the Assurance of Compliance with Laws and Regulations Governing Non-Discrimination in Federally Assisted Programs, (2) the Certification Regarding Lobbying, (3) the Prohibition on Assistance to Drug Traffickers for Covered Countries and Individuals (ADS 206) and (4) the Certification Regarding Terrorist Financing Implementing Executive Order 13224 above.

RFA/APS No. ________________________________

Application No.     ______________________________

Date of Application ______________________________

Name of Recipient            _______________________________

Typed Name and Title         __________________________________

Signature              _____________________________________

Date                   _______________

PART II - KEY INDIVIDUAL CERTIFICATION NARCOTICS OFFENSES AND DRUG TRAFFICKING

I hereby certify that within the last ten years:

1. I have not been convicted of a violation of, or a conspiracy to violate, any law or regulation of the United States or any other country concerning narcotic or psychotropic drugs or other controlled substances.

2. I am not and have not been an illicit trafficker in any such drug or controlled substance.

3. I am not and have not been a knowing assistor, abettor, conspirator, or colluder with others in the illicit trafficking in any such drug or substance.

Signature: 		____________________________

Date: 			____________________________

Name: 			____________________________

Title/Position: 	____________________________

Organization: 	____________________________

Address: 		____________________________

____________________________

Date of Birth: 	____________________________

NOTICE:

1. You are required to sign this Certification under the provisions of 22 CFR Part 140, Prohibition on Assistance to Drug Traffickers. These regulations were issued by the Department of State and require that certain key individuals of organizations must sign this Certification.

2. If you make a false Certification you are subject to U.S. criminal prosecution under 18 U.S.C. 1001.

PART III - PARTICIPANT CERTIFICATION NARCOTICS OFFENSES AND DRUG TRAFFICKING

1. I hereby certify that within the last ten years:

a. I have not been convicted of a violation of, or a conspiracy to violate, any law or regulation of the United States or any other country concerning narcotic or psychotropic drugs or other controlled substances.

b. I am not and have not been an illicit trafficker in any such drug or controlled substance.

c. I am not or have not been a knowing assistor, abettor, conspirator, or colluder with others in the illicit trafficking in any such drug or substance.

2. I understand that USAID may terminate my training if it is determined that I engaged in the above conduct during the last ten years or during my USAID training.

Signature: 		___________________________________

Name: 			___________________________________

Date: 			___________________________________

Address: 		___________________________________

___________________________________

Date of Birth: 	___________________________________

NOTICE:

1. You are required to sign this Certification under the provisions of 22 CFR Part 140,Prohibition on Assistance to Drug Traffickers. These regulations were issued by the Department of State and require that certain participants must sign this Certification.

2. If you make a false Certification you are subject to U.S. criminal prosecution under 18 U.S.C. 1001.

PART IV -  CERTIFICATION OF COMPLIANCE WITH THE STANDARD PROVISIONS ENTITLED “CONDOMS” AND “PROHIBITION ON THE PROMOTION OR ADVOCACY OF THE LEGALIZATION OR PRACTICE OF PROSTITUTION OR SEX TRAFFICKING.”

Applicability: This certification requirement only applies to the prime recipient. Before a U.S. or non-U.S. non-governmental organization receives FY04-FY08 HIV/AIDS funds under a grant or cooperative agreement, such recipient must provide to the Agreement Officer a certification substantially as follows:

“[Recipient's name] certifies compliance as applicable with the standard

provisions entitled “Condoms” and “Prohibition on the Promotion or Advocacy

of the Legalization or Practice of Prostitution or Sex Trafficking” included in

the referenced agreement.”

RFA/APS No.		_______________________________

Application No.	 	_______________________________

Date of Application	_______________________________

Name of Applicant/Subgrantee	_______________________________

Typed Name and Title	_______________________________

_______________________________

Signature 			_______________________________

PART V - SURVEY ON ENSURING EQUAL OPPORTUNITY FOR APPLICANTS

Applicability:  All RFA’s must include the attached Survey on Ensuring Equal Opportunity for Applicants as an attachment to the RFA package. Applicants under unsolicited applications are also to be provided the survey. ( While inclusion of the survey by Agreement Officers in RFA packages is required, the applicant’s completion of the survey is voluntary, and must not be a requirement of the RFA. The absence of a completed survey in an application may not be a basis upon which the application is determined incomplete or non-responsive. Applicants who volunteer to complete and submit the survey under a competitive or non-competitive action are instructed within the text of the survey to submit it as part of the application process.)

PART VI - OTHER STATEMENTS OF RECIPIENT

1.  AUTHORIZED INDIVIDUALS

The recipient represents that the following persons are authorized to negotiate on its behalf with the Government and to bind the recipient in connection with this application or grant:

Name               Title               Telephone No.      Facsimile No.

________________________________________________________________

________________________________________________________________

________________________________________________________________

2.  TAXPAYER IDENTIFICATION NUMBER (TIN)

If the recipient is a U.S. organization, or a foreign organization which has income effectively connected with the conduct of activities in the U.S. or has an office or a place of business or a fiscal paying agent in the U.S., please indicate the recipient's TIN:

TIN: ________________________________

3.  DATA UNIVERSAL NUMBERING SYSTEM (DUNS) NUMBER

(a)  In the space provided at the end of this provision, the recipient should supply the Data Universal Numbering System (DUNS) number applicable to that name and address.  Recipients should take care to report the number that identifies the recipient's name and address exactly as stated in the proposal.

(b)  The DUNS is a 9-digit number assigned by Dun and Bradstreet Information Services.  If the recipient does not have a DUNS number, the recipient should call Dun and Bradstreet directly at 1-800-333-0505. A DUNS number will be provided immediately by telephone at no charge to the recipient.  The recipient  should be prepared to provide the following information:

(1) Recipient's name.

(2) Recipient's address.

(3) Recipient's telephone number.

(4) Line of business.

(5) Chief executive officer/key manager.

(6) Date the organization was started.

(7) Number of people employed by the recipient.

(8) Company affiliation.

(c)  Recipients located outside the United States may obtain the location and phone number of the local Dun and Bradstreet Information Services office from the Internet Home Page at http://www.dbisna.com/dbis/customer/custlist.htm. If an offeror is unable to locate a local service center, it may send an e-mail to Dun and Bradstreet at globalinfo@dbisma.com.

The  DUNS system is distinct from the Federal Taxpayer Identification Number (TIN) system.

DUNS: ________________________________________

4.  LETTER OF CREDIT (LOC) NUMBER

If the recipient has an existing Letter of Credit (LOC) with USAID, please indicate the LOC number:

LOC:  _________________________________________

5.  PROCUREMENT INFORMATION

(a)  Applicability.  This applies to the procurement of goods and services planned by the recipient (i.e., contracts, purchase orders, etc.) from a supplier of goods or services for the direct use or benefit of the recipient in conducting the program supported by the grant, and not to assistance provided by the recipient (i.e., a subgrant or subagreement) to a subgrantee or subrecipient in support of the subgrantee's or subrecipient's program.  Provision by the recipient of the requested information does not, in and of itself, constitute USAID approval.

(b)  Amount of Procurement.  Please indicate the total estimated dollar amount of goods and services which the recipient plans to purchase under the grant:

$__________________________

(c) Nonexpendable Property.  If the recipient plans to purchase nonexpendable equipment which would require the approval of the Agreement Officer, please indicate below (using a continuation page, as necessary) the types, quantities of each, and estimated unit costs. Nonexpendable equipment for which the Agreement Officer's approval to purchase is required is any article of nonexpendable tangible personal property charged directly to the grant, having a useful life of more than one year and an acquisition cost of $5,000 or more per unit.

TYPE/DESCRIPTION(Generic)             QUANTITY       ESTIMATED UNIT COST

(d)  Source, Origin, and Componentry of Goods.  If the recipient plans to purchase any goods/commodities which are not of U.S. source and/or U.S. origin, and/or does not contain at least 50% componentry, which are not at least 50% U.S. source and origin, please indicate below (using a continuation page, as necessary) the types and quantities of each, estimated unit costs of each, and probable source and/or origin, to include the probable source and/or origin of the components if less than 50% U.S. components will be contained in the commodity.  "Source" means the country from which a commodity is shipped to the cooperating country or the cooperating country itself if the commodity is located therein at the time of purchase.  However, where a commodity is shipped from a free port or bonded warehouse in the form in which received therein, "source" means the country from which the commodity was shipped to the free port or bonded warehouse.  Any commodity whose source is a non-Free World country is ineligible for USAID financing.  The "origin" of a commodity is the country or area in which a commodity is mined, grown, or produced.  A commodity is produced when, through manufacturing, processing, or substantial and major assembling of components, a commercially recognized new commodity results, which is substantially different in basic characteristics or in purpose or utility from its components.  Merely packaging various items together for a particular procurement or relabeling items do not constitute production of a commodity.  Any commodity whose origin is a non-Free World country is ineligible for USAID financing.  "Components" are the goods, which go directly into the production of a produced commodity. Any component from a non-Free World country makes the commodity ineligible for USAID financing.

TYPE/DESCRIPTION   QUANTITY   ESTIMATED   GOODS        PROBABLE  GOODS        PROBABLE

(Generic)                   UNIT COST   COMPONENTS   SOURCE    COMPONENTS   ORIGIN

(e)  Restricted Goods.  If the recipient plans to purchase any restricted goods, please indicate below (using a continuation page, as necessary) the types and quantities of each, estimated unit costs of each, intended use, and probable source and/or origin.  Restricted goods are Agricultural Commodities, Motor Vehicles, Pharmaceuticals, Pesticides, Rubber Compounding Chemicals and Plasticizers, Used Equipment, U.S. Government-Owned Excess Property, and Fertilizer.

TYPE/DESCRIPTION  QUANTITY  ESTIMATED  PROBABLE  INTENDED USE

(Generic)                UNIT COST   SOURCE    ORIGIN

(f)  Supplier Nationality.  If the recipient plans to purchase any goods or services from suppliers of goods and services whose nationality is not in the U.S., please indicate below (using a continuation page, as necessary) the types and quantities of each good or service, estimated costs of each, probable nationality of each non-U.S. supplier of each good or service, and the rationale for purchasing from a non-U.S. supplier.  Any supplier whose nationality is a non-Free World country is ineligible for USAID financing.

TYPE/DESCRIPTION   QUANTITY   ESTIMATED   PROBABLE SLUPPIER   NATIONALITY   RATIONALE

(Generic)                   UNIT COST   (Non-US Only)                   for NON-US

(g)  Proposed Disposition.  If the recipient plans to purchase any nonexpendable equipment with a unit acquisition cost of $5,000 or more, please indicate below (using a continuation page, as necessary) the proposed disposition of each such item.  Generally, the recipient may either retain the property for other uses and make compensation to USAID (computed by applying the percentage of federal participation in the cost of the original program to the current fair market value of the property), or sell the property and reimburse USAID an amount computed by applying to the sales proceeds the percentage of federal participation in the cost of the original program (except that the recipient may deduct from the federal share $500 or 10% of the proceeds, whichever is greater, for selling and handling expenses), or donate the property to a host country institution, or otherwise dispose of the property as instructed by USAID.

TYPE/DESCRIPTION(Generic)   QUANTITY   ESTIMATED UNIT COST   PROPOSED   DISPOSITION

6.  PAST PERFORMANCE REFERENCES

On a continuation page, please provide past performance information requested in the RFA.

7.  TYPE OF ORGANIZATION

The recipient, by checking the applicable box, represents that -

(a)  If the recipient is a U.S. entity, it operates as [  ] a corporation incorporated under the laws of the State of, [ ] an individual, [  ] a partnership, [  ] a nongovernmental nonprofit organization, [  ] a state or loc al governmental organization, [  ] a private college or university, [  ] a public college or university, [  ] an international organization, or [  ] a joint venture; or

(b)  If the recipient is a non-U.S. entity, it operates as [  ] a corporation organized under the laws of _____________________________ (country), [  ] an individual, [  ] a partnership, [  ] a nongovernmental nonprofit organization, [  ] a nongovernmental educational institution, [ ] a governmental organization, [ ] an international organization, or [ ] a joint venture.

8.  ESTIMATED COSTS OF COMMUNICATIONS PRODUCTS

The following are the estimate(s) of the cost of each separate communications product (i.e., any printed material [other than non- color photocopy material], photographic services, or video production services) which is anticipated under the grant.  Each estimate must include all the costs associated with preparation and execution of the product.  Use a continuation page as necessary.

E.  Award Format

(NAME)

(ADDRESS)

Reference:

Subject:  Cooperative Agreement No.________________

Dear _________:

Pursuant to the authority contained in the Foreign Assistance Act of 1961, as amended, the U.S. Agency for International Development (USAID) hereby awards to (Organization/Recipient), hereinafter referred to as the “Recipient”, the sum of $ __________ to provide support for a program in ___________ as described in the Schedule of this award and in Attachment B, entitled "Program Description."

This Cooperative Agreement is effective and obligation is made as of the date of this letter and shall apply to expenditures made by the Recipient in furtherance of program objectives during the period beginning with the effective date _______ and ending________.  USAID will not be liable for reimbursing the Recipient for any costs in excess of the obligated amount.

This Cooperative Agreement is made to the Recipient _____________, on condition that the funds will be administered in accordance with the terms and conditions as set forth in Attachment A (the Schedule), Attachment B (the Program Description), and Attachment C (the Standard Provisions), all of which have been agreed to by your organization.

Please sign the original and all enclosed copies of this letter to acknowledge your receipt of the Cooperative Agreement, and return the original and all but one copy to the Agreement Officer.

Sincerely yours,

xxxxxxxxxxxxxxxxxxx

Agreement Officer

Attachments:

A.  Schedule

B.  Program Description

C.  Standard Provisions

ACKNOWLEDGED:

BY:    _______________________________

TITLE: _______________________________

DATE:  _______________________________

A.  GENERAL

1. Appropriation:

2. Amount Obligated this Action:

3. Total Estimated USAID Amount:

4. Total Obligated USAID Amount:

5. Cost-Sharing Amount (Non-Federal):

6. Activity Title:

7. USAID Technical Office:

8. Tax I.D. Number:

9. DUNS No.:

10. LOC Number:

B. SPECIFIC

For AID/W Actions:

1. Budget Fiscal Year:

2. Operating Unit:

3. Strategic Objective:

4. Team/Division:

5. Benefiting Geo Area:

6. Object Class:

For Mission Actions:

1. Budget Plan Code:

2. MAARD No.:

3. Strategic Objective No.:

C. PAYMENT OFFICE

TABLE OF CONTENTS

Attachment A   SCHEDULE	3

A.1  PURPOSE OF COOPERATIVE AGREEMENT	3

A.2  PERIOD OF COOPERATIVE AGREEMENT	3

A.3  AMOUNT OF COOPERATIVE AGREEMENT AND PAYMENT	3

A.4  COOPERATIVE AGREEMENT BUDGET	3

A.5  REPORTING AND EVALUATION	3

A.6  INDIRECT COST RATE	3

A.7  TITLE TO PROPERTY	3

A.8  AUTHORIZED GEOGRAPHIC CODE	3

A.9  COST SHARING	3

A.10 SUBSTANTIAL INVOLVEMENT	3

A.11  PROGRAM INCOME	3

A.12  SPECIAL PROVISIONS	3

A.12.1 USAID DISABILITY POLICY (DEC 2004)	3

A.12.2  EXECUTIVE ORDER ON TERRORISM FINANCING (FEB 2002)	3

A.12.3  FOREIGN GOVERNMENT DELEGATIONS TO INTERNATIONAL	3

CONFERENCES (JAN 2002)	3

A.12.4  COUNTRY-BY-COUNTRY BREAKDOWN OF EXPENDITURES	3

-End of Schedule- Attachment B    PROGRAM DESCRIPTION	3

Attachment B    PROGRAM DESCRIPTION	3

ATTACHMENT C  STANDARD PROVISIONS	3

STANDARD PROVISIONS FOR U.S., NONGOVERNMENTAL ORGANIZATIONS	3

# Attachment A   SCHEDULE

## A.1  PURPOSE OF COOPERATIVE AGREEMENT

The purpose of this Cooperative Agreement is to provide support for the program described in Attachment 2 to this Cooperative Agreement entitled "Program Description."

## A.2  PERIOD OF COOPERATIVE AGREEMENT

1. The effective date of this Cooperative Agreement is _________. The estimated completion date of this Cooperative Agreement is _________.

(For incrementally funded Cooperative Agreements or where pre-awarded expenses are authorized, add the following sentence :)

2. Funds obligated hereunder are available for program expenditures for the estimated period ________ to ________.

## A.3  AMOUNT OF COOPERATIVE AGREEMENT AND PAYMENT

(For fully funded Cooperative Agreements use the following :)

1. USAID hereby obligates the amount of $______ for purposes of this Cooperative Agreement.

2. Payment shall be made to the Recipient by Letter of Credit in accordance with procedures set forth in 22 CFR 226. (NOTE: Letter of Credit is the "preferred payment method".  However, the Agreement Officer must select the appropriate method of payment in accordance with the applicability requirements set forth in 22 CFR 226; i.e., letter of credit, advance payment or reimbursement.)

-Or-

(For incrementally funded Cooperative Agreements use the following in place of the above :)

1. The total estimated amount of this Cooperative Agreement for the period shown in A.2.1 above is $________.

2. USAID hereby obligates the amount of $___________ for program expenditures during the period set forth in A.2.2 above and as shown in the Budget below. The Recipient will be given written notice by the Agreement Officer if additional funds will be added. USAID is not obligated to reimburse the Recipient for the expenditure of amounts in excess of the total obligated amount.

3. Payment will be made to the Recipient by Letter of Credit in accordance with procedures set forth in 22 CFR 226 (NOTE: Letter of Credit is the "preferred payment method". However the Agreement Officer must select the appropriate method of payment in accordance with the applicability requirements set forth in 22CFR 226; i.e., letter of credit, advance payment or reimbursement.)

## A.4  COOPERATIVE AGREEMENT BUDGET

(NOTE - the items included in the budget, including local cost financing items, should relate to the results, activities or functions described in Attachment B - Program Description, not to specific cost items (such as salaries or travel) except for those listed as items 4-6 below. However, at the discretion of the Agreement Officer, an alternative budget may be appropriate.)

The following is the Agreement Budget, including local cost financing items, if authorized.  Revisions to this budget shall be made in accordance with 22 CFR 226.

TOTAL*

From**__to**__      From**__to**__   From**__to**__

Cost Element           $US/Local		 $US/Local		$US/Local

1.

2.

3.

4. Training

5. Procurement

6. Indirect Costs     ____ _______      ____ _______     ____ ______

overhead

7. Total $            ____ _______      ____ _______     ____ ______

* Use all three columns for incrementally funded Cooperative Agreements, otherwise use only this column.

** Insert effective and expiration dates of Cooperative Agreement or obligation/funding dates.

## A.5  REPORTING AND EVALUATION

1. Financial Reporting

The Recipient shall submit __ (an original and __copies). (Note - Agreement Officer to determine type of report, frequency of reporting periods and address)  Financial Reports shall be in keeping with 22 CFR 226.

(For U.S. Organizations under Letter of Credit the following language shall be used):

In accordance with 22 CFR 226.52, the SF 269 and SF 272 will be required on a quarterly basis. The recipient shall submit these forms in the following manner:

(1) The SF 272 and 272a (if necessary) must be submitted via electronic format to the U.S. Department of Health and Human Services (http://www.dpm.psc.gov).  A copy of this form shall also be submitted at the same time to the Agreement Officer (NOTE: if Agreement Officer desires a copy) and the Cognizant Technical Officer.

(2) The SF 269 or 269a (as appropriate) shall be submitted to the Cognizant Technical officer with one copy to the Agreement Officer (Note: if Agreement Officer desires).

(3) In accordance with 22 CFR 226.70-72, the original and two copies of all final financial reports shall be submitted to M/FM, the Agreement Officer (if requested) and the CTO.  The electronic version of the final SF 272 or 272a shall be submitted to HHS in accordance with paragraph (1) above.

2. Program Reporting

The Recipient shall submit (Note: specify number of copies, not to exceed the original and two copies) of a performance report to , the Cognizant Technical Officer,  (Note: specify name and title of the Agreement Officer, if desired, along with address).  The performance reports are required to be submitted _________ (Note: state frequency, not to exceed quarterly) and shall contain the following information: (Note: state reporting requirements, as related to the Program Description)

3.  Final Report

The Recipient shall submit the original and one copy to M/FM, the Agreement Officer (if requested),  and the CTO  and one copy, in electronic (preferred) or paper form of final documents to one of the following: (a) Via E-mail: docsubmit@dec.cdie.org ; (b) Via U.S. Postal Service:  Development Experience Clearinghouse, 8403 Colesville Road, Suite 210 Silver Spring, MD  20910, USA; (c) Via Fax: (301) 588-7787; or (d) Online:

http://www.dec.org/index.cfm?fuseaction=docSubmit.home.

(Note: Agreement Officer to verify ADS 540 for detailed information on which categories of development experience documents should or should not be submitted to CDIE and appropriate format for electronic transmission.)

The final performance report shall contain the following information __________. (Note: state reporting requirements, as related to the Program Description).

## A.6  INDIRECT COST RATE

(Note: Establish the applicable indirect cost rate(s), base(s) on which they apply, and the Recipient's accounting period(s) they cover, as provided in the appropriate Standard Provision.  If an Indirect Cost Rate Agreement has been executed by USAID or a cognizant Federal agency, such rate(s) are required to be incorporated herein if such costs are covered by the Cooperative agreement.  The most current overhead information should be obtained from the Overhead and Special Costs and Contract Close-Out Branch (M/OAA/CAS).)

Pending establishment of revised provisional or final indirect cost rates, allowable indirect costs shall be reimbursed on the basis of the following negotiated provisional or predetermined rates and the appropriate bases:

Description            Rate         Base    Type    Period

1/      1/       1/

2/      2/       2/

3/      3/       3/

1/Base of Application:

Type of Rate: Provisional

Period:

2/Base of Application:

Type of Rate: Provisional

Period:

3/Base of Application:

Type of Rate: Provisional

Period:

## A.7  TITLE TO PROPERTY

(Note: Specify to whom title will vest for property, by category if appropriate.)

Property Title will be vested with the Cooperative Country.

## A.8  AUTHORIZED GEOGRAPHIC CODE

(Note: Add the following for cooperative agreements having a procurement element greater than $250,000.)

The authorized geographic code for procurement of goods and services under this award is _______.

## A.9  COST SHARING

(Note: For those cooperative agreements with a Cost-share element add the following :)

The Recipient agrees to expend an amount not less than of the total activity costs.

## A.10 SUBSTANTIAL INVOLVEMENT

Substantial involvement during the implementation of this Agreement shall be limited to approval of the elements listed below:

(Note: Refer to ADS 303 for a list of approved substantial involvement.  Involvement may consist of one or all of the listed elements shown below and in that ADS section, unless a deviation is approved in accordance with 303.3.4)

- Approval of Recipient Implementation Plans.

- Approval of specified key personnel assigned to the positions listed below.  The personnel currently listed have been approved.  All changes thereto must be submitted for the approval by the Cognizant Technical Officer.

Title:               Name:

Title:			Name:

c.  Agency and recipient collaboration or joint participation.

d.  Agency Authority to immediately halt a construction activity.

## A.11  PROGRAM INCOME

(Note: For Cooperative agreements which may generate Program Income, add the following :)

The Recipient shall account for Program Income in accordance with 22 CFR 226.24 (or the Standard Provision entitled Program Income for non-U.S. organizations).  Program Income earned under this award shall be added to the project.

(Note: Agreement Officers, in consultation with the Technical Officer, must decide how Program Income will be applied: 1) added to the Project; 2) used to finance the non-Federal share; 3) deducted from the total Federal share.  All three may be picked as long as a descending order (i.e. "excess amounts may be applied to another alternative") is established in accordance with 22 CFR 226.24.  Agreement Officers are encouraged to be as specific as possible in detailing the appropriate types of activities Program Income may be applied for when using the additive option as described as 226.24(b)(1).

## A.12  SPECIAL PROVISIONS

“ORGANIZATIONS ELIGIBLE FOR ASSISTANCE (ASSISTANCE) (JUNE 2005)

An organization that is otherwise eligible to receive funds under this agreement

to prevent, treat, or monitor HIV/AIDS shall not be required to endorse or utilize a

multisectoral approach to combatting HIV/AIDS, or to endorse, utilize, or

participate in a prevention method or treatment program to which the

organization has a religious or moral objection.

CONDOMS (ASSISTANCE) (JUNE 2005)

Information provided about the use of condoms as part of projects or activities

that are funded under this agreement shall be medically accurate and shall

include the public health benefits and failure rates of such use and shall be

consistent with USAID’s fact sheet entitled, “USAID: HIV/STI Prevention and

Condoms. This fact sheet may be accessed at:

http://www.usaid.gov/our_work/global_health/aids/TechAreas/prevention/condomfactsheet.html”

“PROHIBITION ON THE PROMOTION OR ADVOCACY OF THE

LEGALIZATION OR PRACTICE OF PROSTITUTION OR SEX TRAFFICKING

(ASSISTANCE) (JUNE 2005)

(a) The U.S. Government is opposed to prostitution and related activities, which

are inherently harmful and dehumanizing, and contribute to the phenomenon of

trafficking in persons. None of the funds made available under this agreement

may be used to promote or advocate the legalization or practice of prostitution or

sex trafficking. Nothing in the preceding sentence shall be construed to preclude

the provision to individuals of palliative care, treatment, or post-exposure

pharmaceutical prophylaxis, and necessary pharmaceuticals and commodities,

including test kits, condoms, and, when proven effective, microbicides.

(b) Except as noted in the second sentence of this paragraph, as a condition of

entering into this agreement or any subagreement, a non-governmental

organization or public international organization recipient/subrecipient must have

a policy explicitly opposing prostitution and sex trafficking. The following

organizations are exempt from this paragraph: the Global Fund to Fight AIDS,

Tuberculosis and Malaria; the World Health Organization; the International AIDS

Vaccine Initiative; and any United Nations agency.

(c) The following definition applies for purposes of this provision:

Sex trafficking means the recruitment, harboring, transportation, provision, or

obtaining of a person for the purpose of a commercial sex act. 22 U.S.C.

7102(9).

(d) The recipient shall insert this provision, which is a standard provision, in all

subagreements.

(e) This provision includes express terms and conditions of the agreement and

any violation of it shall be grounds for unilateral termination of the agreement by

USAID prior to the end of its term.

(End of Provision)”

(Note: - Use this section to delete inapplicable Standard Provisions or to add provisions of special applicability as authorized.  Included should be waivers, including authorized local cost financing, and any alterations to the Standard Provisions or 22 CFR 226 which have been approved as deviations for the specific award.)

### A.12.1 USAID DISABILITY POLICY (DEC 2004)

- The objectives of the USAID Disability Policy are (1) to enhance the attainment of United States foreign assistance program goals by promoting the participation and equalization of opportunities of individuals with disabilities in USAID policy, country and sector strategies, activity designs and implementation; (2) to increase awareness of issues of people with disabilities both within USAID programs and in host countries; (3) to engage other U.S. government agencies, host country counterparts, governments, implementing organizations and other donors in fostering a climate of nondiscrimination against people with disabilities; and (4) to support international advocacy for people with disabilities.  The full text of the policy paper can be found at the following website: http://www.usaid.gov/about_usaid/disability/.

(b)  USAID therefore requires that the recipient not discriminate against people with disabilities in the implementation of USAID funded programs and that it make every effort to comply with the objectives of the USAID Disability Policy in performing the program under this grant or cooperative agreement. To that end and to the extent it can accomplish this goal within the scope of the program objectives, the recipient should demonstrate a comprehensive and consistent approach for including men, women and children with disabilities.

### A.12.2  EXECUTIVE ORDER ON TERRORISM FINANCING (FEB 2002)

The Contractor/Recipient is reminded that U.S. Executive Orders and U.S. law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism.  It is the responsibility of the contractor/recipient to ensure compliance with these Executive Orders and laws.  This provision must be included in all subcontracts/subawards issued under this contract/agreement.

(Note: Before making the award, the Agreement Officer must obtain from the organization, the terrorist financing certification shown in AAPD 04-14.)

(Note: The following “Foreign Government Delegations” provision is only included in agreements funded from the following accounts: - Development Assistance, including assistance for sub-Saharan Africa, - Child Survival and Disease Programs Fund, and - Micro and Small Enterprise Development Program Account):

### A.12.3  FOREIGN GOVERNMENT DELEGATIONS TO INTERNATIONAL

### CONFERENCES (JAN 2002)

Funds in this [agreement, amendment] may not be used to finance the travel, per diem, hotel expenses, meals, conference fees or other conference costs for any member of a foreign government's delegation to an international conference sponsored by a public international organization, except as provided in ADS Mandatory Reference "Guidance on Funding Foreign Government Delegations to International Conferences" or as approved by the AO.

(Note: For those awards covering programs in more than one country, include the following special provision):

### A.12.4  COUNTRY-BY-COUNTRY BREAKDOWN OF EXPENDITURES

Recipient shall list each country included in the program and the total amount expended for each country under the award for the reporting period in the "Remarks" block on the "Financial Status Report" SF 269 or SF 269A, or on a separate sheet of paper with the "Request for Advance or Reimbursement" SF 270.

# -End of Schedule-

# Attachment B    PROGRAM DESCRIPTION

# ATTACHMENT C  STANDARD PROVISIONS

# STANDARD PROVISIONS FOR U.S., NONGOVERNMENTAL ORGANIZATIONS

(See 	Standard Provisions for U.S., Nongovernmental Recipients listed under Mandatory References in ADS 303.)

Mandatory Standard Provisions for U.S., Nongovernmental Recipients

I. MANDATORY STANDARD PROVISIONS FOR U.S. NONGOVERNMENTAL

RECIPIENTS.......4

1. APPLICABILITY OF 22 CFR PART 226 (May 2005)...........................4

2. INELIGIBLE COUNTRIES (MAY 1986).......................................4

3. NONDISCRIMINATION (MAY 1986)..........................................4

4. NONLIABILITY (NOVEMBER 1985)..........................................5

5. AMENDMENT (NOVEMBER 1985).............................................5

6. NOTICES (NOVEMBER 1985)...............................................5

7. SUBAGREEMENTS (June 1999).............................................5

8. OMB APPROVAL UNDER THE PAPERWORK REDUCTION ACT (December 2003)........6

9. USAID ELIGIBILITY RULES FOR GOODS AND SERVICES (April 1998)...........6

*10. DEBARMENT, SUSPENSION, AND OTHER RESPONSIBILITY MATTERS (January 2004) 10

*11. DRUG-FREE WORKPLACE (January 2004).................................11

*12. EQUAL PROTECTION OF THE LAWS FOR FAITH-BASED AND COMMUNITY ORGANIZATIONS (February 2004)............................................12

*13. IMPLEMENTATION OF E.O. 13224 -- EXECUTIVE ORDER ON TERRORIST FINANCING (March 2002).............................................................13

*14. MARKING UNDER USAID-FUNDED ASSISTANCE INSTRUMENTS (December 2005)..13

15. REGULATIONS GOVERNING EMPLOYEES (AUGUST 1992)......................18

16. CONVERSION OF UNITED STATES DOLLARS TO LOCAL CURRENCY (NOVEMBER 1985) 19

17. USE OF POUCH FACILITIES (AUGUST 1992)..............................20

18. INTERNATIONAL AIR TRAVEL AND TRANSPORTATION (JUNE 1999)............21

19. OCEAN SHIPMENT OF GOODS (JUNE 1999)................................23

20. LOCAL PROCUREMENT (April 1998).....................................25

21. VOLUNTARY POPULATION PLANNING ACTIVITIES – MANDATORY REQUIREMENTS (MAY 2006) 26

II. REQUIRED AS APPLICABLE STANDARD PROVISIONS FOR U.S., NONGOVERNMENTAL RECIPIENTS.................................................................30

1. NEGOTIATED INDIRECT COST RATES - PREDETERMINED (April 1998)..........30

2. NEGOTIATED INDIRECT COST RATES - PROVISIONAL (Nonprofit) (April 1998)31

3. NEGOTIATED INDIRECT COST RATE - PROVISIONAL (Profit) (April 1998)....32

4. PUBLICATIONS AND MEDIA RELEASES (MARCH 2006).........................33

5. PARTICIPANT TRAINING (April 1998)....................................34

6. VOLUNTARY POPULATION PLANNING ACTIVITIES – SUPPLEMENTAL REQUIREMENTS (MAY 2006)...............................................................34

7. PROTECTION OF THE INDIVIDUAL AS A RESEARCH SUBJECT (April 1998)......50

8. CARE OF LABORATORY ANIMALS (MARCH 2004)..............................51

9. TITLE TO AND CARE OF PROPERTY (COOPERATING COUNTRY TITLE) (NOVEMBER 1985)....................................................................52

10. PUBLIC NOTICES (MARCH 2004)........................................56

11. (RESERVED).........................................................57

*12. COST SHARING (MATCHING) (July 2002)................................57

13. PROHIBITION OF ASSISTANCE TO DRUG TRAFFICKERS (JUNE 1999)..........57

*14. INVESTMENT PROMOTION (NOVEMBER 2003)...............................58

*15. REPORTING OF FOREIGN TAXES (March 2006)............................59

*16. FOREIGN GOVERNMENT DELEGATIONS TO INTERNATIONAL CONFERENCES (January 2002) 60

17. ORGANIZATIONS ELIGIBLE FOR ASSISTANCE (JULY 2004)..................61

18. PROHIBITION ON THE USE OF FEDERAL FUNDS TO PROMOTE, SUPPORT, OR ADVOCATE FOR THE LEGALIZATION OR PRACTICE OF PROSTITUTION - ASSISTANCE (JULY 2004) 61

*19. ORGANIZATIONS ELIGIBLE FOR ASSISTANCE (JUNE 2005)..................63

*20. CONDOMS (JUNE 2005)................................................63

*21. PROHIBITION ON THE PROMOTION OR ADVOCACY OF THE LEGALIZATION OR PRACTICE OF PROSTITUTION OR SEX TRAFFICKING (JUNE 2005)..................64

22. USAID DISABILITY POLICY - ASSISTANCE (DECEMBER 2004)...............65

23. STANDARDS FOR ACCESSIBILITY FOR THE DISABLED IN USAID ASSISTANCE

*An asterisk indicates that the adjacent information is new or substantively revised. 2

I. MANDATORY STANDARD PROVISIONS FOR U.S. NONGOVERNMENTAL RECIPIENTS

1. APPLICABILITY OF 22 CFR PART 226 (May 2005)

a. All provisions of 22 CFR Part 226 and all Standard Provisions attached to this agreement are applicable to the recipient and to subrecipients which meet the definition of "Recipient" in Part 226, unless a section specifically excludes a subrecipient from coverage. The recipient shall assure that subrecipients have copies of all the attached standard provisions.

b. For any subawards made with Non-US subrecipients the Recipient shall include the applicable "Standard Provisions for Non-US Nongovernmental Grantees." Recipients are required to ensure compliance with monitoring procedures in accordance with OMB Circular A-133.

[END OF PROVISION]

2. INELIGIBLE COUNTRIES (MAY 1986)

Unless otherwise approved by the USAID Agreement Officer, funds will only be expended for assistance to countries eligible for assistance under the Foreign Assistance Act of 1961, as amended, or under acts appropriating funds for foreign assistance.

[END OF PROVISION]

3. NONDISCRIMINATION (MAY 1986)

(This provision is applicable when work under the grant is performed in the U.S. or when employees are recruited in the U.S.)

No U.S. citizen or legal resident shall be excluded from participation in, be denied the benefits of, or be otherwise subjected to discrimination under any program or activity funded by this award on the basis of race, color, national origin, age, handicap, or sex.

[END OF PROVISION]

*An asterisk indicates that the adjacent information is new or substantively revised. 4

4. NONLIABILITY (NOVEMBER 1985)

USAID does not assume liability for any third party claims for damages arising out of this award.

[END OF PROVISION]

5. AMENDMENT (NOVEMBER 1985)

The award may be amended by formal modifications to the basic award document or by means of an exchange of letters between the Agreement Officer and an appropriate official of the recipient.

[END OF PROVISION]

6. NOTICES (NOVEMBER 1985)

Any notice given by USAID or the recipient shall be sufficient only if in writing and delivered in person, mailed, or cabled as follows:

To the USAID Agreement Officer, at the address specified in the award.

To recipient, at recipient's address shown in the award or to such other address designated within the award

Notices shall be effective when delivered in accordance with this provision, or on the effective date of the notice, whichever is later.

[END OF PROVISION]

7. SUBAGREEMENTS (June 1999)

Subrecipients, subawardees, and contractors have no relationship with USAID under the terms of this agreement. All required USAID approvals must be directed through the recipient to USAID.

[END OF PROVISION]

8. OMB APPROVAL UNDER THE PAPERWORK REDUCTION ACT (December 2003)

*Information collection requirements imposed by this grant are covered by OMB approval number 0412-0510; the current expiration date is 04/30/2005. The Standard Provisions containing the requirement and an estimate of the public reporting burden (including time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information) are

Standard Provision Burden Estimate

Air Travel and Transportation 1 (hour)

Ocean Shipment of Goods .5

Patent Rights .5

Publications .5

Negotiated Indirect Cost Rates -

(Predetermined and Provisional) 1

Voluntary Population Planning .5

Protection of the Individual as a 1

Research Subject

22 CFR 226 Burden Estimate

22 CFR 226.40-.49 Procurement

of Goods and Services 1

22 CFR 226.30 - .36

Property Standards 1.5

Comments regarding this burden estimate or any other aspect of this collection of information, including suggestions for reducing this burden, may be sent to the Office of Procurement, Policy Division (M/OP/P) U.S. Agency for International Development, Washington, DC 20523-7801 and to the Office of Management and Budget, Paperwork Reduction Project (0412-0510), Washington, D.C 20503.

[END OF PROVISION]

9. USAID ELIGIBILITY RULES FOR GOODS AND SERVICES (April 1998)

(This provision is not applicable to goods or services which the recipient provides with private funds as part of a cost-sharing requirement, or with Program Income generated under the award.)

a. Ineligible and Restricted Goods and Services: USAID's policy on ineligible and restricted goods and services is contained in ADS Chapter 312.

(1) Ineligible Goods and Services. Under no circumstances shall the recipient procure any of the following under this award:

(i) Military equipment,

(ii) Surveillance equipment,

(iii) Commodities and services for support of police or other law enforcement activities,

(iv) Abortion equipment and services,

(v) Luxury goods and gambling equipment, or

(vi) Weather modification equipment.

(2) Ineligible Suppliers. Funds provided under this award shall not be used to procure any goods or services furnished by any firms or individuals whose name appears on the "Lists of Parties Excluded from Federal Procurement and Nonprocurement Programs." USAID will provide the recipient with a copy of these lists upon request.

(3) Restricted Goods. The recipient shall not procure any of the following goods and services without the prior approval of the Agreement Officer:

(i) Agricultural commodities,

(ii) Motor vehicles,

(iii) Pharmaceuticals,

(iv) Pesticides,

(v) Used equipment,

(vi) U.S. Government-owned excess property, or

(vii) Fertilizer.

Prior approval will be deemed to have been met when:

(i) the item is of U.S. source/origin;

(ii) the item has been identified and incorporated in the program description or schedule of the award (initial or revisions), or amendments to the award; and

(iii) the costs related to the item are incorporated in the approved budget of the award.

Where the item has not been incorporated into the award as described above, a separate written authorization from the Agreement Officer must be provided before the item is procured.

*An asterisk indicates that the adjacent informa

Source and Nationality: The eligibility rules for goods and services based on source and nationality are divided into two categories. One applies when the total procurement element during the life of the award is over $250,000, and the other applies when the total procurement element during the life of the award is not over $250,000, or the award is funded under the Development Fund for Africa (DFA) regardless of the amount. The total procurement element includes procurement of all goods (e.g., equipment, materials, supplies) and services. Guidance on the eligibility of specific goods or services may be obtained from the Agreement Officer. USAID policies and definitions on source, origin and nationality are contained in 22 CFR Part 228, Rules on Source, Origin and Nationality for Commodities and Services Financed by the Agency for International Development, which is incorporated into this Award in its entirety.

(1) For DFA funded awards or when the total procurement element during the life of this award is valued at $250,000 or less, the following rules apply:

(i) The authorized source for procurement of all goods and services to be reimbursed under the award is USAID Geographic Code 935, "Special Free World," and such goods and services must meet the source, origin and nationality requirements set forth in 22 CFR Part 228 in accordance with the following order of preference:

(A) The United States (USAID Geographic Code 000),

(B) The Cooperating Country,

(C) USAID Geographic Code 941, and

(D) USAID Geographic Code 935.

(ii) Application of order of preference: When the recipient procures goods and services from other than U.S. sources, under the order of preference in paragraph (b)(1)(i) above, the recipient shall document its files to justify each such instance. The documentation shall set forth the circumstances surrounding the procurement and shall be based on one or more of the following reasons, which will be set forth in the grantee's documentation:

(A) The procurement was of an emergency nature, which would not allow for the delay attendant to soliciting U.S. sources,

(B) The price differential for procurement from U.S. sources exceeded by 50% or more the delivered price from the non-U.S. source,

(C) Compelling local political considerations precluded consideration of U.S. sources,

(D) The goods or services were not available from U.S. sources, or

(E) Procurement of locally available goods and services, as opposed to procurement of U.S. goods and services, would best promote the objectives of the Foreign Assistance program under the award.

(2) When the total procurement element exceeds $250,000 (unless funded by DFA), the following applies: Except as may be specifically approved or directed in advance by the Agreement Officer, all goods and services financed with U.S. dollars, which will be reimbursed under this award must meet the source, origin and nationality requirements set forth in 22 CFR Part 228 for the authorized geographic code specified in the schedule of this award. If none is specified, the authorized source is Code 000, the United States.

c. Printed or Audio-Visual Teaching Materials: If the effective use of printed or audio-visual teaching materials depends upon their being in the local language and if such materials are intended for technical assistance projects or activities financed by USAID in whole or in part and if other funds including U.S.-owned or U.S.-controlled local currencies are not readily available to finance the procurement of such materials, local language versions may be procured from the following sources, in order of preference:

(1) The United States (USAID Geographic Code 000),

(2) The Cooperating Country,

(3) "Selected Free World" countries (USAID Geographic

Code 941), and

(4) "Special Free World" countries (USAID Geographic

Code 899).

d. If USAID determines that the recipient has procured any of these goods or services under this award contrary to the requirements of this provision, and has received payment for such purposes, the Agreement Officer may require the recipient to refund the entire amount of the purchase.

This provision must be included in all subagreements which include procurement of goods or services which total over $5,000.

[END OF PROVISION]

*10. DEBARMENT, SUSPENSION, AND OTHER RESPONSIBILITY MATTERS (January 2004)

a. The recipient agrees to notify the Agreement Officer immediately upon learning that it or any of its principals:

(1) Are presently excluded or disqualified from covered transactions by any Federal department or agency;

(2) Have been convicted within the preceding three-year period preceding this proposal been convicted of or had a civil judgment rendered against them for commission of fraud or a criminal offense in connection with obtaining, attempting to obtain, or performing a public (Federal, State, or local) transaction or contract under a public transaction; violation of Federal or State antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification or destruction of records, making false statements, tax evasion, receiving stolen property, making false claims, or obstruction of justice; commission of any other offense indicating a lack of business integrity or business honesty that seriously and directly affects your present responsibility;

(3) Are presently indicted for or otherwise criminally or civilly charged by a governmental entity (Federal, State, or local) with commission of any of the offenses enumerated in paragraph (1)(b); and

(4) Have had one or more public transactions (Federal, State, or local) terminated for cause or default within the preceding three years.

b. The recipient agrees that, unless authorized by the Agreement Officer, it will not knowingly enter into any subagreements or contracts under this grant with a person or entity that is included on the Excluded Parties List System (http://epls.arnet.gov). The recipient further agrees to include the following provision in any subagreements or contracts entered into under this award:

DEBARMENT, SUSPENSION, INELIGIBILITY, AND VOLUNTARY EXCLUSION (DECEMBER 2003)

The recipient/contractor certifies that neither it nor its principals is presently excluded or disqualified from participation in this transaction by any Federal department or agency.

c. The policies and procedures applicable to debarment, suspension, and ineligibility under USAID-financed transactions are set forth in 22 CFR Part 208.

[END OF PROVISION]

*An asterisk indicates that the adjacent information is new or substantively revised. 10

*11. DRUG-FREE WORKPLACE (January 2004)

a. The recipient agrees that it will publish a drug-free workplace statement and provide a copy to each employee who will be engaged in the performance of any Federal award. The statement must

(1) Tell the employees that the unlawful manufacture, distribution, dispensing, possession, or use of a controlled substance is prohibited in its workplace;

(2) Specify the actions the recipient will take against employees for violating that prohibition; and

(3) Let each employee know that, as a condition of employment under any award, he or she

(i) Must abide by the terms of the statement, and

(ii) Must notify you in writing if he or she is convicted for a violation of a criminal drug statute occurring in the workplace, and must do so no more than five calendar days after the conviction.

b. The recipient agrees that it will establish an ongoing drug-free awareness program to inform employees about

(i) The dangers of drug abuse in the workplace;

(ii) Your policy of maintaining a drug-free workplace;

(iii) Any available drug counseling, rehabilitation and employee assistance programs; and

(iv) The penalties that you may impose upon them for drug abuse violations occurring in the workplace.

c. Without the Agreement Officer’s expressed written approval, the policy statement and program must be in place as soon as possible, no later than the 30 days after the effective date of this award or the completion date of this award, whichever occurs first.

d. The recipient agrees to immediately notify the Agreement Officer if an employee is convicted of a drug violation in the workplace. The notification must be in writing, identify the employee’s position title, the number of each award on which the employee worked. The notification must be sent to the Agreement Officer within ten calendar days after the recipient learns of the conviction.

e. Within 30 calendar days of learning about an employee’s conviction, the recipient must either

(1) Take appropriate personnel action against the employee, up to and including termination, consistent with the requirements of the Rehabilitation Act of 1973 (29 USC 794), as amended, or

(2) Require the employee to participate satisfactorily in a drug abuse assistance or rehabilitation program approved for these purposes by a Federal, State or local health, law enforcement, or other appropriate agency.

f. The policies and procedures applicable to violations of these requirements are set forth in 22 CFR Part 210.

[END OF PROVISION]

*An asterisk indicates that the adjacent information is new or substantively revised. 11

*12. EQUAL PROTECTION OF THE LAWS FOR FAITH-BASED AND COMMUNITY ORGANIZATIONS (February 2004)

a. The recipient may not discriminate against any beneficiary or potential beneficiary under this award on the basis of religion or religious belief. Accordingly, in providing services supported in whole or in part by this agreement or in its outreach activities related to such services, the recipient may not discriminate against current or prospective program beneficiaries on the basis of religion, a religious belief, a refusal to hold a religious belief, or a refusal to actively participate in a religious practice;

b. The Federal Government must implement Federal programs in accordance with the Establishment Clause and the Free Exercise Clause of the First Amendment to the Constitution. Therefore, if the recipient engages in inherently religious activities, such as worship, religious instruction, and proselytization, it must offer those services at a different time or location from any programs or services directly funded by this award, and participation by beneficiaries in any such inherently religious activities must be voluntary.

c. If the recipient makes subawards under this agreement, faith-based organizations should be eligible to participate on the same basis as other organizations, and should not be discriminated against on the basis of their religious character or affiliation.

[END OF PROVISION]

*13. IMPLEMENTATION OF E.O. 13224 -- EXECUTIVE ORDER ON TERRORIST FINANCING (March 2002)

The Recipient is reminded that U.S. Executive Orders and U.S. law prohibits transactions with, and the provision of resources and support to, individuals and organizations associated with terrorism. It is the legal responsibility of the recipient to ensure compliance with these Executive Orders and laws. This provision must be included in all contracts/subawards issued under this agreement.

[END OF PROVISION]

*14. MARKING UNDER USAID-FUNDED ASSISTANCE INSTRUMENTS (December 2005)

(a) Definitions

Commodities mean any material, article, supply, goods or equipment, excluding recipient offices, vehicles, and non-deliverable items for recipient’s internal use, in administration of the USAID funded grant, cooperative agreement, or other agreement or subagreement.

Principal Officer means the most senior officer in a USAID Operating Unit in the field, e.g., USAID Mission Director or USAID Representative. For global programs managed from Washington but executed across many countries, such as disaster relief and assistance to internally displaced persons, humanitarian emergencies or immediate post conflict and political crisis response, the cognizant Principal Officer may be an Office Director, for example, the Directors of USAID/W/Office of Foreign Disaster Assistance and Office of Transition Initiatives. For non-presence countries, the cognizant Principal Officer is the Senior USAID officer in a regional USAID Operating Unit responsible for the non-presence country, or in the absence of such a responsible operating unit, the Principal U.S Diplomatic Officer in the non-presence country exercising delegated authority from USAID.

Programs mean an organized set of activities and allocation of resources directed toward a common purpose, objective, or goal undertaken or proposed by an organization to carry out the responsibilities assigned to it.

Projects include all the marginal costs of inputs (including the proposed investment) technically required to produce a discrete marketable output or a desired result (for example, services from a fully functional water/sewage treatment facility).

Public communications are documents and messages intended for distribution to audiences external to the recipient’s organization. They include, but are not limited to, correspondence, publications, studies, reports, audio visual productions, and other informational products; applications, forms, press and promotional materials used in connection with USAID funded programs, projects or activities, including signage and plaques; Web sites/Internet activities; and events such as training courses, conferences, seminars, press conferences and so forth.

Subrecipient means any person or government (including cooperating country government) department, agency, establishment, or for profit or nonprofit organization that receives a USAID subaward, as defined in 22 C.F.R. 226.2.

Technical Assistance means the provision of funds, goods, services, or other foreign assistance, such as loan guarantees or food for work, to developing countries and other USAID recipients, and through such recipients to subrecipients, in direct support of a development objective – as opposed to the internal management of the foreign assistance program.

USAID Identity (Identity) means the official marking for the United States Agency for International Development (USAID), comprised of the USAID logo or seal and new brandmark, with the tagline that clearly communicates that our assistance is “from the American people.” The USAID Identity is available on the USAID website at www.usaid.gov/branding and USAID provides it without royalty, license, or other fee to recipients of USAID-funded grants, or cooperative agreements, or other assistance awards

(b) Marking of Program Deliverables

(1) All recipients must mark appropriately all overseas programs, projects, activities, public communications, and commodities partially or fully funded by a USAID grant or cooperative agreement or other assistance award or subaward with the USAID Identity, of a size and prominence equivalent to or greater than the recipient’s, other donor’s, or any other third party’s identity or logo.

(2) The Recipient will mark all program, project, or activity sites funded by USAID, including visible infrastructure projects (for example, roads, bridges, buildings) or other programs, projects, or activities that are physical in nature (for example, agriculture, forestry, water management) with the USAID Identity. The Recipient should erect temporary signs or plaques early in the construction or implementation phase. When construction or implementation is complete, the Recipient must install a permanent, durable sign, plaque or other marking.

(3) The Recipient will mark technical assistance, studies, reports, papers, publications, audio-visual productions, public service announcements, Web sites/Internet activities and other promotional, informational, media, or communications products funded by USAID with the USAID Identity.

(4) The Recipient will appropriately mark events financed by USAID, such as training courses, conferences, seminars, exhibitions, fairs, workshops, press conferences and other public activities, with the USAID Identity. Unless directly prohibited and as appropriate to the surroundings, recipients should display additional materials, such as signs and banners, with the USAID Identity. In circumstances in which the USAID Identity cannot be displayed visually, the recipient is encouraged otherwise to acknowledge USAID and the American people’s support.

(5) The Recipient will mark all commodities financed by USAID, including commodities or equipment provided under humanitarian assistance or disaster relief programs, and all other equipment, supplies, and other materials funded by USAID, and their export packaging with the USAID Identity.

(6) The Agreement Officer may require the USAID Identity to be larger and more prominent if it is the majority donor, or to require that a cooperating country government’s identity be larger and more prominent if circumstances warrant, and as appropriate depending on the audience, program goals, and materials produced.

(7) The Agreement Officer may require marking with the USAID Identity in the event that the recipient does not choose to mark with its own identity or logo.

(8) The Agreement Officer may require a pre-production review of USAID-funded public communications and program materials for compliance with the approved Marking Plan.

(9) Subrecipients. To ensure that the marking requirements “flow down'' to subrecipients of subawards, recipients of USAID funded grants and cooperative agreements or other assistance awards will include the USAID-approved marking provision in any USAID funded subaward, as follows:

“As a condition of receipt of this subaward, marking with the USAID Identity of a size and prominence equivalent to or greater than the recipient’s, subrecipient’s, other donor’s or third party’s is required. In the event the recipient chooses not to require marking with its own identity or logo by the subrecipient, USAID may, at its discretion, require marking by the subrecipient with the USAID Identity.”

(10) Any ‘public communications’, as defined in 22 C.F.R. 226.2, funded by USAID, in which the content has not been approved by USAID, must contain the following disclaimer:

“This study/report/audio/visual/other information/media product (specify) is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The contents are the responsibility of [insert recipient name] and do not necessarily reflect the views of USAID or the United States Government.”

(11) The recipient will provide the Cognizant Technical Officer (CTO) or other USAID personnel designated in the grant or cooperative agreement with two copies of all program and communications materials produced under the award. In addition, the recipient will submit one electronic or one hard copy of all final documents to USAID’s Development Experience Clearinghouse.

(c) Implementation of marking requirements.

(1) When the grant or cooperative agreement contains an approved Marking Plan, the recipient will implement the requirements of this provision following the approved Marking Plan.

(2) When the grant or cooperative agreement does not contain an approved Marking Plan, the recipient will propose and submit a plan for implementing the requirements of this provision within [Agreement Officer fill-in] days after the effective date of this provision. The plan will include:

(i) A description of the program deliverables specified in paragraph (b) of this provision that the recipient will produce as a part of the grant or cooperative agreement and which will visibly bear the USAID Identity.

(ii) the type of marking and what materials the applicant uses to mark the program deliverables with the USAID Identity,

(iii) when in the performance period the applicant will mark the program deliverables, and where the applicant will place the marking,

(3) The recipient may request program deliverables not be marked with the USAID Identity by identifying the program deliverables and providing a rationale for not marking these program deliverables. Program deliverables may be exempted from USAID marking requirements when:

(i) USAID marking requirements would compromise the intrinsic independence or neutrality of a program or materials where independence or neutrality is an inherent aspect of the program and materials;

(ii) USAID marking requirements would diminish the credibility of audits, reports, analyses, studies, or policy recommendations whose data or findings must be seen as independent;

(iii) USAID marking requirements would undercut host-country government “ownership” of constitutions, laws, regulations, policies, studies, assessments, reports, publications, surveys or audits, public service announcements, or other communications better positioned as “by” or “from” a cooperating country ministry or government official;

(iv) USAID marking requirements would impair the functionality of an item;

(v) USAID marking requirements would incur substantial costs or be impractical;

(vi) USAID marking requirements would offend local cultural or social norms, or be considered inappropriate;

(vii) USAID marking requirements would conflict with international law.

(4) The proposed plan for implementing the requirements of this provision, including any proposed exemptions, will be negotiated within the time specified by the Agreement Officer after receipt of the proposed plan. Failure to negotiate an approved plan with the time specified by the Agreement Officer may be considered as noncompliance with the requirements is provision.

(d) Waivers.

(1) The recipient may request a waiver of the Marking Plan or of the marking requirements of this provision, in whole or in part, for each program, project, activity, public communication or commodity, or, in exceptional circumstances, for a region or country, when USAID required marking would pose compelling political, safety, or security concerns, or when marking would have an adverse impact in the cooperating country. The recipient will submit the request through the Cognizant Technical Officer. The Principal Officer is responsible for approvals or disapprovals of waiver requests.

(2) The request will describe the compelling political, safety, security concerns, or adverse impact that require a waiver, detail the circumstances and rationale for the waiver, detail the specific requirements to be waived, the specific portion of the Marking Plan to be waived, or specific marking to be waived, and include a description of how program materials will be marked (if at all) if the USAID Identity is removed. The request should also provide a rationale for any use of recipient’s own identity/logo or that of a third party on materials that will be subject to the waiver.

(3) Approved waivers are not limited in duration but are subject to Principal Officer review at any time, due to changed circumstances.

(4) Approved waivers “flow down” to recipients of subawards unless specified otherwise. The waiver may also include the removal of USAID markings already affixed, if circumstances warrant.

(5) Determinations regarding waiver requests are subject to appeal to the Principal Officer’s cognizant Assistant Administrator. The recipient may appeal by submitting a written request to reconsider the Principal Officer’s waiver determination to the cognizant Assistant Administrator.

(e) Non-retroactivity. The requirements of this provision do not apply to any materials, events, or commodities produced prior to January 2, 2006. The requirements of this provision do not apply to program, project, or activity sites funded by USAID, including visible infrastructure projects (for example, roads, bridges, buildings) or other programs, projects, or activities that are physical in nature (for example, agriculture, forestry, water management) where the construction and implementation of these are complete prior to January 2, 2006 and the period of the grant does not extend past January 2, 2006.

*An asterisk indicates that the adjacent information is new or substantively revised.

[END OF PROVISION]

15. REGULATIONS GOVERNING EMPLOYEES (AUGUST 1992)

(The following applies to the recipient's employees working in the cooperating country under the agreement who are not citizens of the cooperating country.)

a. The recipient's employees shall maintain private status and may not rely on local U.S. Government offices or facilities for support while under this grant.

b. The sale of personal property or automobiles by recipient employees and their dependents in the foreign country to which they are assigned shall be subject to the same limitations and prohibitions which apply to direct-hire USAID personnel employed by the Mission, including the rules contained in 22 CFR Part 136, except as this may conflict with host government regulations.

c. Other than work to be performed under this award for which an employee is assigned by the recipient, no employee of the recipient shall engage directly or indirectly, either in the individual's own name or in the name or through an agency of another person, in any business, profession, or occupation in the foreign countries to which the individual is assigned, nor shall the individual make loans or investments to or in any business, profession or occupation in the foreign countries to which the individual is assigned.

d. The recipient's employees, while in a foreign country, are expected to show respect for its conventions, customs, and institutions, to abide by its applicable laws and regulations, and not to interfere in its internal political affairs.

e. In the event the conduct of any recipient employee is not in accordance with the preceding paragraphs, the recipient's chief of party shall consult with the USAID Mission Director and the employee involved and shall recommend to the recipient a course of action with regard to such employee.

f. The parties recognize the rights of the U.S. Ambassador to direct the removal from a country of any U.S. citizen or the discharge from this grant award of any third country national when, in the discretion of the Ambassador, the interests of the United States so require.

g. If it is determined, either under (e) or (f) above, that the services of such employee should be terminated, the recipient shall use its best efforts to cause the return of such employee to the United States, or point of origin, as appropriate.

[END OF PROVISION]

16. CONVERSION OF UNITED STATES DOLLARS TO LOCAL CURRENCY (NOVEMBER 1985)

(This provision applies when activities are undertaken outside the United States.)

Upon arrival in the Cooperating Country, and from time to time as appropriate, the recipient's chief of party shall consult with the Mission Director who shall provide, in writing, the procedure the recipient and its employees shall follow in the conversion of United States dollars to local currency. This may include, but is not limited to, the conversion of currency through the cognizant United States Disbursing Officer or Mission Controller, as appropriate.

[END OF PROVISION]

17. USE OF POUCH FACILITIES (AUGUST 1992)

(This provision applies when activities are undertaken outside the United States.)

a. Use of diplomatic pouch is controlled by the Department of State. The Department of State has authorized the use of pouch facilities for USAID recipients and their employees as a general policy, as detailed in items (1) through (6) below. However, the final decision regarding use of pouch facilities rest with the Embassy or USAID Mission. In consideration of the use of pouch facilities, the recipient and its employees agree to indemnify and hold harmless, the Department of State and USAID for loss or damage occurring in pouch transmission:

(1) Recipients and their employees are authorized use of the pouch for transmission and receipt of up to a maximum of .9 kgs per shipment of correspondence and documents needed in the administration of assistance programs.

(2) U.S. citizen employees are authorized use of the pouch for personal mail up to a maximum of .45 kgs per shipment (but see (a)(3) below).

(3) Merchandise, parcels, magazines, or newspapers are not considered to be personal mail for purposes of this standard provision and are not authorized to be sent or received by pouch.

(4) Official and personal mail pursuant to a.1. and 2. above sent by pouch should be addressed as follows:

Name of individual or organization (followed by

letter symbol "G")

City Name of post (USAID/______)

Agency for International Development

Washington, D.C. 20523-0001

(5) Mail sent via the diplomatic pouch may not be in violation of U.S. Postal laws and may not contain material ineligible for pouch transmission.

(6) Recipient personnel are NOT authorized use of military postal facilities (APO/FPO). This is an Adjutant General's decision based on existing laws and regulations governing military postal facilities and is being enforced worldwide.

b. The recipient shall be responsible for advising its employees of this authorization, these guidelines, and limitations on use of pouch facilities. c. Specific additional guidance on grantee use of pouch facilities in accordance with this standard provision is available from the Post Communication Center at the Embassy or USAID Mission.

[END OF PROVISION]

*An asterisk indicates that the adjacent information is new or substantively revised.

18. INTERNATIONAL AIR TRAVEL AND TRANSPORTATION (JUNE 1999)

(This provision is applicable when costs for international travel or transportation will be paid for with USAID funds. This provision is not applicable if the recipient is providing for travel with private funds as part of a cost-sharing requirement, or with Program Income generated under the award.)

a. PRIOR BUDGET APPROVAL

In accordance with OMB Cost Principles, direct charges for foreign travel costs are allowable only when each foreign trip has received prior budget approval. Such approval will be deemed to have been met when:

(1) the trip is identified. Identification is accomplished by providing the following information: the number of trips, the number of individuals per trip, and the destination country(s).

(2) the information noted at (a)(1) above is incorporated in: the proposal, the program description or schedule of the award, the implementation plan (initial or revisions), or amendments to the award; and

(3) the costs related to the travel are incorporated in the approved budget of the award.

The Agreement Officer may approve travel which has not been incorporated in writing as required by paragraph (a)(2). In such case, a copy of the Agreement Officer's approval must be included in the agreement file.

b. NOTIFICATION

(1) As long as prior budget approval has been met in accordance with paragraph (a) above, a separate Notification will not be necessary unless:

(i) the primary purpose of the trip is to work with USAID Mission personnel, or

(ii) the recipient expects significant administrative or substantive programmatic support from the Mission.

Neither the USAID Mission nor the Embassy will require Country Clearance of employees or contractors of USAID Recipients.

(2) Where notification is required in accordance with paragraph (1)(i) or (ii) above, the recipient will observe the following standards:

(i) Send a written notice to the cognizant USAID Technical Office in the Mission. If the recipient's primary point of contact is a Technical Officer in USAID/W, the recipient may send the notice to that person. It will be the responsibility of the USAID/W Technical Officer to forward the notice to the field.

(ii) The notice should be sent as far in advance as possible, but at least 14 calendar days in advance of the proposed travel. This notice may be sent by fax or e-mail. The recipient should retain proof that notification was made.

(iii) The notification shall contain the following information: the award number, the cognizant Technical Officer, the traveler's name (if known), date of arrival, and the purpose of the trip.

(iv) The USAID Mission will respond only if travel has been denied. It will be the responsibility of the Technical Officer in the Mission to contact the recipient within 5 working days of having received the notice if the travel is denied. If the recipient has not received a response within the time frame, the recipient will be considered to have met these standards for notification, and may travel.

(v) If a subrecipient is required to issue a Notification, as per this section, the subrecipient may contact the USAID Technical Officer directly, or the prime may contact USAID on the subrecipient's behalf.

c. SECURITY ISSUES

Recipients are encouraged to obtain the latest Department of State Travel Advisory Notices before travelling. These Notices are available to the general public and may be obtained directly from the State Department, or via Internet.

Where security is a concern in a specific region, recipients may choose to notify the US Embassy of their presence when they have entered the country. This may be especially important for long-term posting.

d. USE OF U.S.-OWNED LOCAL CURRENCY

Travel to certain countries shall, at USAID's option, be funded from U.S.-owned local currency. When USAID intends to exercise this option, USAID will either issue a U.S. Government S.F. 1169, Transportation Request (GTR) which the grantee may exchange for tickets, or issue the tickets directly. Use of such U.S.-owned currencies will constitute a dollar charge to this grant.

e. THE FLY AMERICA ACT

The Fly America Act (49 U.S.C. 40118) requires that all air travel and shipments under this award must be made on U.S. flag air carriers to the extent service by such carriers is available. The Administrator of General Services Administration (GSA) is authorized to issue regulations for purposes of implementation. Those regulations may be found at 41 CFR part 301, and are hereby incorporated by reference into this award.

f. COST PRINCIPLES

The recipient will be reimbursed for travel and the reasonable cost of subsistence, post differentials and other allowances paid to employees in international travel status in accordance with the recipient's applicable cost principles and established policies and practices which are uniformly applied to federally financed and other activities of the grantee.

If the recipient does not have written established policies regarding travel costs, the standard for determining the reasonableness of reimbursement for overseas allowance will be the Standardized Regulations (Government Civilians, Foreign Areas), published by the U.S. Department of State, as from time to time amended. The most current subsistence, post differentials, and other allowances may be obtained from the Agreement Officer.

g. SUBAWARDS.

This provision will be included in all subawards and contracts which require international air travel and transportation under this award.

[END OF PROVISION]

19. OCEAN SHIPMENT OF GOODS (JUNE 1999)

(This provision is applicable for awards and subawards for $100,000 or more and when goods purchased with funds provided under this award are transported to cooperating countries on ocean vessels whether or not award funds are used for the transportation.)

*An asterisk indicates that the adjacent information is new or substantively revised.

a. At least 50% of the gross tonnage of all goods purchased under this agreement and transported to the cooperating countries shall be made on privately owned U.S. flag commercial ocean vessels, to the extent such vessels are available at fair and reasonable rates for such vessels.

b. At least 50% of the gross freight revenue generated by shipments of goods purchased under this agreement and transported to the cooperating countries on dry cargo liners shall be paid to or for the benefit of privately owned U.S. flag commercial ocean vessels to the extent such vessels are available at fair and reasonable rates for such vessels.

c. When U.S. flag vessels are not available, or their use would result in a significant delay, the grantee may request a determination of non-availability from the USAID Transportation Division, Office of Procurement, Washington, D.C. 20523, giving the basis for the request which will relieve the grantee of the requirement to use U.S. flag vessels for the amount of tonnage included in the determination. Shipments made on non-free world ocean vessels are not reimbursable under this grant.

d. The recipient shall send a copy of each ocean bill of lading, stating all of the carrier's charges including the basis for calculation such as weight or cubic measurement, covering a shipment under this agreement to:

U.S. Department of Transportation,

Maritime Administration, Division of National Cargo,

400 7th Street, S.W.,

Washington, DC 20590, and

U.S. Agency for International Development,

Office of Procurement, Transportation Division

1300 Pennsylvania Avenue, N.W.

Washington, DC 20523-7900

e. Shipments by voluntary nonprofit relief agencies (i.e., PVOs) shall be governed by this standard provision and by USAID Regulation 2, "Overseas Shipments of Supplies by Voluntary Nonprofit Relief Agencies" (22 CFR Part 202).

f. Shipments financed under this grant must meet applicable eligibility requirements set out in 22 CFR 228.21.

[END OF PROVISION]

20. LOCAL PROCUREMENT (April 1998)

(This provision applies when activities are undertaken outside the United States.)

a. Financing local procurement involves the use of appropriated funds to finance the procurement of goods and services supplied by local businesses, dealers or producers, with payment normally being in the currency of the cooperating country.

b. Locally financed procurements must be covered by source and nationality waivers as set forth in 22 CFR 228, Subpart F, except as provided for in mandatory standard provision, "USAID Eligibility Rules for Goods and Services," or when one of the following exceptions applies:

(1) Locally available commodities of U.S. origin, which are otherwise eligible for financing, if the value of the transaction is estimated not to exceed $100,000 exclusive of transportation costs.

(2) Commodities of geographic code 935 origin if the value of the transaction does not exceed the local currency equivalent of $5,000.

(3) Professional Services Contracts estimated not to exceed $250,000.

(4) Construction Services Contracts estimated not to exceed $5,000,000.

(5) Commodities and services available only in the local economy (no specific per transaction value applies to this category). This category includes the following items:

(i) Utilities including fuel for heating and cooking, waste disposal and trash collection;

(ii) Communications - telephone, telex, fax, postal and courier services;

(iii) Rental costs for housing and office space;

(iv) Petroleum, oils and lubricants for operating vehicles and equipment;

(v) Newspapers, periodicals and books published in the cooperating country;

(vi) Other commodities and services and related expenses that, by their

nature or as a practical matter, can only be acquired, performed, or incurred in the cooperating country, e.g., vehicle maintenance, hotel accommodations, etc.

c. The coverage on ineligible and restricted goods and services in the mandatory standard provision entitled, "USAID Eligibility Rules for Goods and Services," also apply to local procurement.

d. This provision will be included in all subagreements where local procurement of goods or services is a supported element.

[END OF PROVISION]

21. VOLUNTARY POPULATION PLANNING ACTIVITIES – MANDATORY REQUIREMENTS (MAY 2006)

Requirements for Voluntary Sterilization Programs

(1) None of the funds made available under this award shall be used to pay for the performance of involuntary sterilization as a method of family planning or to coerce or provide any financial incentive to any individual to practice sterilization.

Prohibition on Abortion-Related Activities:

(1) No funds made available under this award will be used to finance, support, or be attributed to the following activities: (i) procurement or distribution of equipment intended to be used for the purpose of inducing abortions as a method of family planning; (ii) special fees or incentives to any person to coerce or motivate them to have abortions; (iii) payments to persons to perform abortions or to solicit persons to undergo abortions; (iv) information, education, training, or communication programs that seek to promote abortion as a method of family planning; and (v) lobbying for or against abortion. The term “motivate”, as it relates to family planning assistance, shall not be construed to prohibit the provision, consistent with local law, of information or counseling about all pregnancy options.

(2) No funds made available under this award will be used to pay for any biomedical research which relates, in whole or in part, to methods of, or the performance of, abortions or involuntary sterilizations as a means of family planning. Epidemiologic or descriptive research to assess the incidence, extent or consequences of abortions is not precluded.

[END OF PROVISION]

ATTACHMENT 1:  AAPD 05-11 Marking under Assistance Instruments

I. BRANDING STRATEGY - ASSISTANCE (December 2005)

(a) Definitions

Branding Strategy means a strategy that is submitted at the specific request of a USAID Agreement Officer by an Apparently Successful Applicant after evaluation of an application for USAID funding, describing how the program, project, or activity is named and positioned, and how it is promoted and communicated to beneficiaries and host country citizens. It identifies all donors and explains how they will be acknowledged.

Apparently Successful Applicant(s) means the applicant(s) for USAID funding recommended for an award after evaluation, but who has not yet been awarded a grant, cooperative agreement or other assistance award by the Agreement Officer. The Agreement Officer will request that the Apparently Successful Applicants submit a Branding Strategy and Marking Plan. Apparently Successful Applicant status confers no right and constitutes no USAID commitment to an award.

USAID Identity (Identity) means the official marking for the Agency, comprised of the USAID logo and new brandmark, which clearly communicates that our assistance is from the American people. The USAID Identity is available on the USAID website and is provided without royalty, license, or

other fee to recipients of USAID-funded grants or cooperative agreements or other assistance awards or subawards.

(b) Submission.

The Apparently Successful Applicant, upon request of the Agreement Officer, will submit and negotiate a Branding Strategy. The Branding Strategy will be included in and made a part of the resulting grant or cooperative agreement. The Branding Strategy will be negotiated within the time that the Agreement Officer specifies. Failure to submit and negotiate a Branding Strategy will make the applicant ineligible for award of a grant or cooperative agreement. The Apparently Successful Applicant must include all estimated costs associated with branding and marking USAID programs, such as plaques, stickers, banners, press events and

materials, and the like.

(c) Submission Requirements

At a minimum, the Apparently Successful Applicant’s Branding Strategy will address the following:

(1) Positioning

What is the intended name of this program, project, or activity?

Guidelines: USAID prefers to have the USAID Identity included as part of the program or project name, such as a "title sponsor," if possible and appropriate. It is acceptable to "co-brand" the title with USAID’s and the Apparently Successful Applicant’s identities. For example: "The USAID and [Apparently Successful Applicant] Health Center."

If it would be inappropriate or is not possible to "brand" the project this way, such as when rehabilitating a structure that already exists or if there are multiple donors, please explain and indicate how you intend to showcase USAID's involvement in publicizing the program or project. For example: School #123, rehabilitated by USAID and [Apparently Successful Applicant]/ [other donors]. Note: the Agency prefers "made possible by (or with) the generous support of the American People" next to the USAID Identity in acknowledging our contribution, instead of the phrase "funded by." USAID prefers local language translations.

Will a program logo be developed and used consistently to identify this program? If yes, please attach a copy of the proposed program logo.

Note: USAID prefers to fund projects that do NOT have a separate logo or identity that competes with the USAID Identity.

(2) Program Communications and Publicity

Who are the primary and secondary audiences for this project or program?

Guidelines: Please include direct beneficiaries and any special target segments or influencers. For Example: Primary audience: schoolgirls age 8-12, Secondary audience: teachers and parents–specifically mothers.

What communications or program materials will be used to explain or market the program to beneficiaries?

Guidelines: These include training materials, posters, pamphlets, Public Service Announcements, billboards, websites, and so forth.

What is the main program message(s)?

Guidelines: For example: "Be tested for HIV-AIDS" or "Have your child inoculated." Please indicate if you also plan to incorporate USAID’s primary message – this aid is "from the American people" – into the narrative of program materials. This is optional; however, marking with the USAID Identity is required.

Will the recipient announce and promote publicly this program or project to host country citizens? If yes, what press and promotional activities are planned?

Guidelines: These may include media releases, press conferences, public events, and so forth.

Note: incorporating the message, “USAID from the American People”, and the USAID Identity is required.

Please provide any additional ideas about how to increase awareness that the American people support this project or program.

Guidelines: One of our goals is to ensure that both beneficiaries and host-country citizens know that the aid the Agency is providing is "from the American people." Please provide any initial ideas on how to further this goal.

(3) Acknowledgements

Will there be any direct involvement from a host-country government ministry? If yes, please indicate which one or ones. Will the recipient acknowledge the ministry as an additional co-sponsor?

Note: it is perfectly acceptable and often encouraged for USAID to "co-brand" programs with government ministries.

Please indicate if there are any other groups whose logo or identity the recipient will use on program materials and related communications.

Guidelines: Please indicate if they are also a donor or why they will be visibly acknowledged, and if they will receive the same prominence as USAID.

(d) Award Criteria. The Agreement Officer will review the Branding Strategy for adequacy, ensuring that it contains the required information on naming and positioning the USAID-funded program, project, or activity, and promoting and communicating it to cooperating country beneficiaries and citizens. The Agreement Officer also will evaluate this information to ensure that it is consistent with the stated objectives of the award; with the Apparently Successful Applicant’s cost data submissions; with the Apparently Successful Applicant’s project, activity, or program performance plan; and with the regulatory requirements set out in 22 CFR 226.91. The Agreement Officer may obtain advice and from technical experts while performing the evaluation.

II. MARKING PLAN – ASSISTANCE (December 2005)

(a)Definitions

Marking Plan means a plan that the Apparently Successful Applicant submits at the specific request of a USAID Agreement Officer after evaluation of an application for USAID funding, detailing the public communications, commodities, and program materials and other items that will visibly bear the USAID Identity. Recipients may request approval of Presumptive Exceptions to marking requirements in the Marking Plan.

Apparently Successful Applicant(s) means the applicant(s) for USAID funding recommended for an award after evaluation, but who has not yet been awarded a grant, cooperative agreement or other assistance award by the Agreement Officer. The Agreement Officer will request that Apparently Successful Applicants submit a Branding Strategy and Marking Plan. Apparently Successful Applicant status confers no right and constitutes no USAID commitment to an award, which the Agreement

Officer must still obligate.

USAID Identity (Identity) means the official marking for the Agency, comprised of the USAID logo and new brandmark, which clearly communicates that our assistance is from the American people. The USAID Identity is available on the USAID website and USAID provides it without royalty, license, or other fee to recipients of USAIDfunded grants, cooperative agreements, or other assistance awards or subawards.

A Presumptive Exception exempts the applicant from the general marking requirements for a particular USAID-funded public communication, commodity, program material or other deliverable, or a category of USAID-funded public communications, commodities, program materials or other deliverables that would otherwise be required to visibly bear the USAID Identity. The Presumptive Exceptions are: Presumptive Exception (i). USAID marking requirements may not apply if they would

compromise the intrinsic independence or neutrality of a program or materials where independence or neutrality is an inherent aspect of the program and materials, such as election monitoring or ballots, and voter information literature; political party support or public policy advocacy or reform; independent media, such as television and radio broadcasts, newspaper articles and editorials; and public service announcements or public opinion polls and surveys (22 C.F.R. 226.91(h)(1)).

Presumptive Exception (ii). USAID marking requirements may not apply if they would diminish the credibility of audits, reports, analyses, studies, or policy recommendations whose data or findings must be seen as independent (22 C.F.R. 226.91(h)(2)).

Presumptive Exception (iii). USAID marking requirements may not apply if they would undercut host-country government “ownership” of constitutions, laws, regulations, policies, studies, assessments, reports, publications, surveys or audits, public service announcements, or other communications better positioned as “by” or “from” a cooperating country ministry or government official (22 C.F.R. 226.91(h)(3)).

Presumptive Exception (iv). USAID marking requirements may not apply if they would impair the functionality of an item, such as sterilized equipment or spare parts (22 C.F.R. 226.91(h)(4)).

Presumptive Exception (v). USAID marking requirements may not apply if they would incur substantial costs or be impractical, such as items too small or otherwise unsuited for individual marking, such as food in bulk (22 C.F.R. 226.91(h)(5)).

Presumptive Exception (vi). USAID marking requirements may not apply if they would local cultural or social norms, or be considered inappropriate on such items as condoms, toilets, bed pans, or similar commodities (22 C.F.R. 226.91(h)(6)).

Presumptive Exception (vii). USAID marking requirements may not apply if they would conflict with international law (22 C.F.R. 226.91(h)(7)).

(b) Submission. The Apparently Successful Applicant, upon the request of the Agreement Officer, will submit and negotiate a Marking Plan that addresses the details of the public communications, commodities, program materials that will visibly bear the USAID Identity. The marking plan will be customized for the particular program, project, or activity under the resultant grant or cooperative agreement. The plan will be included in and made a part of the resulting grant or cooperative agreement. USAID and the Apparently Successful Applicant will negotiate the Marking Plan within the time specified by the Agreement Officer. Failure to submit and negotiate a Marking Plan will make the applicant ineligible for award of a grant or cooperative agreement. The applicant must include an estimate of all costs associated with branding and marking USAID programs, such as plaques, labels, banners, press events, promotional materials, and so forth in the budget portion of its application. These costs are subject to revision and negotiation with the Agreement Officer upon submission of the Marking Plan and will be incorporated into the Total Estimated Amount of the grant, cooperative agreement or other assistance instrument.

(c) Submission Requirements.

The Marking Plan will include the following:

(1) A description of the public communications, commodities, and program materials that the recipient will be produced as a part of the grant or cooperative agreement and which will visibly bear the USAID Identity. These include:

(i) program, project, or activity sites funded by USAID, including visible infrastructure projects or other programs, projects, or activities that are physical in nature;

(ii) technical assistance, studies, reports, papers, publications, audio-visual productions, public service announcements, Web sites/Internet activities and other promotional, informational, media, or communications products funded by USAID;

(iii) events financed by USAID, such as training courses, conferences, seminars, exhibitions, fairs, workshops, press conferences, and other public activities; and (iv) all commodities financed by USAID, including commodities or equipment provided under humanitarian assistance or disaster relief programs, and all other equipment, supplies and other materials funded by USAID, and their export packaging.

(2) A table specifying:

(i) the program deliverables that the recipient will mark with the USAID Identity,

(ii) the type of marking and what materials the applicant will be used to mark the program deliverables with the USAID Identity, and

(iii) when in the performance period the applicant will mark the program deliverables, and where the applicant will place the marking.

(3) A table specifying:

(i) what program deliverables will not be marked with the USAID Identity, and (ii) the rationale for not marking these program deliverables.

(d) Presumptive Exceptions.

(1) The Apparently Successful Applicant may request a Presumptive Exception as part of the overall Marking Plan submission. To request a Presumptive Exception, the Apparently Successful Applicant must identify which Presumptive Exception applies, and state why, in light of the Apparently Successful Applicant’s technical proposal and in the context of the program description or program statement in the USAID Request For Application or Annual Program Statement, marking requirements should not be required.

(2) Specific guidelines for addressing each Presumptive Exception are:

(i) For Presumptive Exception (i), identify the USAID Strategic Objective, Interim Result, or program goal furthered by an appearance of neutrality, or state why the program, project, activity, commodity, or communication is ‘intrinsically neutral.’ Identify, by category or deliverable item, examples of program materials funded under the award for which you are seeking exception 1.

(ii) For Presumptive Exception (ii), state what data, studies, or other deliverables will be produced under the USAID funded award, and explain why the data, studies, or deliverables must be seen as credible.

(iii) For Presumptive Exception (iii), identify the item or media product produced under the USAID funded award, and explain why each item or product, or category of item and product, is better positioned as an item or product produced by the cooperating country government.

(iv) For Presumptive Exception (iv), identify the item or commodity to be marked, or categories of items or commodities, and explain how marking would impair the item’s or commodity’s functionality.

(v) For Presumptive Exception (v), explain why marking would not be cost-beneficial or practical.

(vi) For Presumptive Exception (vi), identify the relevant cultural or social norm, and explain why marking would violate that norm or otherwise be inappropriate.

(vii) For Presumptive Exception (vii), identify the applicable international law violated by marking.

(3) The Agreement Officer will review the request for adequacy and reasonableness.

In consultation with the Cognizant Technical Officer and other agency personnel as necessary, the Agreement Officer will approve or disapprove the requested Presumptive Exception. Approved exceptions will be made part of the approved Marking Plan, and will apply for the term of the award, unless provided otherwise.

(e) Award Criteria: The Agreement Officer will review the Marking Plan for adequacy and reasonableness, ensuring that it contains sufficient detail and information concerning public communications, commodities, and program materials that will visibly bear the USAID Identity. The Agreement Officer will evaluate the plan to ensure that it is consistent with the stated objectives of the award; with the applicant’s cost data submissions; with the applicant’s actual project, activity, or program performance plan; and with the regulatory requirements of 22 C.F.R.226.91. The Agreement Officer will approve or disapprove any requested Presumptive Exceptions (see paragraph (d)) on the basis of adequacy and reasonableness. The Agreement Officer may obtain advice and recommendations from technical experts while performing the evaluation.

III. MARKING UNDER USAID-FUNDED ASSISTANCE INSTRUMENTS (December 2005)

(a) Definitions

Commodities mean any material, article, supply, goods or equipment, excluding recipient offices, vehicles, and non-deliverable items for recipient’s internal use, in administration of the USAID funded grant, cooperative agreement, or other agreement or subagreement.

Principal Officer means the most senior officer in a USAID Operating Unit in the field, e.g., USAID Mission Director or USAID Representative. For global programs managed from Washington but executed across many countries, such as disaster relief and assistance to internally displaced persons, humanitarian emergencies or immediate post conflict and political crisis response, the Cognizant Principal Officer may be an Office Director, for example, the Directors of USAID/W/Office of Foreign Disaster Assistance and Office of Transition Initiatives. For non-presence countries, the Cognizant Principal Officer is the Senior USAID officer in a regional USAID Operating Unit responsible for the non-presence country, or in the absence of such a responsible operating unit, the Principal U.S Diplomatic Officer in the non-presence country exercising delegated authority from USAID.

Programs mean an organized set of activities and allocation of resources directed toward a common purpose, objective, or goal undertaken or proposed by an organization to carry out the responsibilities assigned to it.

Projects include all the marginal costs of inputs (including the proposed investment) technically required to produce a discrete marketable output or a desired result (for example, services from a fully functional water/sewage treatment facility).

Public communications are documents and messages intended for distribution to audiences external to the recipient’s organization. They include, but are not limited to, correspondence, publications, studies, reports, audio visual productions, and other informational products; applications, forms, press and promotional materials used in connection with USAID funded programs, projects or activities, including signage and plaques; Web sites/Internet activities; and events such as training courses, conferences, seminars, press conferences and so forth.

Subrecipient means any person or government (including cooperating country government) department, agency, establishment, or for profit or nonprofit organization that receives a USAID subaward, as defined in 22 C.F.R. 226.2.

Technical Assistance means the provision of funds, goods, services, or other foreign assistance, such as loan guarantees or food for work, to developing countries and other USAID recipients, and through such recipients to subrecipients, in direct support of a development objective – as opposed to the internal management of the foreign assistance program.

USAID Identity (Identity) means the official marking for the United States Agency for International Development (USAID), comprised of the USAID logo or seal and new brandmark, with the tagline that clearly communicates that our assistance is “from the American people.” The USAID Identity is available on the USAID website at www.usaid.gov/branding and USAID provides it without royalty, license, or other fee to recipients of USAID-funded grants, or cooperative agreements, or other assistance awards.

(b) Marking of Program Deliverables

(1) All recipients must mark appropriately all overseas programs, projects, activities, public communications, and commodities partially or fully funded by a USAID grant or cooperative agreement or other assistance award or subaward with the USAID Identity, of a size and prominence equivalent to or greater than the recipient’s, other donor’s, or any other third party’s identity or logo.

(2) The Recipient will mark all program, project, or activity sites funded by USAID, including visible infrastructure projects (for example, roads, bridges, buildings) or other programs, projects, or activities that are physical in nature (for example, agriculture, forestry, water management) with the USAID Identity. The Recipient should erect temporary signs or plaques early in the construction or implementation phase. When construction or implementation is complete, the Recipient must install a permanent, durable sign, plaque or other marking.

(3) The Recipient will mark technical assistance, studies, reports, papers, publications, audio-visual productions, public service announcements, Web sites/Internet activities and other promotional, informational, media, or communications products funded by USAID with the USAID Identity.

(4) The Recipient will appropriately mark events financed by USAID, such as training courses, conferences, seminars, exhibitions, fairs, workshops, press conferences and other public activities, with the USAID Identity. Unless directly prohibited and as appropriate to the surroundings, recipients should display additional materials, such as signs and banners, with the USAID Identity. In circumstances in which the USAID Identity cannot be displayed visually, the recipient is encouraged otherwise to acknowledge USAID and the American people’s support.

(5) The Recipient will mark all commodities financed by USAID, including commodities or equipment provided under humanitarian assistance or disaster relief programs, and all other equipment, supplies, and other materials funded by USAID, and their export packaging with the USAID Identity.

(6) The Agreement Officer may require the USAID Identity to be larger and more prominent if it is the majority donor, or to require that a cooperating country government’s identity be larger and more prominent if circumstances warrant, and as appropriate depending on the audience, program goals, and materials produced.

(7) The Agreement Officer may require marking with the USAID Identity in the event that the recipient does not choose to mark with its own identity or logo.

(8) The Agreement Officer may require a pre-production review of USAID-funded public communications and program materials for compliance with the approved Marking Plan.

(9) Subrecipients. To ensure that the marking requirements “flow down'' to subrecipients of subawards, recipients of USAID funded grants and cooperative agreements or other assistance awards will include the USAID-approved marking provision in any USAID funded subaward, as follows: “As a condition of receipt of this subaward, marking with the USAID Identity of a size and prominence equivalent to or greater than the recipient’s, subrecipient’s, other donor’s or third party’s is required. In the event the recipient chooses not to require marking with its own identity or logo by the subrecipient, USAID may, at its discretion, require marking by the subrecipient with the USAID Identity.”

(10) Any ‘public communications’, as defined in 22 C.F.R. 226.2, funded by USAID, in which the content has not been approved by USAID, must contain the following disclaimer: “This study/report/audio/visual/other information/media product (specify) is made possible by the generous support of the American people through the United States Agency for International Development (USAID). The contents are the responsibility of [insert recipient name] and do not necessarily reflect the views of USAID or the United States Government.”

(11) The recipient will provide the Cognizant Technical Officer (CTO) or other USAID personnel designated in the grant or cooperative agreement with two copies of all program and communications materials produced under the award. In addition, the recipient will submit one electronic or one hard copy of all final documents to USAID’s Development Experience Clearinghouse.

(c) Implementation of marking requirements.

(1) When the grant or cooperative agreement contains an approved Marking Plan, the recipient will implement the requirements of this provision following the approved Marking Plan.

(2) When the grant or cooperative agreement does not contain an approved Marking Plan, the recipient will propose and submit a plan for implementing the requirements of this provision within

45 days after the effective date of this provision. The plan will include:

(i) A description of the program deliverables specified in paragraph (b) of this provision that the recipient will produce as a part of the grant or cooperative agreement and which will visibly bear the USAID Identity.

(ii) the type of marking and what materials the applicant uses to mark the program deliverables with the USAID Identity,

(iii) when in the performance period the applicant will mark the program deliverables, and where the applicant will place the marking,

(3) The recipient may request program deliverables not be marked with the USAID Identity by identifying the program deliverables and providing a rationale for not marking these program deliverables. Program deliverables may be exempted from USAID marking requirements when:

(i) USAID marking requirements would compromise the intrinsic independence or neutrality of a program or materials where independence or neutrality is an inherent aspect of the program and materials;

(ii) USAID marking requirements would diminish the credibility of audits, reports, analyses, studies, or policy recommendations whose data or findings must be seen as independent;

(iii) USAID marking requirements would undercut host-country government “ownership” of constitutions, laws, regulations, policies, studies, assessments, reports, publications, surveys or audits, public service announcements, or other communications better positioned as “by” or “from” a cooperating country ministry or government official;

(iv) USAID marking requirements would impair the functionality of an item;

(v) USAID marking requirements would incur substantial costs or be impractical;

(vi) USAID marking requirements would offend local cultural or social norms, or be considered inappropriate;

(vii) USAID marking requirements would conflict with international law.

(4) The proposed plan for implementing the requirements of this provision, including any proposed exemptions, will be negotiated within the time specified by the Agreement Officer after receipt of the proposed plan. Failure to negotiate an approved plan with the time specified by the Agreement Officer may be considered as noncompliance with the requirements is provision.

(d) Waivers.

(1) The recipient may request a waiver of the Marking Plan or of the marking requirements of this provision, in whole or in part, for each program, project, activity, public communication or commodity, or, in exceptional circumstances, for a region or country, when USAID required marking would pose compelling political, safety, or security concerns, or when marking would have an adverse impact in the cooperating country. The recipient will submit the request through the Cognizant Technical Officer. The Principal Officer is responsible for approvals or disapprovals of waiver requests.

(2) The request will describe the compelling political, safety, security concerns, or adverse impact that require a waiver, detail the circumstances and rationale for the waiver, detail the specific requirements to be waived, the specific portion of the Marking Plan to be waived, or specific marking to be waived, and include a description of how program materials will be marked (if at all) if the USAID Identity is removed. The request should also provide a rationale for any use of recipient’s own identity/logo or that of a third party on materials that will be subject to the waiver.

(3) Approved waivers are not limited in duration but are subject to Principal Officer review at any time, due to changed circumstances.

(4) Approved waivers “flow down” to recipients of subawards unless specified otherwise. The waiver may also include the removal of USAID markings already affixed, if circumstances warrant.

(5) Determinations regarding waiver requests are subject to appeal to the Principal Officer’s Cognizant Assistant Administrator. The recipient may appeal by submitting a written request to reconsider the Principal Officer’s waiver determination to the Cognizant Assistant Administrator.

(e) Non-retroactivity. The requirements of this provision do apply to any materials, events, or commodities produced prior to January 2, 2006. The requirements of this provision do not apply to program, project, or activity sites funded by USAID, including visible infrastructure projects

(For example, roads, bridges, buildings) or other programs, projects, or activities that are physical

in nature (for example, agriculture, forestry, water management) where the construction and implementation of these are complete prior to January 2, 2006 and the period of the grant does not extend past January 2, 2006.

ATTACHMENT 2:  Application for Federal Assistance  (SF 424)

APPLICATION FOR FEDERAL ASSISTANCE

2. DATE SUBMITTED

APPLICANT IDENTIFIER

1. TYPE OF SUBMISSION

3. DATE RECEIVED BY STATE

STATE APPLICATION IDENTIFIER

Application

Preapplication

Construction

Construction

Non-Construction

Non-Construction

4. DATE RECEIVED BY FEDERAL

FEDERAL IDENTIFIER

AGENCY

5. APPLICANT INFORMATION

Legal Name

Organizational Unit

Address (Street, County, State and ZIP code)

Name and telephone number of person to be contacted

on matters involving this application (give area code)

6. EMPLOYER IDENTIFICATION NUMBER (EIN)

7. TYPE OF APPLICANT (enter appropriate letter in box)

A. State

I. State Controlled Institu-

B. County

tion of Higher Learning

C. Municipal

J. Private University

D. Township

K. Indian Tribe

E. Interstate

L. Individual

F. Intermunicipal

M. Profit Organization

G. Special District

N. Other (Specify)

H. Independent School Dist.

8. TYPE OF APPLICATION

New

Continuation

Revision

If Revision, enter appropriate letter(s) in box(es)

A. Increase Award

B. Decrease Award

C. Increase Duration

D. Decrease Duration

E. Other (specify)

9. NAME OF FEDERAL AGENCY

10. CATALOG OF FEDERAL DOMESTIC ASSISTANCE NUMBER

11. DESCRIPTIVE TITLE OF APPLICANTS PROJECT

Title:

12. AREAS AFFECTED BY PROJECT (Cities, Counties, Street, etc.)

13. PROPOSED PROJECT

14. CONGRESSIONAL DISTRICTS OF

Start Date

Ending Date

Applicant

Project

15. ESTIMATED FUNDING

16. IS APPLICATION SUBJECT TO REVIEW BY STATE

EXECUTIVE ORDER 12372 PROCESS?

a. YES.  THIS PREAPPLICATION-APPLICATION WAS MADE

AVAILABLE TO THE STATE EXECUTIVE ORDER

12372 PROCESS FOR REVIEW ON

DATE

b. NO.

PROGRAM IS NOT COVERED BY E.O 12372

OR PROGRAM HAS NOT BEEN SELECTED BY

STATE FOR REVIEW

a. Federal

b. Applicant

c. State

d. Local

e. Other

f. Program Income

g. Total

17. IS THE APPLICATION DELINQUENT ON ANY FEDERAL DEBT?

Yes   If 'Yes', attach an explanation.

No

18. TO THE BEST OF MY KNOWLEDGE AND BELIEF, ALL DATA IN THIS APPLICATION/PREAPPLICATION ARE TRUE AND CORRECT.  THE

DOCUMENT HAS BEEN DULY AUTHORIZED BY THE GOVERNING BODY OF THE APPLICANT AND THE APPLICANT WILL COMPLY WITH

THE ATTACHED ASSURANCES IF THE ASSISTANCE IS AWARDED.

a. Type Name of Authorized Representative

b. Title

c. Telephone Number

d. Signature of Authorized Representative

e. Date Signed

Previous Editions Usable

Standard Form 424 (Rev. 4/92)

Authorized Local Reproduction

Prescribed by OMB Circular A-102

INSTRUCTION FOR THE SF424

PLEASE DO NOT RETURN YOUR COMPLETED FORM TO THE OFFICE OF MANAGEMENT

AND BUDGET, SEND IT TO THE ADDRESS PROVIDED BY THE SPONSORING AGENCY.

Public reporting burden for this collection of information is estimated to average 45 minutes per response, including

time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and

completing and reviewing the collection of information.  Send comments regarding the burden estimate or any other

aspect of this collection of information, including suggestions for reducing this burden, to the Office of Management

and Budget, Paperwork Reduction Project (0348-0043), Washington, DC 20503.

This is a standard form used by applicants as a required facesheet for preapplications and applications submitted for

Federal assistance.  It will be used by Federal agencies to obtain application certification that States which have

included in their process, have been given an opportunity to review the applicant's submission.

Item:

Entry:

Item:

Entry:

1. Self-explanatory.

12. List only the largest political entitles affected

(e.g., State, counties, cities).

2. Date application submitted to Federal agency (or

State if applicable) & applicant's control number

13. Self-explanatory.

(if applicable).

14. List the applicant's Congressional District and

3. State use only (if applicable)

any District(s) affected by the program or project.

4. If this application is to continue or revise an

15. Amount requested or to be contributed during the

existing award, enter present Federal identifier

first funding/budget period by each contributor.

number.  If for a new project, leave blank.

Value of in-kind contributions should be included

on appropriate lines as applicable.  If the action

5. Legal name of applicant, name of primary organi-

will result in a dollar change to an existing

zational unit which will undertake the assistance

award, indicate only the amount of the change.

activity, complete address of the applicant, and

For decreases, enclose the amounts in parentheses.

name and telephone number of the person to contact

If both basic and supplemental amounts are included,

on matters related to this application.

show breakdown on an attached sheet.  For multiple

program funding, use totals and show breakdown using

6. Enter Employer Identification Number (EIN) as

same categories as item 15.

assigned by the Internal Revenue Service.

16. Applicants should contact the State Single Point of

7. Enter the appropriate letter in the space provided.

Contact (SPOC) for Federal Executive Order 12372 to

determine whether the application is subject to the

8. Check appropriate box and enter appropriate letter(s)

State intergovernmental review process.

in the space(s) provided:

17. This qustion applies to the applicant organization,

-- 'New' means a new assistance award.

not the person who signs as the authroized repre-

sentative.  Categories of debt include delinquent

-- 'Continuation' means an extension for an

audit disallowances, loans and taxes.

additional funding/budget period for a project

with a projected completion date.

18. To be signed by the authorized representative

of the applicant.  A copy of the governing body's

-- 'Revision' means any change in the Federal

authorization for you to sign this application

Government's financial obligation or contingent

as official representative must be on file in the

liability from an existing obligation.

applicant's office.  (Certain Federal agencies

may require that this authorization be submitted

9. Name of Federal agency from which assistance is

as part of the application.)

being requested with this application.

10. Use the Catalog of Federal Domestic Assistance Number

and title of the program under which assistance is

requested.

11. Enter a brief descriptive title of the project.

If more than one program is involved, you should

append an explanation on a separate sheet.  If

appropriate (e.g., construction or real property

projects), attach a map showing project location.

For preapplications, use a separate sheet to rpovide

a summary description of this project.

SF 424 Back (Rev. 4/92)

BUDGET INFORMATION - Non-Construction Programs

Grant Program

Catalog of Federal

Estimated Unobligated Funds

New or Revised Budget

Function

Domestic Assist-

or Activity

ance Number

Federal

Non-Federal

Federal

Non-Federal

Total

(a)

(b)

(c)

(d)

(e)

(f)

(g)

1.

-

2.

-

3.

-

4.

-

5.  Totals

Grant Program Function or Activity

Total

6. Object Class Categories

(1)

(2)

(3)

(4)

(5)

a. Personnel

b. Fringe Benefits

c. Travel

d. Equipment

e. Supplies

f. Contractual

g. Construction

h. Other

i. Total Direct Charges (Sum of 6a-6h)

j. Indirect Charges

k. TOTALS (Sum of 6i and 6j)

7. Program Income

Previous Edition Usable

Authorized for Local Reproduction

Standard Form 424A (Rev. 4/92)

Prescribed by OMB Circular A-102

BUDGET INFORMATION - Non-Construction Programs (cont'd)

(a) Grant Program

(b) Applicant

(c) State

(d) Other Sources

(e) TOTALS

8.

9.

10.

11.

12. TOTAL (Sum of lines 8-11)

Total Amt 1st Year

1st Quarter

2nd Quarter

3rd Quarter

4th Quarter

13. Federal

14. Non-Federal

15. TOTAL (Sum of lines 13 and 14)

FUTURE FUNDING PERIODS (Years)

(a) Grant Program

(b) First

(c) Second

(d) Third

(e) Fourth

16.

17.

18.

19.

20. TOTAL (Sum of lines 16-19)

21. Direct Charges:

22. Indirect Charges:

23. Remarks:

Authorized for Local Reproduction

Standard Form 424A (Rev. 4/92)  Page 2

INSTRUCTION FOR THE SF424A

PLEASE DO NOT RETURN YOUR COMPLETED FORM TO THE OFFICE OF MANAGEMENT

AND BUDGET, SEND IT TO THE ADDRESS PROVIDED BY THE SPONSORING AGENCY.

Public reporting burden for this collection of information is estimated to average 180 minutes per response, including

time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and

completing and reviewing the collection of information.  Send comments regarding the burden estimate or any other

aspect of this collection of information, including suggestions for reducing this burden, to the Office of Management

and Budget, Paperwork Reduction Project (0348-0044), Washington, DC 20503.

General Instructions

in Column (5), Line 6k, should be the same as the total amount shown

in Section A, Column (g), Line 5.  For supplemental grants and changes

This form is designed so that application can be made for funds from

to grants, the total amount of the increase or decrease as shown in

one or more grant programs.  In preparing the budget, adhere to any

Column (1) - (4), Line 6k should be the same as the sum of the amounts

existing Federal grantor agency guidelines which prescribe how and

in Section A, Columns (e) and (f) on Line 5.

whether budgeted amounts should be separately shown for different

functions or activities within the program.  For some programs,

Line 7 - Enter the estimated amount of income, if any, expected to

grantor agencies may require a breakdown by function or activity.

be generated from this project.  Do not add or subtract this amount

Sections A, B, C, and D should include budget estimates for the whole

from the total project amount.  Show under the program narrative

project except when applying for assistance which requires Federal

statement the nature and source of income.  The estimated amount of

authorization in annual or other funding period increments.  In the

program income may be considered by the Federal grantor agency in

latter case, Sections A, B, C, and D should provide the budget for

determining the total amount of the grant.

the first budget period (usually a year) and Section E should present

the need for Federal assistance in the subsequent budget periods.

Section C. Non-Federal Resources

All applications should contain a breakdown by the object class

categories shown in Lines a - k of Section B.

Lines 8-11  Enter amounts of non-Federal resources that will be used

on the grant.  If in-kind contributions are included, provide a brief

Section A, Budget Summary Lines 1-4 Columns (a) and (b)

explanation on a separate sheet.

For applications pertaining to a single Federal grant program (Federal

Column (a) - Enter the program titles identical to Column (a),

activity breakdown, enter on Line 1 under Column (a) the catalog

Section A.  A breakdown by function or activity is not necessary

program title and the catalog number in Column (b).

Column (b) - Enter the amount of the State's cash and in-kind

For applications pertaining to a single program requiring budget

contribution if the applicant is not a State or State agency.

amounts by multiple functions or activities, enter the name of each

activity or function on each line in Column (a), and enter the catalog

Column (c) - Enter the amount of the State's cash and in-kind

number in Column (b).  For applications pertaining to multiple

contribution if the applicant is not a State or State agency.

programs where none of the programs require a breakdown by function

Applicants which are a State or State agencies should leave

or activity, enter the catalog program title on each line in Column

this column blank.

(a) and the respective catalog number on each line in Column (b).

Column (d) - Enter the amount of cash and in-kind contributions

For applications pertaining to multiple programs where one or more

to be made from all other sources

programs require a breakdown by function or activity, prepare a

separate sheet for each program requiring the breakdown.  Additional

Column (e) Enter total of columns (b), (c) and (d).

sheets should be used when one form does not provide adequate space

for all breakdown of data required.  However, when more than one sheet

Line 12 - Enter the total for each of Columns (b)-(e).  The amount in

is used, the first page should always provide the summary totals by

Column (c) should be equal to the amount on Line 5, Column (f),

programs.

Section A.

Lines 1-4 Columns (c) through (g)

Section D.  Forecasted Cash Needs

For new applications, leave Columns (c) and (d) blank.  For each line

Line 13 - Enter the amount of cash needed by quarter from the grantor

entry in Columns (a) and (b), enter in Columns (e), (f), and (g) the

agency during the first year.

appropriate amounts of funds needed to support the project for the

first funding period (usually a year).

Line 14 - Enter the amount of cash from all other sources needed by

quarter during the first year.

For continuing grant program applications, submit these forms before

the end of each funding period as required by the grantor agency.

Line 15 - Enter the totals of amounts on Lines 13 and 14.

Enter in Columns (c) and (d) the estimated amounts of funds which will

remain unobligated at the end of the grant funding period only if the

Section E.  Budget Estimates of Federal Funds Needed for Balance of

Federal grantor agency instructions provide for this.  Otherwise,

the Project.

leave these columns blank.  Enter in Columns (e) and (f) the amounts

of funds needed for the upcoming period.  The amount(s) in Column (g)

Lines 16-19 - Enter in Column (a) the same grant program titles shown

should be the sum of amounts in Columns (c) and (f).

in Column (a), Section A.  A breakdown by function or activity is not

necessary.  For new applications and continuation grant applications,

For supplemental grants and changes to existing grants, do not use

enter in the proper columns amounts of Federal funds which will be

Columns (c) and (d).  Enter in Column (e) the amount of the increase

needed to complete the program or project over the succeeding funding

or decrease of Federal funds and enter in Column (f) the amount of

periods (usually in years).  This section need not be completed for

the increase or decrease of non-Federal funds.  In Column (g) enter

revisions (amendments, changes, or supplements) to funds for the

the new total budgeted amount (Federal and non-Federal) which includes

current year of existing grants.

the total previous authorized budgeted amounts plus or minus, as

appropriate, the amounts shown in Columns (c) and (f).  The amount(s)

If more than four lines are needed to list the program titles, submit

in Column (g) should not equal the sum of amounts in Columns (c) and (f).

additional schedules as necessary

Line 5 - Show the totals for all columns used

Line 20 - Enter the total for each of the Columns (b)-(e).  When

schedules are prepared for this Section, annotate accordingly and

Section B Budget Categories

show the overall totals on this line.

In the column headings (1) through (4), enter the titles of the same

Section F.  Other Budget Information

programs, functions, and activities shown on Lines 1-4.  Column (a),

Section A.  When additional sheets are prepared for Section A, provide

Line 21 - Use this space to explain amounts for individual direct

similar column headings on each sheet.  For each program, function or

object-class cost categories that may appear to be out of the ordinary

activity, fill in the total requirements for funds (both Federal and

or to explain the details as required by the Federal grantor agency.

non-Federal) by object class categories.

Line 22 - Enter the type of indirect rate (provisional, predetermined,

Lines 6a - i  Show the totals of Lines 6a to 6h in each column.

final or fixed) that will be in effect during the funding period, the

estimated amount of the base to which the rate is applied, and the

Line 6j    Show the amount of indirect cost.

total indirect expense.

Line 6k - Enter the total of amounts on Lines 6i and 6j.  For all

Line 23 - Provide any other explanations or comments deemed necessary.

applications for new grants and continuation grants the total amount

Standard Form 424A (Rev. 4/92) Page 3

ASSURANCES - NON-CONSTRUCTION PROGRAMS

PLEASE DO NOT RETURN YOUR COMPLETED FORM TO THE OFFICE OF MANAGEMENT

AND BUDGET, SEND IT TO THE ADDRESS PROVIDED BY THE SPONSORING AGENCY.

Public reporting burden for this collection of information is estimated to average 15 minutes per response, including

time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and

completing and reviewing the collection of information.  Send comments regarding the burden estimate or any other

aspect of this collection of information, including suggestions for redurcing this burden, to the Office of Management

and Budget, Paperwork Reduction Project (0348-0040), Washington, DC 20503.

NOTE:  Certain of these assurances may not be applicable to your project or program.  If you have questions, please

contact the awarding agency.  Further, certain Federal awarding agencies may require applicants to certify to

additional assurances.  If such is the case, you will be notified.

As the duly authorized representative of the applicant I certify that the applicant:

1.  Has the legal authority to apply for Federal assist-

and Alcoholism Prevention.  Treatment and Rehabili-

ance and the institutional, managerial and financial

tation Act of 1970 (P.L. 91-616), as amended, relating

capability (including funds sufficient to pay the non-

to nondiscrimination on the basis of alcohol abuse or

Federal share of project cost) to ensure proper

alcoholism; (g) ½½523 and 527 of the Public Health

planning, management and completion of the project

Service Act of 1912 (42 U.S.C. 290 dd-3 and 290 cc-3),

described in this application.

as amended, relating to confidentiality of alcohol

and drug abuse patient records; (h) Title VIII of the

2.  Will give the awarding agency, the Comptroller

Civil Rights Act of 1968 (42 U.S.C. ½3601 et seq.),

General of United States, and if appropriate, the

as amended, relating to nondiscrimination in the sale,

State, through any authorized representative, access

rental or financing of housing; (i) any other non-

to and the right to examine all records, books,

discrimination provisions in the specific statute(s)

papers, or documents related to the award; and will

under which application for Federal assistance is

establish a proper accounting system in accordance

being made; and (j) the requirements of any other

with generally accepted accounting standards or agency

nondiscrimination statute(s) which may apply to the

directives.

application.

3.  Will establish safeguards to prohibit employees

7.  Will comply, or has already complied, with the

from using their positions for a purpose that

requirements of Titles II and III of the Uniform

constitutes or presents the appearance of personal

Relocation Assistance and Real Property Acquisition

or organizational conflict of interest, or personal

Policies Act of 1970 (P.L. 91-646) which provide for

gain.

fair and equitable treatment of persons displaced or

whose property is acquired as a result of Federal

4.  Will initiate and complete the work within the

or federally assisted programs.  These requirements

applicable time frame after receipt of approval of

apply to all interests in real property acquired for

the awarding agency.

project purposes regardless of Federal participation

in purchases.

5.  Will comply with the Intergovernmental Personnel Act

of 1970 (42 U.S.C. ½4728-4763) relating to prescribed

8.  Will comply, as applicable, with provisions of the

standards for merit systems for programs funded under

Hatch Act (5 U.S.C. ½½1501-1508 and 7324-7328) which

one of the nineteen statutes or regulations specified

limit the political activities of employees whose

in Appendix A of OPM's Standards for a Merit System

principal employment activities are funded in whole

of Personnel Administration (5 C.F.R. 900, Subpart F).

or in part with Federal funds.

6.  Will comply with all Federal statutes relating to

9.  Will comply as applicable, with the provisions of the

nondiscrimination.  These include but are not limited

Davis-Bacon Act (40 U.S.C. ½½276a to 276z - 276a-7),

by (a) Title VI of the Civil Rights Act of 1964

the Copeland Act (40 U.S.C. ½½276c and 18 U.S.C. ½½874),

(P.L. 88-352) which prohibits discrimination on the

and the Contract Work Hours and Safety Standards Act

basis of race, color or national origin; (b) Title IX

(40 U.S.C. ½½327-333), regarding labor standards for

of the Education Amendments of 1972, as amended

federally assisted construction subagreements.

(20 U.S.C. ½1681-1683, and 1685-1686), which prohibits

discrimination on the basis of sex; (c) Section 504

10.  Will comply if applicable, with flood insurance

of the Rehabilitation Act of 1973, as amended (29 U.S

purchase requirements of Section 102(a) of the Flood

C. ½794), which prohibits discrimination on the basis

Disaster Protection Act of 1973 (P.L. 93-234) which

of handicaps; (d) the Age Discrimination Act of 1975,

requires recipients in a special flood hazard are to

as amended (42 U.S.C. ½6101-6107), which prohibits

participate in the program and to purchase flood

discrimination on the basis of age; (e) the Drug Abuse

insurance if the total cost of insurable construction

Office and Treatment Act of 1972 (P.L. 92-255), as

and acquisition is $10,000 or more.

amended, relating to nondiscrimination on the basis

of drug abuse; (f) the Comprehensive Alcohol Abuse

Standard Form 424B (Rev. 4/92)

Previous Edition Unusable

Prescribed by OMB Circular A-102

ASSURANCES - NON-CONSTRUCTION PROGRAMS (cont'd)

11.  Will comply with environmental standards which may

14.  Will comply with P.L. 93-348 regarding the protection

be prescribed pursuant to the following: (a) insti-

of human subjects involved in research, development,

tution of environmental quality control measures

and related activities supported by this award of

under the National Environmental Policy Act of

assistance.

1969 (P.L. 91-190) and Executive Order (E.O.) 11514;

(b) notification of violating facilities pursuant to

15.  Will comply with the Laboratory Animal Welfare Act

EO 11738; (c) protection of wetlands pursuant to EO

of 1966 (P.L. 89-544, as amended, 7 U.S.C. 2131 et

11990; (d) evaluation of flood hazards in floodplains

seq.) pertaining to the care, handling, and treat-

in accordance with EO 11988; (e) assurance of project

ment of warm blooded animals held for research,

consistency with the approved State management program

teaching, or other activities supported by this

developed under the Coastal Zone Management Act of

award of assistance.

1972 (16 U.S.C. ½½1451 et seq.); (f) conformity of

Federal actions to State (Clean Air) Implementation

16.  Will comply with the Lead-Based Paint Poisoning

Plans under Section 176(c) of the Clean Air Act of

Prevention Act (42 U.S.C. ½½4801 et seq.) which

1955, as amended (42 U.S.C. ½½7401 et seq.); (g)

prohibits the use of lead based paint in construc-

protection of underground sources of drinking water

tion or rehabilitation of residence structures.

under the Save Drinking Water Act of 1974, as amended,

(P.L. 93-523); and (h) protection of endangered species

17.  Will ensure to be performed the required financial

under the Endangered Species Act of 1973, as amended,

and compliance audits in accordance with the Single

(P.L. 93-205).

Audit Act of 1984 or OMB Circular No. A-133, Audits

of Institutions or Higher Learning and other Non-

12. Will comply with the Wild and Scenic Rivers Act

profit Institutions.

of 1968 (16 U.S.C. ½½1271 et seq.) related to

protecting components or potential components of

18.  Will comply with all applicable requirements of all

the national wild and scenic rivers system.

other Federal laws, executive orders, regulations

and policies governing this program.

13.  Will assist the awarding agency in assuring compli-

ance with Section 106 of the National Historic

Preservation Act of 1966, as amended (16 U.S.C. 470),

EO 11593 (identification and protection of historic

properties), and the Archacological and Historic

Preservation Act of 1974 (16 U.S.C. 469a-1 et seq.).

SIGNATURE OF AUTHORIZED CERTIFYING OFFICIAL

TITLE

APPLICANT ORGANIZATION

DATE SUBMITTED

Standard Form 424B (Rev. 4/92) Back