Funding Opportunity Title:  C-NOFO-19-103:  Indian Women Social Entrepreneurs Network

CFDA Number: 19.040 - Public Diplomacy Programs

Contact:  Grant Applications Manager, U.S. Consulate, Chennai

Email:  ChennaiPASG@State.Gov

Application Open Date:  6/24/2019

| Application End Date: | 7/31/2019 | 11:59 pm midnight Washington, DC |
| --- | --- | --- |

For the purposes of determining if an award is submitted on time, we will utilize the time-stamp provided by Grants.gov. This deadline is firm and is not a rolling deadline. If organizations fail to meet the deadline noted above their application will be considered ineligible and will not be considered for funding.

Section I. Funding Opportunity Description

The U.S. Consulate General Public Affairs Section in Chennai is soliciting proposals for a grant/cooperative agreement that meets the specifications stated in Section II from legally recognized non-profit, non-governmental organizations that meet U.S. and Indian technical and legal requirements to develop and implement public diplomacy programs as specified by Section II below. Information about the Public Affairs Section can be found at: https://in.usembassy.gov/.

Background:  Nearly 25 percent of all social enterprises in India are led by women, compared to less than 10 percent of commercial small and medium enterprises that have a woman at the helm.  Women are often subject to discrimination from their families, communities, and investors when compared to male peers.  This issue is even more acute for women because social entrepreneurship can be stigmatized as being unprofitable.  The sector of women-led social enterprises in India would benefit from the establishment of a formalized, cohesive network that would give them access to information, capital, mentorship, and other opportunities that they currently lack in both social and commercial enterprises. This project will provide 40 women social entrepreneurs across India, with the skills that will result in scaling their businesses and create a formal network called the Indian Women Social Entrepreneurs Network (IWSEN).

Project Objectives:

- Enhance the operating environment and networking capacity of women social entrepreneurs in India with attention to replicating and scaling, as evidenced by a pre and post-project survey.

- Guide the participants to form a pan-India network of women social entrepreneurs founded on practical knowledge and information sharing, as evidenced by the establishment of IWSEN.

- Use the IWSEN platform to successfully advocate for support and funding for women-led social enterprise, leading to their economic and social empowerment and at the same time positively impacting their communities.

Section II.  Indian Women Social Entrepreneurs Network

Goals:  Based on funding availability, this award will support capacity-building workshops for women social entrepreneurs across India and help establish a formal network that will serve as a platform to promote women-led social enterprises. The project will showcase U.S. best practices in the social entrepreneurship sector leading to increased business opportunities and market access in both countries.

Program Description:  The Public Affairs Section of the U.S. Consulate General in Chennai (PAS Chennai) seeks proposals for a project titled Indian Women Social Entrepreneurs Network (IWSEN).  This project will invite 40 women social entrepreneurs from India and provide them with tools through which these change-makers’ vision and goals are affirmed, supported, promoted, and propelled to the next level. The project will highlight the benefit of creating networks of support, knowledge, and resource sharing through localized frameworks, rather than just scaling single business ventures.  A major goal of the project is the creation of the Indian Women Social Entrepreneurs Network (IWSEN), which will be designed, executed, and launched with the collective inputs of the 40 participants.  The participants will receive practical training to scale their business enterprise through this project and will become founding members and master trainers for future members of IWSEN.  IWSEN will also serve as a platform to trigger social and cultural change in how women are viewed by providing increased economic empowerment and financial independence to them.  Where appropriate, the grantee will highlight best practices from the United States and emphasize the benefits to the U.S. economy from the development of this network.

Phase One: The grantee will identify 40 Indian women social entrepreneurs with strong leadership qualities who will be invited to participate in this project.  They will also identify U.S. and Indian subject matter experts who will provide their expertise, knowledge, and skills to build capacity of the participants and help in the formation of IWSEN.  The U.S. experts ideally should be representatives from social entrepreneurship networks that promote women led social ventures in the United States.

Simultaneously, the grantee, with inputs from the U.S. and Indian experts, will identify a core group of 10 women across India who will take the lead to form the IWSEN.

Phase Two:  The grantee will organize one or more workshop(s) during which the 40 participants will receive practical training in successful business models, networking, communication, and best practices in social entrepreneurship from U.S. and Indian experts.  The participants will also receive mentorship training from the experts, which they, in turn, will use to encourage, mentor, and support other women social entrepreneurs in their communities.

Phase Three:  Following the workshop(s) the grantee will guide the Core Group members to form, register, and formally launch IWSEN within a reasonable period of time, e.g. three to four months. The Core Group will also be responsible for starting chapters in their regions after the formal launch of IWSEN.

Phase Four:  The grantee will monitor the impact of the workshop(s) and the IWSEN on the 40 participants and their social enterprises

Proposals must detail:  The grantee is responsible for all aspects of the program as noted below.  Submitted proposals should include programmatic and financial details on the following:

- Schedule and Timelines: The grantee will prepare a detailed schedule outlining the timelines of the entire project from start to finish in consultations with PAS Chennai.

- Selection of Experts: The grantee will be responsible for identifying Indian and American experts to serve as resource persons for this project.  As appropriate, the grantee may draw upon the expertise of the Nexus Center located at the American Center of the U.S. Embassy in New Delhi. The U.S. experts should ideally be representatives from a social entrepreneurship network that has successfully promoted women-led social ventures within the United States and helped expand their businesses at the regional and international levels.  It is important for the American experts to have some knowledge about the social entrepreneurship sector in India. The grantee will be responsible for managing all logistical components including international/domestic flights, visas (for the American experts), insurance, lodging, local transportation, per diem, and honorarium.

- Selection of participants and local partners:  The grantee will be responsible for identifying 40 participants from throughout India for the project in consultations with the U.S. Consulate General Chennai.  The grantee should ensure that there is even representation of participants across the country.  Each participating Post will clear and approve the final list of participants from their consular districts.  The grantee will be responsible for managing all components of their participation, including domestic flights, lodging, local transportation, and per diem.

- Selection of Partners and Sponsors:  If desired, the grantee may propose local partner organizations and potential co-sponsors for this project.

- Developing the Project Agenda:  The grantee will draw up a detailed agenda for the entire project, which will include the training aspect and the launch of IWSEN in consultations with the experts and U.S. Consulate General Chennai staff.

- Logistics for the two workshops and launch event:  The grantee will develop the workshop agenda and materials in coordination with the Indian and U.S. experts (to be approved by PAS Chennai) and will manage all logistics related to the workshop(s) including the formal launch of IWSEN.  Proposals must include detailed expenses associated with the workshop(s), including arranging for workshop materials and A/V support, and developing and implementing a media amplification plan.  PAS Chennai will provide final approval on the workshop agenda and materials.  PAS Chennai will also provide final approval for any additional participants and guests who may be invited for the IWSEN launch.

- Securing a venue:  The grantee must be able to secure a suitable venue for the workshop(s), ideally as an in-kind contribution or cost-share element.  In the event this is not possible, the cost for venue rental may be included in the budget.

- Registration of IWSEN:  The grantee will work closely with the 10 Core Group members (with inputs from the remaining participants) to develop the goals, objectives and other content for the IWSEN network and also guide them through the legal and related procedures for its formal registration.

- Traditional and social media plan for amplification of the program activities and outcomes:  The grantee will develop and implement a robust traditional and social media plan for amplification of workshop activities and outcomes.  The grantee will consult with local partners and PAS Chennai's Media and Digital Engagement team prior to finalizing and executing the plan.

- Monitoring and evaluation plan:  The grantee will be responsible for submitting a detailed monitoring and evaluation plan for all components of the program, including survey tools and timelines.  The plan should demonstrate and measure the program goals and objectives. The grantee is responsible for collecting baseline data, conducting follow-up surveys, and reporting.  The grantee will brief PAS Chennai on the qualitative and quantitative progress of the project implementation in quarterly reports.

USG Role:

- PAS Chennai and other participating Posts representing the U.S. Mission to India will approve the final list of workshop participants from their consular districts.

- PAS Chennai will approve the final agenda and list of experts invited to speak at the workshop(s) before they are confirmed by the grantee.

- PAS Chennai will approve any co-sponsor(s) and/or partners before they are finalized by the grantee.

- PAS Chennai’s Media and Digital Engagement team will approve the traditional and social media plan for amplification of workshop activities and outcomes.

Section III. Award Information

1. Funding Type and Amount:  Cooperative agreement

- Minimum (“Floor”) Award Amount:  $55,000

- Maximum (“Ceiling”) Award Amount:  $60,000

The Public Affairs Section reserves the right to award less or more than the funds described under circumstances deemed to be in the best interest of the U.S. government, pending the availability of funds and approval of the designated grants officer.

2. Project and Budget Periods: Grant projects generally should be completed in one year or less.

Section IV. Eligibility Criteria

- Eligibility is open to all non-profit, non-governmental organizations. Individuals are not eligible for an award under this Notice of Funding Opportunity (NOFO). Organizations may sub-contract with other entities, but only one, non-profit, non-governmental entity can be the prime recipient of the award. When sub-contracting with other entities, the responsibilities of each entity must be clearly defined in the proposal.

- Cost-sharing or matching is required for this funding opportunity.

- Pre-award costs are not an allowable expense for this funding opportunity.

- This award does not allow:

  - Programs relating to partisan political activity;

  - Charitable or development activities;

  - Construction programs;

  - Programs that support specific religious activities;

  - Fund-raising campaigns;

  - Lobbying for specific legislation or programs

  - Scientific research or surveys;

  - Commercial projects;

  - Programs intended primarily for the growth or institutional development of the organization;

  - Programs that duplicate existing programs; or

  - Illegal activities

Other Eligibility Requirements:

Organizations must have a Data Universal Numbering System (DUNS) number from Dun & Bradstreet http://fedgov.dnb.com/webform and an active SAM registration (www.SAM.gov). The U.S. Department of State will not make an award to an applicant until the applicant has complied with all applicable DUNS and SAM requirements by the time the Department is ready to make an award.

Applicants must register with Grants.gov prior to submitting an application. Registering with Grants.gov is a one-time process; however, it may take weeks to have the registration validated and confirmed. Please begin the registration process immediately to ensure that the process is completed well in advance of the deadline for applications. Until that process is complete, you will not be issued a user password for Grants.gov, which is required for application submission.

There are four steps that you must complete before you are able to register:

(1) obtain a Data Universal Numbering System (DUNS) number from Dun & Bradstreet (if your organization does not have one already) by visiting http://fedgov.dnb.com/webform ;

(2) register with System for Award Management (SAM) www.SAM.gov;

(3) register yourself as an Authorized Organization Representative (AOR); and

(4) be authorized as an AOR by your organization.

For more information, go to www.grants.gov. Please note that your SAM registration must be annually renewed. Failure to renew your SAM registration may prohibit submission of a grant application through Grants.gov.

For Indian applicants, the Foreign Contribution Regulation Act (FCRA) of the Government of India applies.

Applicants must acquire all required registrations and rights in the United States and India.  All intellectual property considerations and rights must be fully met in the United States and India.

Any sub-recipient organization must also meet all the U.S. and Indian requirements described above.

Section V. Application Submission:

Instructions: Please follow all instructions below carefully. Failure to furnish all information or comply with stated requirements may lead to the application’s disqualification for consideration.  Applicants must set forth accurate and complete information as required by this NOFO.

Applicants must ensure:

- All documents are in English

- All budgets are in U.S. dollars and calculated @ USD 1 = INR 68

- All pages are numbered

- All materials are submitted in .pdf format

- Applicant has read the Standard Terms and Conditions applicable to all Grants and Cooperative agreements.  Included in the package here.

- Forms SF-424, SF-424A and SF-424B are completed and submitted with the application. These forms are included in the package.

- Applicants submitting proposals over $100,000 must also submit Standard Form LLL (SF-LLL), Disclosure of Lobbying Activities. This form is available at: http://apply07.grants.gov/apply/forms/sample/SFLLL-V1.1.pdf

We recommend that you submit your program proposal using “Recommended Application format” template (Attachment A) and detailed budget using “Recommended Budget Spreadsheet” template (Attachment B). Feel free to submit additional information as you deem necessary.

- Budget Narrative: The budget narrative supplements the information provided in the budget spreadsheet and justifies how the budget cost elements are necessary to implement project objectives and accomplish the project goals. Together, the budget narrative and spreadsheets should provide a complete financial and qualitative description that supports the proposed project plan and should be directly relatable to the specific project components described in the applicant’s proposal.

- Letters of Intent: If local partnerships are included as part of the proposal, applicants must include a letter of intent between all partners as part of their application. The letters must identify the type of relationship to be entered into (formal or informal), the roles and responsibilities of each partner in relation to the proposed project activities, and the expected result of the partnership.  The individual letters should not exceed one (1) page in length.

- Proof of Non-profit Status: Documentation to demonstrate the applicant’s non-profit status (e.g. U.S.-based organizations should submit a copy of their IRS determination letter, Indian organizations should provide a copy of their NGO status).

The U.S. Consulate General Chennai reserves the right to request additional programmatic and financial information regarding the proposal.

Questions: For questions on this solicitation please contact Grants Applications Manager, Public Affairs Section, U.S. Consulate General, Chennai, India, at: ChennaiPASG@State.Gov

All application materials must be submitted electronically through Grants.gov.  If you are unable to submit your proposal on grants.gov, you may submit via email at ChennaiPASG@State.Gov before the deadline. The subject line should be as follows -- Applicant Organization name – C-NOFO-19-103:  Indian Women Social Entrepreneurs Network (IWSEN)

For questions relating to grants.gov, please contact them at 1-800-518-4726 or support@grants.gov.

Section VI. Review and Selection Process

1.  Criteria.  Each application submitted under this announcement will be evaluated and rated on the basis of the criteria enumerated in Section VII below. The criteria are designed to assess the quality of the proposed project, and to determine the likelihood of its success.

2.  Acknowledgement of receipt.  Applicants will receive acknowledgment of receipt of their proposal.

3.  Review.  A technical review panel will review the proposal and based upon the criteria noted in Section VII.  A determination will be made regarding the program’s proposed area of activity and the Mission’s strategic goals, and those proposals that are the best fit will be given additional consideration.

4.  Follow up notification.  Applicants will generally be notified within 90 days after the NOFO deadline regarding the results of the review panel.

Section VII. Application Evaluation Criteria

1. Completeness of Proposal.  The proposal meets all of the outstanding technical and logistical criteria required in this cooperative agreement, addressing the objectives as noted in Section II above.  (15 points)

2. Innovation.  Applicant clearly describes how its proposal will address the requested program within the proposed timeframe and articulates an innovative strategy or plan. (20 points)

3. Institutional and organizational capacity.  The organization and any partners demonstrate subject matter expertise in the form and content of the proposal, and in organizing and managing the project. The applicant must have knowledge, expertise and contacts with various stakeholders in the field of social entrepreneurship. (20 points)

4. Budget and narrative justification.  The budget and narrative justification are complete and reasonable in relation to the proposed activities and anticipated results. The cost estimates are realistic. (15 points)

5. Monitoring and evaluation.  The Monitoring and Evaluation component of the proposal will outline in detail how the proposal’s activities will advance the program’s goals and objectives (listed above). A strong proposal will include:

- A schedule of when grant activities will occur (such as overview planning, research methodology, sample size, participant selection, indicators, analysis and presentation etc.), and when the applicant will check the project’s progress to know how it is performing.  Results of those checks are expected to be reported in the quarterly reports.

- Expected project outputs, including definitions and targets. Outputs can include: number of trainings held; number of workshops implemented; number of outreach activities conducted.

- Expected project outcomes, including definitions and targets. Outcomes can include number of participants in trainings, number of new network members who join as a result of participant outreach, number of new women’s social entrepreneurships created after initial training.

- A plan to include the grantee’s reflection of how their project, as a whole, contributed to the program’s goals.  As applicable, a strong final report would be supported by success stories, behaviors changed, lessons learned, and results obtained. (15 points)

6.  Sustainability.  The project demonstrates sustainable capacity and relationship building between the Indian and American organizations, as appropriate. The proposal describes how activities will be carried on after the program ends and may include (but not be limited to) continued involvement of stakeholders; future commitment of funding; on-going training; planned meetings of program participants.  (15 points)

Section VIII. Award Administration

1.  Award notices: The grant or cooperative agreement award shall be written, signed, awarded, and administered by the Grants Officer, who is the U.S. government official delegated the authority by the U.S. Department of State Procurement Executive to write, award, and administer grants and cooperative agreements. The assistance award agreement is the authorizing document and will be provided to the recipient. The awardee will interact with a designated Grants Officer Representative (GOR).

2.   Reporting requirements:  All awards issued under this announcement require both program and financial reports on a frequency specified in the award agreement. The disbursement of funds will be tied to the timely submission of these reports. All details related to award administration will be specified in the award agreement. The point of contact for questions or issues related to the administration of the grant/cooperative agreement will be specified in the award agreement.

Attachment A

RECOMMENDED APPLICATION FORMAT

| 1. GENERAL INFORMATION |  |  |  |
| --- | --- | --- | --- |
| 1.1 Applicant Name |  |  |  |
| a. Legal Name (as in Bank Account): |  |  |  |
| b. Address: |  |  |  |
| c. City/Town: | d. District: |  | e. State: |
| f. Zip/Pin Code: |  | g. Website: |  |
| h. Other Info. (if any): |  |  |  |

| 1.2 Point of Contact |  |  |  |
| --- | --- | --- | --- |
| a. Last Name: |  | b. First Name: |  |
| c. Tel: | d. Cell: | E. E-mail | d. Fax |

2. BACKGROUND OF ORGANIZATION

2.1 Description

2.2 Key Personnel

2.3 Project Partner(s)

2.4 Past Grants (U.S. Embassy, Department of State, Other)

2.5 Strengths and Capacity of Organization

| 3. PROJECT DESCRIPTION |  |  |
| --- | --- | --- |
| 3.1 Project Information |  |  |
| a. Project Name: |  |  |
| b. Duration (months): | c. Start Date: Click here to enter a date. | d. End Date: Click here to enter a date. |

3.2 Executive Summary

3.3 Project Justification

3.4 Project Goal and Objectives

3.5 Project Innovation

3.6 Project Activities

3.7 Project Accomplishments (Milestones)

3.8 Monitoring and Evaluation Plan

3.9 Sustainability

4. BUDGET

4.1 (See Attachment B: Suggested Grant Proposal Budget Worksheet to submit your Detailed Budget submission)

- Total Funding applied for: $____________________ (must match with Attachment B) - Total Recipient share (if any)$ __________________ (must match with Attachment B)

4.2 Budget Narratives and other Remarks (if any)

Instructions

Key Personnel:  Name of the organization, address, phone/fax number/e-mail address, name and title of director (or person who is to sign the grant/cooperative agreement) and other significant staff members, particularly those who will be involved in the project and budget specifics. Provide an executive summary of the project description (no more than one page) with reference to the amount and duration of the funding request.

Description of Organization:  Applicants must submit a full description of the organization and its expertise to organize and manage all aspects of this particular project. This applies to all proposed project partner as well.

Justification:  This is a very important aspect of the proposal and applicants should pay particular attention to it. Define what the project will accomplish, and how will it benefit stakeholders. Please do not exceed one page.

Activities:  Outline a plan of action that describes the scope and detail of how the proposed work will be accomplished. Provide an overview of the full sequence of proposed project activities, including beginning and end dates and locations of events. Account for all functions or activities identified in the application.

Accomplishments, Monitoring and Evaluation, and Sustainability:  Provide quantitative monthly or quarterly projections of the accomplishments to be achieved for each function or activity. When accomplishments cannot be quantified by activity or function, list them in chronological order to show the schedule of accomplishments and their target dates. Describe how you plan to monitor progress, and determine overall success and impact of the program. Note how you expect the impact of the project will be sustained over time, and by whom.

Budget:  Please refer to Attachment B “Suggested Grant Proposal Budget Worksheet.” Provide a detailed budget of every cost associated with the project. The more information and detail that you provide about the proposed budget, with a budget narrative, the better we can determine the viability and completeness of your proposal. For the budget line item “indirect costs” or “administrative overhead,” any figure you provide without a specific breakout will be returned for additional information or rejected. If your organization has an approved “Negotiated Indirect Cost Rate Agreement” or NICRA, please note that on your application and provide supporting documentation. Please also include the types and amounts of funding your organization has already received for the current project. Budgets must be calculated in U.S. dollars. Please note that the Fly America Act requires that anyone whose air travel is financed by U.S. Government funds to utilize the economy class services of a U.S. flag carrier.