UNITED STATES

DEPARTMENT OF THE INTERIOR

NATIONAL PARK SERVICE

Geologic Mapping of the Lancing, Hebbertsburg, and Fox Creek 7.5 minute Quadrangles, Obed Wild and Scenic River

Authority: 16 USC §1a-2(j), 16 USC §5933 and the 1998 NPS Omnibus Act

Funding Opportunity Announcement

No. P14AS00040

CFDA No. 15.945

CFDA Title: Cooperative Research and Training Programs – Resources of the National Park System

ISSUE DATE: March 12, 2014

CLOSING DATE & TIME March 18, 12:00 PM., Eastern Daylight Time

Contact Information:

Brian Straka, Agreements Officer
North Administrative Service Unit
Great Smoky Mountains National Park
Phone: 865.436.1217   Fax: 865.436.1220

Brian_Straka@nps.gov

SECTION I.  Funding Opportunity Description

A. Project Objectives: The Cooperator will provide geologic map coverage in a  GIS for three 7.5 minute quadrangles (Lancing, Hebbertsburg, and Fox Creek) that will complete the geologic map of Obed Wild and Scenic River (OBED).

B. Project Tasks:

The University of Tennessee’s Dr. Robert Hatcher and his students will provide the National Park Service Geologic Resources Inventory (GRI) with geologic maps of the Lancing, Hebbertsburg, and Fox Creek 7.5 minute quadrangles.

All geologic features present on the published map(s) are present as GIS data, and are fully attributed shape files to standards as identified in Part I d of the USGS-NCGMP 2004 STATEMAP program announcement No. 04hQPA0003.

ROLE OF COOPERATOR IN THIS PROJECT:

Collaboratively undertake project work titled “Geologic Mapping in Obed Wild and Scenic River”.

- The Cooperator will: produce a geologic map of the Lancing, Hebbertsburg, and Fox Creek 7.5 minute quadrangles that cover an unmapped portion of Obed Wild and Scenic River and deliver the products listed below.

- Appoint Dr.Robert Hatcher as Principal Investigators (PI).

- Acknowledge the NPS and the Southern Appalachian CESU in any peer-reviewed publication generated from this project.

ROLE OF NPS IN THIS PROJECT:

- The NPS will: Provide the cooperator with all relevant NPS Obed Wild and Scenic River (OBED) GIS data sets and other associated data that may be important to geologic mapping and data interpretation.  Such data sets may include, but not be limited to, park boundaries, park infrastructure/facilities, etc.

- Provide the cooperator all relevant LIDAR imagery and aerial imagery that is in the possession of OBED or Appalachian Highlands Network.

- Provide natural resource management staff from the NPS-Geologic Resources Division-Denver and from the participating park units to collaborate with the cooperator on project study design, to frequently consult with the cooperator on creation of the map legends/map categories, and to review all preliminary, interim, and final documents associated with the project.

- When available, provide logistical support to facilitate the conduct of mapping activities in OBED, such as, but not limited to, access to remote park areas, assistance with the NPS permitting process,  and assistance with field data collection.

- Provide, through the Geologic Resources Division, assistance required by Dr. Hatcher and his students to create the geologic maps in a Geographic Information System (GIS) using state-or-the-art ESRI ARCGIS software.

Additionally, OBED staff will meet with Dr. Hatcher and his students prior to commencing mapping and participate in a post-mapping meeting to review the mapping product.

C. Project Products:

For the the Lancing, Hebbertsburg, and Fox Creek 7.5 minute quadrangles, the cooperator deliver to the NPS a digital geologic map in ESRI ArcGIS 9.x or latest version including:

- A personal geodatabase (.mdb) for each digital geologic-GIS map with a Geologic Unit Information table and Source Map Information table, where applicable

- Accompanying text and graphics containing map explanatory information

- A description of map units

- A stratigraphic column depicting stratified units

- Where applicable, a correlation diagram showing age relationships of map units
An explanation of map symbols

- FGDC compliant metadata for all files developed

- Completed data may be delivered via CD-ROM or by file transfer protocol (ftp) or some other suitable agreed upon electronic medium.

D. Project Schedule:

The period of performance shall be date of agreement signature through 12/31/2014. A preliminary schedule (subject to revision) for the project includes the following key dates:

- February, 2014 – Meeting with park staff, commencement of field mapping

- June, 2014 – Completion of field mapping, with possible field checking throughout the summer.

- August, 2014 – Completion of office compilation of map data, integration of sampling data, development of GIS, and any accompanying descriptions.

- September, 2014 – Delivery of final product to Geologic Resources Inventory team and close out meeting with park staff.

E. Furnished Property / Other Considerations:

If available and of use to the cooperator, the NPS will provide digital images or LiDAR of the area encompassed by the three, above mentioned quadrangles.  If requested, the NPS will also deliver shape files of the OBED boundary for the cooperator’s use

F. National Park Service Project Contact:

ATR:  Bruce A. Heise,  National Park Service, Geologic Resources Division, Denver, CO   bruce_heise@nps.gov, 303-969-2017

PR Requisitioner: Emi Hirabayaski Buck, National Park Service, Office of Budget and Finance, Denver, CO emi_buck@nps.gov  303-969-2070

Cooperator(s): Dr. Robert Hatcher, Distinguished Scientist and Professor, Department of Earth and Planetary Science, University of Tennessee, Knoxville, TN, bobmap@utk.edu  (865) 974-6565

# SECTION II.  AWARD INFORMATION

- Expected Number of Awards:  One (1)

- Estimated Total Program Funding:  $43,537.00

- Award Ceiling:

##### D.  Assistance Instrument:  Southern Appalachian Mountains Cooperative Ecosystem Studies Unit Cooperative Agreement

# SECTION III.  ELIGIBILITY INFORMATION

A. Eligible Applicants:  Members organizations / universities of the Southern Appalachian Mountains Cooperative Ecosystems Studies Unit (SA-CESU)

B. Cost Sharing or Matching: $0.00

SECTION IV.  APPLICATION AND SUBMISSION INFORMATION

A.  Address to Request Application Package:

This announcement contains all information, instruction and attachments necessary to submit an application through Grants.gov.

B.  Content and Form of Application:

The application package shall consist of all the required SF-424 Standard Forms shown below AND Proposal Submission Format (Attachment A) and Budget (Attachment B) narrative.  If the project budget exceeds $100,000 a Certification for Federal Assistance is also required (Attachment C).

1. Required Standard Forms:

| SF Forms to Submit | SF-424 Family of Forms |
| --- | --- |
| Application | Form SF-424, Application for Federal Assistance http://cesu.utk.edu/documents/nps_documents_only/NPS_SF-424.pdf (Some fields in this form have been already been filled in with NPS information.) |
| Budget Information | Form SF-424A, Budget Information - Non-Construction Programs http://cesu.utk.edu/documents/project_templates/SF-424_A.pdf |
| Assurances | Form SF-424B, Assurances - Non-Construction Programs http://cesu.utk.edu/documents/project_templates/SF-424_B.pdf |

SF-424 forms should be completed and signed by the appropriate grants officer.  This is often the Office of Sponsored Programs at Universities.   PDF format is preferred.

Assistance with any of the SF-424 forms can be requested of the SA-CESU NPS Coordinator (Ray Albright at 865 974-8443 or ray_albright@nps.gov)

2. Proposal Submission.

Proposal Submission Format (Attachment A) can be used as an example when submitting your proposal.  The proposal technical text must be no longer than 10 pages, no smaller than font size 11, and have 1-inch margins.  The 10-page limit includes all text, figures, references, and vitae.  (The Budget, Attachment B, is not included in the 10-page limit.)

Communication with the National Park Service Project Contact (see Section I.F. above) is encouraged during the development of the proposal.  The intent of a cooperative project is for all parties to ‘build the project together’.   The SA-CESU NPS Coordinate is also available for consultation regarding the proposal.

The proposal text should include the following:

  - Purpose and Objectives– (Attachment A, Section I) - (a) Describe why the project is needed by the National Park Service; (b) Describe the project’s objectives.

  - Technical Approach – (Attachment A, Section II) - Describe how you propose to conduct and achieve the project in accordance with the project objectives. The project design must contain enough detail to show the development of the project and the relationship between the objectives, tasks, and milestones.  The work plan must be clear, suitable, and feasible with respect to the following;  (a) Describe the techniques, procedures, and methodologies to be used; (b) Describe data collection, analysis, and means of relationship interpretation; (c) Describe expected results or outcomes; and (d) Describe the procedures for evaluating project efficacy, including fixed performance indices with probabilities for obtaining them.

  - Qualifications, Experience, and Past Performance – (Attachment A, Section III) - Describe who will carry out the project activities.  List all project personnel, including consultants.   Describe their responsibilities and the amount of time each will dedicate to the project.  Briefly describe how their experience and qualifications are appropriate to successfully achieve the stated objectives.

3. Project Budget

Submit a detailed budget breakdown (Attachment B).  The project budget should follow the budget categories in SF-424 A page A1.

The budget can be in page form or spreadsheet form (preferred).  Page form is provided in Attachment B.

The budget should contain the following (as applicable, not all projects will have all budget categories):

- Salaries and Wages.  Include all employees and their titles working on the project.

- Fringe Benefits.  Show rates/amounts.

- Travel and Per Diem.  For each trip, indicate the number of persons traveling, the total days they will be in travel status, and the total subsistence and transportation costs for that trip.

- Equipment. List each item of tangible, nonexpendable personal property having a useful life of more than one year and an acquisition cost of $5,000 or more per unit.

- Supplies and Materials.  Include consumable supplies and materials to be used in the project. Supplies can be listed as categories such as ‘field supplies ‘or ‘lab supplies’.

- Contractual. Show procurement contracts (rentals, licenses, insurance, subscriptions) and sub-contracts / consultant agreements.

- Construction. (omit this budget category since SA-CESU projects do not involve construction)

- Other Costs.  This should include the cost of duplication and printing, long distance telephone calls, equipment rental, postage, and other services not previously listed.

- Total Direct Charges.  This is the sum of all costs in a. through h.

- Indirect Charges.  The Southern Appalachian Mountains Cooperative Ecosystems Studies Unit (SA-CESU) has a negotiated indirect cost rate of no more than 17.5% on Modified Total Direct Costs.

Be aware that graduate student tuition, equipment and rental of non-university owned space are excluded from Total Direct Charges and result in Modified Total Direct Costs.  Indirect costs should be charged against the Modified Total Direct Costs.

- TOTALS.  Sum of i. and j. above.

C.  Submission Dates and Times:

All responses will be required to be submitted electronically through grants.gov.  The application package should consist of:

- The proposal

- The Budget Breakdown

- The family of SF-424 forms.

- An optional cover letter of submission

The electronic submission into Grants.gov is due by March 18, 2014 @ 12:00 p.m. Eastern Daylight Time. An application package received after the closing date and time will not be considered for award.  If it is determined that an application package will not be considered due to lateness, you will be so notified immediately.

D.  Submission Instructions and Information:

All Funding Opportunities and Notice of Intents are posted to Grants.Gov, www.grants.gov. Please access this website and download these documents by using the Funding Opportunity Announcement # P14AS….

When you are ready to submit your proposal there are two options. The preferred option is to access FedConnect, www.fedconnect.net. Your sponsored programs office may have already registered for an account, or you can request to register on your own, this is a free service.

Once you have singed in, there are two ways to search; by agency or reference number (Funding Opportunity Announcement #).

For an agency search, we are DOI – NPS (note DOI space hyphen space NPS), the search will not work unless you type it this way. Many announcements will appear, continue to look for the Funding Opportunity Announcement #.

The other way you can search is by reference number (Funding Opportunity Announcement #). This is the easiest way to find the announcement.

After you find the, reference number (Funding Opportunity Announcement #), click on the Title.

The next page is where you can upload your proposal, but you have to be registered in FedConnect. When a recipient submits a report via FedConnect, the Grant Document Owner will receive your proposal in the agency Grant writing system and a notification is sent via email.

FedConnect is not mandatory…(yet). Because of this, you may submit your proposal directly to Grant/Agreements Officer.

Late Submissions, Modifications, and Withdrawals of Application and/or Proposal - Any application package received after the exact time specified for receipt will not be considered in the original selection process unless the application is received before award is made and it is determined by NPS that the late receipt was due to mishandling by the Government.  Any modification of an application or quotation is subject to the same conditions stated above.

E.  Intergovernmental Review:

This funding opportunity is not subject to Executive Order (EO) 12372, “Intergovernmental Review of Federal Programs”.

F.  Funding Restrictions:

A CESU task agreement issued under the Southern Appalachian Mountains CESU Cooperative Agreement by the NPS, signed by the NPS, obligates NPS funds.  Costs incurred prior to receipt of a signed CESU task agreement may not be reimbursed. Once the CESU task agreement has been signed by the NPS, the recipient may incur costs as specified in their proposed and approved budget submittal. Funding for the first year does not guarantee funding in subsequent years.  A new set of SF-424 forms must be submitted for subsequent years.

# SECTION V.  Award Administration Information

A.  Award Notices:

Project work cannot begin before a fully executed copy of the CESU task agreement is approved, signed and awarded by the NPS.  The date of the award is the effective date that the project can start.

B.  Administrative and National Policy Requirements:

1.  Office of Management and Budget (OMB) Circulars

By accepting Federal assistance, your organization agrees to abide by the applicable OMB Circulars in the expenditure of Federal funds and performance under this program.  http://www.whitehouse.gov/omb/circulars/

2 CFR Part 220 (OMB Circular A-21) - Cost Principles for Educational Institutions

2 CFR Part 225 (OMB Circular A-87) - Cost Principles for State, Local and Indian Tribal Governments

2 CFR Part 230 (OMB Circular A-122) - Cost Principles for Non-Profit Organizations

2 CFR Part 215 (OMB Circular A-110) - Uniform Administrative Requirements for Grants and Other Agreements with Institutions of Higher Education, Hospitals and Other Non-Profit Organizations

OMB Circular A-133, "Audits of States, Local Governments, and Non-Profit Organizations."

2.   Standard Award Terms and Conditions

This agreement incorporates the Standard Award Terms and Conditions found at the following Department of the Interior website as if they were given here:  http://www.doi.gov/pam/TermsandConditions.html

Prohibition on Text Messaging and Using Electronic  Equipment Supplied by the Government while Driving. This executive order introduces a Federal Government-wide prohibition on the use of text messaging while driving on official business or while using Government-supplied equipment, driving company-owned or rented vehicles or GOV, or while driving POV when on official Government business or when performing any work for or on behalf of the Government.

Acceptance of a Federal Financial Assistance award from the Department of the Interior (DOI) carries with it the responsibility to be aware of and comply with the terms and conditions of award.  Acceptance is defined as the start of work, drawing down funds, or accepting the award via electronic means.  Awards are based on the application submitted to, and as approved by DOI and are subject to the terms and conditions incorporated either directly or by reference in the following:

- Program legislation/regulations.

- Special terms and conditions.

- Code of Federal Regulations/Regulatory Requirements, as applicable (Contact your program officer with any questions regarding the applicability of the following):

2 CFR Part 175 Trafficking Victims Protection Act of 2000

43 CFR 12(A) Administrative and Audit Requirements and Cost Principles for Assistance Programs

43 CFR 12(E)	Buy American Requirements for Assistance Programs

43 CFR 12(C) Uniform Administrative Requirements for Grants and Cooperative Agreements to State and Local

43 CFR 12(F)	Uniform Administrative Requirements for Grants and Cooperative Agreements with Institutions of Higher Education, Hospitals, other Non-Profit and Commercial Organizations

43 CFR 43 Government wide Requirements for a Drug-Free Workplace

43 CFR 42 Government wide Debarment and Suspension (Nonprocurement)

43 CFR 18 New Restrictions on Lobbying

3.  Compliance with Buy American Act:

a. Notice:  Pursuant to sec. 307 of the Omnibus Consolidated Appropriations Act of 1997, Public Law 104-208, 110 Stat. 3009, please be advised of the following:

In the case of any equipment or product that may be authorized to be purchased with financial assistance provided using funds made available in this act, it is the sense of the Congress that entities receiving the assistance should, in expending the assistance, purchase only American-made equipment and products.

b. Recipient agrees to follow the requirements in 43 CFR Part 12, Subpart E, Buy American Requirements for Assistance Programs.

4.  Opposition to Any Legislation - In accordance with the Department of the Interior, Environment, and Related Agencies Act, 2006, Title IV, Section 402, No part of any appropriation contained in this Act shall be available for any activity or the publication or distribution of literature that in any way tends to promote public support or opposition to any legislative proposal on which Congressional action is not complete other than to communicate to Members of Congress as described in 18 U.S.C. 1913.

5.  Endorsements -  Recipient shall not publicize or otherwise circulate, promotional material (such as advertisements, sales brochures, press releases, speeches, still and motion pictures, articles, manuscripts or other publications) which states or implies governmental, Departmental, bureau, or government employee endorsement of a product, service, or position which the recipient represents.  No release of information relating to this award may state or imply that the Government approves of the recipient’s work products, or considers the recipient’s work product to be superior to other products or services.

All information submitted for publication or other public releases of information regarding this project shall carry the following disclaimer:

The views and conclusions contained in this document are those of the authors and should not be interpreted as representing the opinions or policies of the U.S. Government.  Mention of trade names or commercial products does not constitute their endorsement by the U.S. Government.

Recipient must obtain prior Government approval for any public information releases concerning this award which refer to the Department of the Interior or any bureau or employee (by name or title).  The specific text, layout photographs, etc. of the proposed release must be submitted with the request for approval.

A recipient further agrees to include this provision in a subaward to and subrecipient, except for a subaward to a State government, a local government, or to a federally recognized Indian tribal government.

6.  Retention and Access Requirements for Records -  All recipient financial and programmatic records, supporting documents, statistical records, and other grants-related records shall be maintained and available for access in accordance with 43 CFR Subpart C, Section 12.82 for State, local and Indian tribal governments or Subpart F, Section 12.953 for institutions of higher education, hospitals, other non-profit and all other organizations.

7.  Increasing Seat Belt Use -  Recipients of grants/cooperative agreements and/or sub-awards are encouraged to adopt and enforce on-the-job seat belt use policies and programs for their employees when operating company-owned, rented, or personally owned vehicles. These measures include, but are not limited to, conducting education, awareness, and other appropriate programs for their employees about the importance of wearing seat belts and the consequences of not wearing them.

8.   Special Terms and Conditions.

a. Order of Precedence - Any inconsistency in the agreement shall be resolved by giving precedence in the following order:  (a) Any national policy requirements and administrative management standards; (b) 43 CFR Part 12; (c) requirements of the applicable OMB Circulars and Treasury regulations; (d) special terms and conditions; and (e) all agreement sections, documents, exhibits, and attachments; (f) and the recipient’s project proposal.

b. Amendments - The agreement may be amended by written agreement signed by both the recipient’s Authorized Representative and the NPS AO.  Administrative changes (i.e. NPS AO name change, etc.) which do not change the project management plan, NTE amount, etc. or otherwise affect the recipient may be signed unilaterally by the NPS AO.  Additionally, a unilateral amendment may be utilized if it should become necessary to suspend or terminate the agreement in accordance with 43 CFR, Subpart C, Section 12.83 for State, local and Indian tribal governments or Subpart F, Section 12.961 for institutions of higher education, hospitals, other non-profit and all other organizations.

All other changes shall be made by means of a bilateral amendment to the agreement.  No oral statement made by any person, or written statement by any person other than the NPS AO, shall be allowed in any manner or degree to amend or otherwise effect the terms of the agreement.

All requests for amendment of the agreement shall be made in writing, provide a full description of the reason for the request, and be sent to the attention of the NPS AO.  Any request for project extension shall be made at least 30 days prior to the expiration date of the agreement or the expiration date of any extension period that may have been previously granted.  Any determination to extend the period of performance or to provide follow-on funding for continuation of a project is solely at the discretion of the NPS.

c. Budget and Program Plan Revision - The budget plan is the financial expression of the project or program as approved during the award process.  Recipients are required to report deviations from budget and program plans and request prior approval for budget and program plan revisions.  Recipients are not required to request prior approval for deviations among approved direct cost categories when the cumulative amount of the transfer is less than 10 percent of that cost category.  However, the recipient must report any deviation to the NPS AO and Program Officer (PO).

d. Audit Requirements -  Non-Federal entities that expend $500,000 or more during a year in Federal awards shall have a single or program-specific audit conducted for that year in accordance with the Single Audit Act Amendments of 1996 (31 U.S.C. 7501-7507) and revised OMB Circular A-133, which is available at http://www.whitehouse.gov/omb/grants/grants_circulars.html.

Federal awards are defined as Federal financial assistance and Federal cost-reimbursement contracts that non-Federal entities receive directly from Federal awarding agencies or indirectly from pass-through entities. They do not include procurement contracts, under grants or contracts, used to buy goods or services from vendors.  Non-Federal entities that expend less than $500,000 for a fiscal year in Federal awards are exempt from Federal audit requirements for that year, except as noted in A-133, §_215(a), but records must be available for review or audit by appropriate officials of the Federal agency, pass-through entity, and General Accounting Office (GAO).

Audits shall be made by an independent auditor in accordance with generally accepted government auditing standards covering financial audits.  Additional audit requirements applicable to this agreement are found at 43 CFR 12.66 or 43 CFR 12.926, as applicable.  General guidance on the single audit process is included in a pamphlet titled, Highlights of the Single Audit Process" which is available on the internet at http://www.dot.gov/ost/m60/grant/sincontact.html.  Additional information on single audits is available from the Federal Audit Clearinghouse at http://harvester.census.gov/sac/ .

e. Metric Conversion - All performance and final reports, other reports, or publications, produced under this agreement, shall employ the metric system of measurements to the maximum extent practicable.  Both metric and inch-pound units (dual units) may be used if necessary during and transition period(s).  However, the recipient may use non-metric measurements to the extent the recipient has supporting documentation that the use of metric measurements is impracticable or is likely to cause significant inefficiencies or loss of markets to the recipient, such as when foreign competitors are producing competing products in non-metric units.

f. Officials Not to Benefit - No member of or delegate to Congress, or resident commissioner, shall be admitted to any share of this agreement, or to any benefit arising from it.  However, this clause does not apply to this agreement to the extent that this agreement is made with a corporation’s general benefit.

g. Deposit of Publications - In addition to any requirements listed in the Project Management Plan, two (2) copies of each applicable publication produced under this agreement shall be sent to the Natural Resources Library with a transmittal that identifies the sender and the publication, and states that the publication is intended for deposit in the Natural Resources Library.  Publications shall be sent to the following address:

U.S. Department of the Interior

Natural Resources Library

Interior Service Center

Gifts and Exchanges Section

1849 C Street, N.W.

Washington, D.C. 20240

h. Reimbursable Costs and Limitations:

The recipient shall not incur costs or obligate funds for any purpose pertaining to operation of the program or activities beyond the expiration date stated in the agreement.  The only costs which are authorized for a period of up to 90 days following the award expiration date are those strictly associated with closeout activities for preparation of the final report.

The NPS's financial participation is limited.  The NPS will only fund up to its share of those amounts requested in the project proposal and as are subsequently approved and funded in the agreement.  The recipient shall not be obligated to continue performance under the agreement or to incur costs in excess of the costs set forth in the proposal and subsequent agreement.  However, if the recipient chooses to expend funds in excess of the approved project budget, the recipient will be responsible to fund the excess without funding participation by the NPS.

i. Inspection - The NPS has the right to inspect and evaluate the work performed or being performed under this agreement, and the premises where the work is being performed, at all reasonable times and in a manner that will not unduly delay the work.  If NPS performs inspection or evaluation on the premises of the recipient or a subrecipient, the recipient shall furnish and shall require sub-recipients to furnish all reasonable facilities and assistance for the safe and convenient performance of these duties.

- Copyrights:

1.  For recipients subject to the administrative standards set forth in OMB Circular A-110, the following copyright provision, as implemented by 43 CFR 12.936(a), shall apply:

“The recipient may copyright any work that is subject to copyright and was developed, or for which ownership was purchased, under an award. The Federal awarding agency(ies) reserves a royalty-free, nonexclusive and irrevocable right to reproduce, publish, or otherwise use the work for Federal purposes, and to authorize others to do so.”

2.  For recipients subject to the administrative standards set forth in OMB Circular A-102 and the Grants Management Common Rule, the following copyright provision, as implemented by 43 CFR 12.74, shall apply:

“The Federal awarding agency reserves a royalty-free, nonexclusive, and irrevocable license to reproduce, publish or otherwise use, and to authorize others to use, for Federal Government purposes:

(a)  The copyright in any work developed under a grant, subgrant, or contract under a grant or subgrant; and

(b)  Any rights of copyright to which a grantee, subgrantee or a contractor purchases ownership with grant support.”

- Rights to Data - For recipients subject to the administrative standards set forth in OMB Circular A-110, the following provision, as implemented by 43 CFR 12.936(c), shall apply:

"The Federal Government has the right to:

(1)  Obtain, reproduce, publish or otherwise use the data first produced under an award; and

(2) Authorize others to receive, reproduce, publish, or otherwise use such data for Federal purposes.”

l. Procurement Procedures - It is a national policy to place a fair share of purchases with minority business firms.  The Department of the Interior is strongly committed to the objectives of this policy and encourages all recipients of its grants and cooperative agreements to take affirmative steps to ensure such fairness.  Positive efforts shall be made by recipients to utilize small businesses, minority-owned firms, and women's business enterprises, whenever possible. Recipients of Federal awards shall take all of the following steps to further this goal:

1.  Ensure that small businesses, minority-owned firms, and women's business enterprises are used to the fullest extent practicable.

2.  Make information on forthcoming opportunities available and arrange time frames for purchases and contracts to encourage and facilitate participation by small businesses, minority-owned firms, and women's business enterprises.

3.  Consider in the contract process whether firms competing for larger contracts intend to subcontract with small businesses, minority-owned firms, and women's business enterprises.

4.  Encourage contracting with consortiums of small businesses, minority-owned firms and women's business enterprises when a contract is too large for one of these firms to handle individually.

5.  Use the services and assistance, as appropriate, of such organizations as the Small Business Development Agency in the solicitation and utilization of small business, minority-owned firms and women's business enterprises.

9.  Central Contractor Registration (CCR) - Prior to award the Recipient shall register and maintain their own information with Dun & Bradstreet and the Central Contractor Registration System.

Obtain a valid Dun & Bradstreet Number (D&B) from Dun & Bradstreet @ http://www.dnb.com/or by calling them at 800-333-0505.

Register on the Central Contractor Registration System (CCR) @ http://www.ccr.gov

10.  Payments:

a.  Financial Management Service’s (FMS), Automated Standard Application for Payment (ASAP) System.  If recipient is registered in ASAP payments will be made through that system.

Payments will be made by the United States Department of Treasury, FMS, ASAP system.  ASAP is a recipient-initiated, on-line payment and information system for Financial Assistance Agreements that is recipient initiated.  The recipient will request federal funds that are due directly from the Federal Reserve Bank on a reimbursable basis.

The ASAP Requestor ID, furnished by the Department of Treasury, will be used to access the account to request reimbursement payments. The NPS NPS AO will create an ASAP Account ID unique to this agreement. The first nine characters will be the agreement number. The remaining three characters will identify NPS funding line items.  Drawdown of funds will be taken from specific lines on this agreement.  An amendment will be stamped to indicate the appropriate line number for the drawdown.

11. Property Management and Disposition - Any NPS property used or other property acquired under this agreement, including intangible property such as copyrights and patents shall be governed by the provisions of 43 CFR, Subpart C, Section 12.71 through 12.72 for State, local and Indian tribal governments or Subpart F, Section 12.930 through 12.937 for institutions of higher education, hospitals, other non-profit and all other organizations.  The NPS assumes no liability for any actions or activities conducted under this agreement except to the extent that recourse or remedies are provided by Congress under the Federal Tort Claims Act [28 U.S.C. 1346(b), 2401(b), 2671 - 2680, as amended by P.L. 89-506, 80 Stat. 306]".

C.  Reporting:

1.  For ASAP Recipients: - Federal Financial Reports:  Reports of expenditures are required as documentation of the financial status of awards according to the official accounting records of the recipient’s organization. The recipient shall submit a completed original and one copy of the quarterly FFR, the SF 425, Federal Financial Report (Short Form), (Down load the form at:  http://www.whitehouse.gov/OMB/grants/grants_forms.html to report the status of funds for this agreement.  In addition include separately, detailed information of costs, by budget categories that reflects the approved SF 424A, Budget Information.  The quarterly report(s) shall be sent to the NPS AO and are due 30 calendar days after the end of the quarterly reporting period.  The recipient will report program outlays and program income on a cash basis.

An original and one copy of the final FFR is due to the NPS AO no later than 90 calendar days after the expiration or termination of this agreement.

Recipients who are placed on agency review, shall submit an original and one completed copy of the SF 425, Federal Financial Report (Short Form), (Down load the form at: http://www.whitehouse.gov/OMB/grants/grants_forms.html to report the status of funds for each payment requested before reimbursement payments are made.  In addition include separately, detailed information of costs, by budget categories that reflects the approved SF 424A, Budget Information.  This does not relieve the recipient of the quarterly FFR requirement unless reimbursement is only requested on a quarterly basis.

The NPS AO may review the report for patterns of cash expenditures, including accelerated or delayed drawdowns, and to assess whether performance or financial management problems exist. Before submitting FFRs to the NPS AO, grantees must ensure that the information submitted is accurate, complete, and consistent with the grantee’s accounting system. The recipient’s Authorized Certifying Official’s signature on the FFR certifies that the information in the FFR is correct and complete and that all outlays and obligations are for the purposes set forth in agreement documents, and represents a claim to the Federal government. Filing a false claim may result in the imposition of civil or criminal penalties.

2.  Performance Reports - Recipient shall submit an annual performance report(s) to the NPS AO within 30 days after the end of the fiscal year.  The performance report must be prepared in accordance with 43 CFR, Subpart C, Section 12.80 for State, local and Indian tribal governments or Subpart F, Section 12.951 for institutions of higher education, hospitals, other non-profit and all other organizations.  The performance report shall include a narrative summary both of completed activities and activities in progress, a calculation of percent of completed work based on work identified in the Project Management Plan, the reason for slippage if objectives or milestones are not met, a prediction of future activities and how they will be accomplished, and a discussion of issues and problems which may impact the ability to complete the work on time.  Recommendations to overcome problems shall also be provided.

In lieu of the fourth quarter performance report an annual program performance report shall be submitted at the end of each year of the agreement.  An original shall be submitted to the NPS AO no later than 90 days following the end of each year of the agreement.  Copies of this report may be required to be included with any application for continuing support of the agreement

An original of the final program performance report shall be submitted no later than 90 days following the expiration or termination of the agreement.

3. Non-compliance - Failure to comply with the reporting requirements contained in this agreement may be considered a material non-compliance with the terms and conditions of the award.  Non-compliance may result in withholding of future payments, suspension or termination of the agreement, recovery of funds paid under the agreement, and withholding of future awards.

D.  DEFINITIONS:.

1.  Agreement – The CESU Task Agreement under the Southern Appalachian Mountain CESU Cooperative Agreement

2.  Agreements Officer (NPS AO) - The NPS's Agreements Officer.  The NPS AO is the only individual authorized to obligate funds, award, modify or terminate an agreement.

3.  Agreements Technical Representative (ATR) - The NPS employee designated for the purpose of administering the technical aspect of an agreement.  The ATR is authorized to clarify technical requirements, and to review and approve work which is clearly within the scope of the work specified in an agreement.  The ATR is not authorized to issue changes or in any other way modify an agreement.

4.  The National Park Service (NPS) - May also be referred to as the Service.

5.  The Code of Federal Regulations (CFR) – General and permanent regulations issued by Executive departments and agencies of the Federal Government.

6.  Fiscal Year (FY) - The Federal fiscal year which extends from October 1 of one year through September 30 of the following year.

7.  Not-to-Exceed (NTE) Amount - The maximum Federal funding amount.

8.  The Office of Management and Budget (OMB) -

9.  Project Manager/Principal Investigator - The recipient's Project Manager/Principal Investigator.

10.  Responsible Official: The recipient's Responsible Official -  The responsible official is the individual who is authorized to act for the recipient’s organization and commit the recipient to compliance with the terms and conditions of this agreement.

E.  Financial Support.

1.  An agreement shall be funded each FY based on the availability of NPS funding. The recipient hereby releases the NPS from all liability due to failure of Congress to appropriate funds for the agreement.

2.  Funds obligated but not expended in one FY can be carried forward and expended in the subsequent FY.

3.  The dollar amount represents the estimated not-to-exceed (NTE) amount for which the NPS will be responsible under the terms of the agreement. The NPS shall not be obligated to pay for nor shall the recipient be obligated to perform any effort that will require the expenditure of Federal funds above the NTE amount.

4.  Program income for the agreement shall be in accordance with 43 CFR, Subpart F, Section 12.924.

-- END OF PROGRAM ANNOUNCEMENT –

ATTACHMENT A

U.S. DEPARTMENT OF THE INTERIOR

BUREAU OF LAND MANAGEMENT

CERTIFICATION FOR FEDERAL ASSISTANCE

Certification Regarding Lobbying - Certification for Contracts, Grants, Loans, and Cooperative Agreements.  Applies to recipients of awards exceeding $100,000.

This certification is required by Section 1352, title 31, U.S. Code, entitled "Limitation on use of appropriated funds to influence certain Federal contracting and financial transactions."

The undersigned certifies, to the best of his or her knowledge and belief, that:

(1)  No Federal appropriated funds have been paid or will be paid, by or on behalf of the undersigned, to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment, or modification of any Federal contract, grant, loan, or cooperative agreement.

(2)  If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned shall complete and submit Standard Form-LLL, "Disclosure Form to Report Lobbying," in accordance with its instructions.

(3)  The undersigned shall require that the language of this certification be included in the award documents for all subawards at all tiers (including subcontracts, subgrants, and contracts under grants, loans, and cooperative agreements) and that all subrecipients shall certify accordingly.

This certification is a material representation of fact upon which reliance was placed when this transaction was made or entered into.  Submission of this certification is a prerequisite for making or entering into this transaction imposed by Section 1352, title 31, U.S. Code.  Any person who fails to file the required certification shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

As the authorized certifying official, I hereby certify that the above specified certifications are true.

Signature & Date____________________________________________________________________________

Typed name and Title ________________________________________________________________________

Applicant/Recipient Name ____________________________________________________________________

ATTACHMENT B

PROPOSAL SUBMISSION FORMAT

Please read the announcement carefully before completing this information.

Section I.  Purpose, Objectives, and Relevance

A.	Describe why the project is needed by the applicant.

B.	Describe the applicant’s objectives.

- Describe how the applicant’s objectives support their mission and how this project benefits the Public.

SECTION II.  TECHNICAL APPROACH

Describe how the applicant proposes to conduct and achieve the project in accordance with the Statement of Joint Objectives in Section I.  The project design must contain enough detail to show the development of the project and the relationship between the partners, milestones, and objectives.  The work plan must be clear, suitable, and feasible with respect to the following;  (a) Describe the techniques, procedures, and methodologies to be used; (b) Describe data collection, analysis, and means of interpretation; (c) Describe expected results or outcomes; and (d) Describe the procedures for evaluating project effectiveness, including fixed performance indices with probabilities for obtaining them.

Section iii.  QUALIFICATIONS, EXPERIENCE, PAST PERFORMANCE

Describe who will carry out the project activities.  List all project personnel, including consultants.   Describe their responsibilities and the amount of time each will dedicate to the project.  Briefly describe how their experience and qualifications are appropriate to successfully achieve the stated objectives.

# Attachment C

# section iv.  Budget

This is a suggested format for the applicant to use for the detailed budget/costs breakdown of cost categories identified on the SF-424A, Budget Information. Each cost item should clearly show how the total charge for that item was determined.  All major costs should be listed in budget categories similar to those listed below, and all cost items should be explained in the Budget Justification.

| A. Salaries and Wages. Provide the names and/or titles of key project personnel. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Name/Title of Position | Full Time Monthly Salary | % FTE | No. of Months | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  | $ |  |  | $ | $ | $ | $ |
|  | $ |  |  | $ | $ | $ | $ |
|  | $ |  |  | $ | $ | $ | $ |
|  | $ |  |  | $ | $ | $ | $ |
|  | $ |  |  | $ | $ | $ | $ |
| Subtotal |  |  |  | $ | $ | $ | $ |

| B. Fringe Benefits. If more than one rate is used, list each rate and the wage or salary base. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Rate | Salary or Wage Base | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
| Subtotal |  | $ | $ | $ | $ |

| C. Consultant/Contracting Fees. This should include payments for professional and technical consultants participating in the project. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name and type of Consultant | # of Days | Daily Rate of Compensation | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ | $ |
| Subtotal |  |  | $ | $ | $ | $ |

| D. Travel and Per Diem. For each trip, indicate the number of persons traveling, the total days they will be in travel status, and the total subsistence and transportation costs for that trip. Per diem rates shall not exceed maximum Federal rates. To view current Federal per diem rates, visit http://www.gsa.gov/Portal/gsa/ep/channelView.do?pageTypeId=8203&channelId=-15943and follow the links to per diem information. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| From/To | No. of People | No. of Travel Days | Per diem (lodging and meals) per person per day | Total per diem (lodging and meals) for this trip | Transportation costs (airfare and mileage) per person | Total transportation costs (airfare and mileage) for this trip | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ | $ | $ | $ | $ |
| Subtotal |  |  |  |  |  |  | $ | $ | $ | $ |

| E. Supplies and Materials. Include consumable supplies and materials to be used in the project, listing each item and quantity individually. Include items of expendable equipment, i.e., equipment costing less than $500 or with an estimated useful life of less than two years. Equipment costing more than that should be listed in the Other Costs category (Category G, below). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | # of items | Cost | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  |  |  | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ |
|  |  |  | $ | $ | $ | $ |
| Subtotal |  |  | $ | $ | $ | $ |

| F. Services. This should include the cost of duplication and printing, long distance telephone calls, equipment rental, postage, and other services not previously listed. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Item | Method of Computation | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  |  | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ |
|  |  | $ | $ | $ | $ |
| Subtotal |  | $ | $ | $ | $ |

| G. Other Costs. List equipment items in excess of $500, and other items not previously listed. Note that equipment items worth less than $500 or that have a useful life of less than 2 years must be listed in the Supplies and Materials category. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Item | Cost | Grant Funds | Match / Cost Share (if any) | Third Party Share (if any) | Total |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
|  | $ | $ | $ | $ | $ |
| Subtotal |  | $ | $ | $ | $ |

| H. Indirect Costs. If indirect costs will be charged to the grant, complete the table below with your current approved indirect cost rate and the direct costs it will be applied to. A copy of your most recent indirect cost rate must be attached if indirect costs will be requested. |  |  |
| --- | --- | --- |
| * The Direct Costs from items A -- F to which the indirect cost rate applies | Current Approved Indirect Cost Rate Percentage (%) | Indirect Cost Rate Amount |
| $ | % | $ |

- Budget Justification. Provide a brief narrative justification of all cost items, including matching funds, listed in the budget. Be specific and explain why these items are necessary to accomplish the grant objectives. Travel Costs: If the project involves travel costs, include a brief summary of each trip (for example, Project Director and two students will fly from Hometown to Someplace and stay three days to examine Someplace Museum’s collection). Travel is limited to this project only. Equipment. If purchasing or renting computer equipment or other large budget items follow the procedures in 43CFR, Subpart C, Section 12.76 for State, local and Indian tribal governments or Subpart F, Section 12.940 through 12.948 for institutions of higher education, hospitals, other non-profit and all other organizations, as applicable.