## Instructions
OMB Control No. 0648-0384
Instructions | Expiration Date 01/31/2025
Please follow instructions below to fill out your milestone chart ("Milestone chart" tab). See example milestone charts under "Example" tabs.
For FFO-2023, the anticipated project start date is October 1, 2023. Please align your milestones and tasks in this Gantt chart using the start date proposed in your application
1. Fill out Columns A-E as follows (See "Example" tabs):
a. Each task (column B) should fit under a project milestone (in bold, column A). Please add additional milestones in column A as needed and add the associated tasks for each milestone in separate rows in column B.
b. Please provide a category of your choosing for each task in column C. Suggestions include (but are not limited to): Field Preparation, Field Work Sampling, Lab Analyses, Data Analyses, Data Management, Outreach, Reporting/Publications, Meetings. You may have different task categories under a single milestone (e.g., see milestone 2 in “Example” tab).
c. Please add the start date and completion date for each task in columns D and E, respectively.
Note: Although the template only contains 3 milestones with 3 tasks each, there is no limit to the number of milestones or tasks associated with each milestone.
2. Using the timeline provided in rows 1 through 3, please fill in the appropriate cells for each task using blue that corresponds to the start and completion date provided in columns D and E, respectively. Blue cells can be continuous (e.g., from 10/1/2023- 9/30/2027) or on a frequency of your choosing (e.g., bi-monthly or quarterly meetings).
3. Using the timeline provided in rows 1 through 3, please fill in the appropriate cells for each milestone using green that corresponds to the start and completion date of all of the tasks associated with that milestone.
4. Please save the spreadsheet as "[PI Last Name- Project title keyword- milestone chart]" and submit the file along with your full application to Grants.gov ahead of the deadline for this funding opportunity

## Milestone Chart
Milestone | Task | Task Category | Task Start Date | Task Completion Date | 2023 |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[5 empty] | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Milestone 1: [Enter name of milestone] | bar: Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A
1.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
1.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
1.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Milestone 2: [Enter name of milestone] | bar: Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A
2.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
2.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
2.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Milestone 3: [Enter name of milestone] | bar: Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A; Q1 O to Q4 A
3.1 | [Enter first task] | [Enter category] | [Enter start date] | [Enter due date]
3.2 | [Enter second task] | [Enter category] | [Enter start date] | [Enter due date]
3.3 | [Enter third task] | [Enter category] | [Enter start date] | [Enter due date]
Etc.

## Example (research project)
| Task | Task Category | Task Start Date | Task Completion Date | 2023 |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[5 empty] | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Milestone 1: Meetings | bar: Q1 O to Q4 S
1.1 | Project team meeting - planning refresh | Meetings | 2023-10-01 | 2023-10-31 | bar: Q1 O
1.2 | Project team meetings with external stakeholders | Meetings | 2023-11-01 | 2028-03-31 | bar: Q1 N; Q3 M; Q3 M; Q2 F; Q2 J; Q4 A; Q2 F
1.3 | Project team meetings - adaptive planning of research design/methods | Meetings | 2023-12-01 | 2027-01-31 | bar: Q1 D to Q2 J; Q2 J; Q1 D; Q1 N
1.4 | Project team - communications and transfer of findings | Meetings | 2024-08-01 | 2027-08-31 | bar: Q4 A; Q3 A; Q3 A; Q3 A to Q3 M; Q3 A
1.5 | Project team - application of findings check in | Meetings | 2024-10-01 | 2027-09-30 | bar: Q1 O; Q1 O; Q1 O; Q1 O; Q4 J
1.6 | Conference calls with technical monitors | Meetings | 2023-10-01 | 2027-09-30 | bar: Q1 O; Q2 J; Q3 M; Q1 O; Q3 M; Q1 O; Q3 M; Q1 O; Q3 M; Q1 O; Q3 M
1.7 | Site visit with technical monitors (annual) | Meetings | 2024-08-01 | 2027-09-30 | bar: Q4 A; Q3 A; Q3 A; Q3 A; Q3 A
Milestone 2: Field Data Collection | bar: Q2 M to Q4 J
2.1 | Expedition #1: Pre-Expedition Preparation | Cruise | 2024-03-01 | 2024-04-30 | bar: Q2 M to Q3 A
2.2 | Expedition #1: Full Depth Cruise | Cruise | 2024-05-01 | 2024-06-30 | bar: Q3 M to Q3 J
2.3 | Expedition #2: Pre-Expedition Preparation | Cruise | 2025-03-01 | 2025-04-30 | bar: Q2 M to Q3 A
2.4 | Expedition #2: Mesophotic Cruise 1 | Cruise | 2025-05-01 | 2025-06-30 | bar: Q3 M to Q3 J
2.5 | Expedition #3: Pre-Expedition Preparation | Cruise | 2026-03-01 | 2026-04-30 | bar: Q2 M to Q3 A
2.6 | Expedition #3: Mesophotic Cruise 2 | Cruise | 2026-05-01 | 2026-06-30 | bar: Q3 M to Q3 J
2.7 | Expedition #4: Pre-Expedition Preparation | Cruise | 2027-03-01 | 2027-04-30 | bar: Q2 M to Q3 A
2.8 | Expedition #4: Mesophotic Cruise 3 | Cruise | 2027-05-01 | 2027-06-30 | bar: Q3 M to Q3 J
Milestone 3: Field Data Processing | bar: Q4 J to Q4 A
3.1 | Voucher specimens curation | Data Processing | 2024-07-01 | 2027-12-01 | bar: Q4 J to Q4 S; Q4 J to Q4 S; Q4 J to Q4 S; Q4 J to Q4 S
3.2 | DNA extractions | Data Processing | 2024-08-01 | 2028-04-01 | bar: Q4 A to Q1 N; Q4 A to Q1 N; Q4 A to Q1 N; Q4 A to Q1 N
3.3 | DNA barcoding | Data Processing | 2024-11-01 | 2027-04-30 | bar: Q1 N to Q3 A; Q1 N to Q3 A; Q1 N to Q3 A; Q1 N to Q3 A
3.4 | Publication of DNA barcoding data on GenBank | Data Management | 2028-05-01 | 2028-08-31 | bar: Q3 A to Q4 A
3.5 | RAD Sequencing Contracting | Admin | 2024-08-01 | 2024-08-31 | bar: Q4 A
3.6 | RAD Sequencing | Data Processing | 2024-09-01 | 2028-06-01 | bar: Q4 S to Q2 F; Q4 S to Q2 F; Q4 S to Q2 F; Q4 S to Q2 F
3.7 | RADseq data QAQC and filtering | Data Processing | 2025-01-01 | 2028-03-31 | bar: Q2 J to Q2 M; Q2 J to Q2 M; Q2 J to Q2 M; Q2 J to Q2 M
Milestone 4: Data Interpretation | bar: Q3 A to Q4 A
4.1 | Analyses of spatial population genetic structuring | Data Analysis | 2025-04-01 | 2028-06-30 | bar: Q3 A to Q3 J; Q3 A to Q3 J; Q3 A to Q3 J; Q3 A to Q3 J
4.2 | Analyses of genetic connectivity rate and directionality | Data Analysis | 2025-07-01 | 2027-08-31 | bar: Q4 J to Q4 A; Q4 J to Q4 A; Q4 J to Q4 A
4.3 | Integration of population genetic and modeling data | Modeling | 2025-08-01 | 2028-08-31 | bar: Q4 A to Q4 A
4.4 | Larval Dispersal modeling | Modeling | 2026-11-01 | 2028-08-31 | bar: Q1 N to Q4 A
Milestone 4: Publications | bar: Q3 J to Q4 S
5.1 | Cruise Reports | Publication | 2024-06-01 | 2027-07-31 | bar: Q3 J to Q4 J; Q3 J to Q4 J; Q3 J to Q4 J; Q3 J to Q4 J
5.2 | Dissemination of cruise metadata | Data Management | 2024-11-01 | 2027-12-31 | bar: Q1 N to Q1 D; Q1 N to Q1 D; Q1 N to Q1 D; Q1 N to Q1 D
5.3 | Completion of peer-reviewed publications | Publication | 2026-01-01 | 2028-09-30 | bar: Q2 J to Q4 S
Milestone 6: Outreach | bar: Q3 M to Q2 M
6.1 | Stakeholder workshops | Workshop | 2024-05-01 | 2028-02-28 | bar: Q3 M; Q3 M; Q2 J; Q2 F
6.2 | Training sessions for resource managers | Workshop | 2024-10-01 | 2027-10-31 | bar: Q1 N; Q1 O; Q1 O
6.3 | Scientific Meeting | Presentations | 2024-09-01 | 2028-03-31 | bar: Q4 S to Q2 M
6.4 | End of Project workshop | Workshop | 2028-03-01 | 2028-03-31 | bar: Q2 M
Milestone 7: Reporting | bar: Q2 M to Q4 S
7.1 | Progress reports | Data Management | 2024-03-01 | 2028-09-30 | bar: Q2 M; Q4 S; Q2 M; Q4 S; Q2 M; Q4 S; Q2 M; Q4 S; Q2 M; Q4 S
7.2 | Final Report | Data Management | 2028-07-01 | 2028-09-30 | bar: Q4 J to Q4 S
7.3 | Archive annotated video frames at DSCRTP w/in 6 months after cruise | Data Management | 2024-07-01 | 2028-08-31 | bar: Q3 J to Q4 A; Q3 J to Q4 A; Q3 J to Q4 A; Q3 J to Q4 A; Q3 J to Q4 A
7.4 | Archive coral specimens at NOAA/Harvey Mudd/Smithsonian within 1 yr from collection | Data Management | 2025-02-01 | 2028-02-28 | bar: Q2 F; Q2 F; Q2 F; Q2 F
7.5 | Archive CTD data at NCEI within 1 year from collection | Data Management | 2025-02-01 | 2028-02-28 | bar: Q2 F; Q2 F; Q2 F; Q2 F
7.6 | Archive video at NCEI at end of project | Data Management | 2027-11-01 | 2028-08-31 | bar: Q1 N to Q4 A
7.7 | Archive genetic data at NCBI/Dryad at time of publication | Data Management | 2027-11-01 | 2028-08-31 | bar: Q1 N to Q4 A
7.8 | Archive model output at NCEI at time of publication | Data Management | 2027-11-01 | 2028-08-31 | bar: Q1 N to Q4 A