## LOE (hidden)
Proposed Staff |  | Position Title | Labor Category | Logistics | Team Planning Meeting | Data Collection and Work Plan | Desk Review | Travel to Field (Barbados) | Pilot test tools in Barbados | Inbrief & Training (Barbados) | Barbados + travel | St Lucia + travel | Dominica + travel | Trinidad and Tobago + Travel | Suriname + travel | Guyana + travel | St. Kitts and Neviss + travel | Antigua and Barbudas + travel | St. Vincent and Grenadines + travel | Grenada + travel | Return Home | Data Analysis | Draft Report, Concept Note, and Annex Writing | Final Report Writing | Quality Assurance | Total
[5 empty] | Pre-Departure Planning |  |  | Field Work | [13 empty] | Data Analysis and Reporting
Technical Team
Team A | Bertrand Laurent | Team Leader |  |  | 1 | 3 | 2 | 1 | 2 | 2 | 6 | 5 | 5 |  |  |  | 5 | 5 | 5 | 5 | 1 | 6 | 6 | 3 |  | 63
| Sharene Mckenzie | Subject Matter Expert |  |  | 1 | 1 | 2 | 1 | 1 | 2 | 6 | 5 | 5 |  |  |  | 5 | 5 | 5 | 5 | 1 | 4 | 2 | 1 |  | 52
| Danielle De Garcia | Evaluation Methods Specialist |  |  | 1 | 2 | 2 | 1 | 2 | 2 | 6 | 5 | 5 | [7 empty] | 1 | 2 | 2 | 1 |  | 32
| Aaron Foss | Youth Specialist |  |  | 1 |  | 1 | 1 |  | 2 | 6 | 5 | 5 | [7 empty] | 1 | 1 | 1 |  |  | 24
Team B | Nicole Hazel | Deputy Team Leader |  |  | 1 | 3 | 2 | 1 | 2 | 2 |  |  |  | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 5 | 5 | 2 |  | 60
| Henry Charles | Subject Matter Expert |  |  | 1 | 1 | 2 | 1 | 1 | 2 |  |  |  | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 4 | 2 | 1 |  | 52
| Mateusz Pucilowski | Evaluation Methods Specialist |  |  | 1 | 2 | 2 | 1 | 2 | 2 |  |  |  | 6 | 5 | 5 |  |  |  |  | 1 | 2 | 2 | 1 |  | 32
| Rajwantie Sahai | Youth Specialist/PM |  | 2 | 2 |  | 1 | 1 |  | 2 |  |  |  | 6 | 5 | 5 |  |  |  |  | 1 | 1 | 1 |  | 2 | 29
Support Team
Andrew Green |  | STA |  |  | 1 | 1 | [16 empty] | 1 | 1 | 1 | 5
Rashida Beckles |  | Local Logistician (ODC) |  | 15 | [21 empty] | 15
Julie Mandolini-Trummel |  | Program Assistant |  | 8 | 1 | [19 empty] | 1 | 10
TOTAL |  |  |  | 25 | 11 | 13 | 14 | 8 | 10 | 16 | 24 | 20 | 20 | 24 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 25 | 22 | 10 | 4 | 374

## Work Plan
| Name of Project |  |  |  | YEAR 1 | [11 empty] | Year 2
|  | 2015-08-31 | 2015-09-07 | 2015-09-14 | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Start-Up Activities | Kick-off Meeting w/ CSO
Develop Final Work Plan for CSO review
Project Activities | Analysis
Trainings
Dialogues
Monitoring and Evaluation | Baseline Assessement
Mid-term Review
Final Evaluation
Monitoring Visits
Reporting | Quarterly Reports
Monthly Meetings with CSO
Final Report

## Org Chart (hidden)
Organizational Chart
Local Logistician
Rashida Beckles