## Ext. Activity Timeline
Addressing Child Trafficking in Senegal
Anti-Trafficking in Persons Organization ABC
Project Start Date: | 2017-10-01
Project End-date: | 2018-09-30
Activity | Responsible | Q1 (FY 17) |  |  | Q2 (FY 18) |  |  | Q3 (FY 18) |  |  | Q4 (FY 18)
|  | Jul. | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Jan. | Feb. | Mar.
Objective 1: Increase the capacity of law enforcement and legal system personnel to identify and combat trafficking of talibechildren.
Obtain a list of police officers in Dakar and Pikine from the National Police to undergo the Leahy vetting process. | Project Officer, CNLTP | bar: Q1 (FY 17) Sept.
Identify gaps & refine existing anti-trafficking and referral system traininng modules. | Project Officer, Child Protection Advisor (Plan) | bar: Q1 (FY 17) Sept. to Q2 (FY 18) Oct.
Organize 2 training sessions for police on anti-trafficking legislation and child-friendly justice. | Project Officer | bar: Q2 (FY 18) Nov. to Q2 (FY 18) Dec.
Contact Presidents of the court systems in Saint Louis and Pikine for permission to obtain court related, police and gendarmarie records pertaining to prosecutions and arrests | Project Officer | bar: Q2 (FY 18) Oct. to Q2 (FY 18) Nov.
Analyze court and police records for monitoring and evaluation purposes. | Project Officer, Plan Senegal M&E Advisor | bar: Q2 (FY 18) Dec.
Identify and invite participants from Koranic teachers associations, the Daara Inspectorate, Civil Society Organizations, Parlamentarians and other relevant stakeholders to participate in discussions around Daara regulation. | Project Officer, Child Protection Advisor (Plan) | bar: Q2 (FY 18) Oct.
Organize 2 workshops to finalize proposed amendments to the draft bill to increase Daara regulation at the national level. | Project Officer, Child Protection Advisor (Plan) | bar: Q2 (FY 18) Nov. to Q2 (FY 18) Dec.
Convene the CSO working group to discuss and plan ways to support the government in their initiative to remove children from the street and increase care and rehabilitation of talibe in St Louis and Pikine. (1 per month) | Project Officer, Child Protection Advisor (Plan) | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Objective 2: Strengthen the referral system for trafficking victims.
Organize 7 training sessions (4 in Pikine and 3 in Saint Louis) for journalists, district and community level child protection committees on the referral system procedures, referral services and tracking informaton. | ENDA Pikine | bar: Q2 (FY 18) Oct. to Q2 (FY 18) Nov.
Objective 3: Raise awareness of the risks and prevalence of trafficking among talibes.
Organize 30 awareness raising forums in areas that have not yet been reached. (15 in Pikine and 15 in Saint Louis) | ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Identify topics for discussion and CBOs to be guests on interactive radio programs (20) to raise awarenss of child trafficking and the support services and mechanisms available to support them. | ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Objective 4: Increase available community-based services for talibe trafficking victims and children culnerable to trafficking.
Organize 8 (4 in Saint Louis + 4 in Pikine) workshops for CBOs, NGOs and collectives to brainstorm actions and measures to regulate the installation of Daaras in their respective municipalities. | ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Promote and support 4 local initiatives to regulate the installation of Daaras. | ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct. to Q3 (FY 18) Jan.
Engage CBOs and assist them in developing action plans for their communities (at least 2 youth associations included). | ENDA Saint Louis | bar: Q2 (FY 18) Oct. to Q2 (FY 18) Nov.
Support CBOs in implementing their action plans and provide guidanc on monitoring progress on activities. | ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Conduct surveys with public and private CBOs to gather information on the number of children who received services and were correctly referenced by police, local CBOs and committees, etc. (Saint Louis and Dakar/Pikine) | Project Officer, ENDA Saint Louis + Pikine | bar: Q2 (FY 18) Oct.; Q3 (FY 18) Feb.; Q4 (FY 18) Mar.
Organize 2 data analyzing workshops to discuss and share status of CBO implemented action plans. | ENDA Saint Louis + Pikine | bar: Q3 (FY 18) Jan. to Q3 (FY 18) Feb.; Q4 (FY 18) Jan. to Q4 (FY 18) Feb.
Monitoring and Evaluation (General)
12 monitoring visits to assist and observe project activites as well as supervise monitoring efforts (6 to Saint Louis and 6 to Pikine). | Project Officer | bar: Q2 (FY 18) Oct. to Q4 (FY 18) Mar.
Develop terms of reference for the recruitment of a consultant to conduct the final project evaluation. | Plan USA & Project Officer | bar: Q2 (FY 18) Oct.
Recruitment and selection of the final evaluation consultant. | Plan USA & Project Officer | bar: Q2 (FY 18) Nov. to Q2 (FY 18) Dec.
Conduct final evaluation | Plan USA & Project Officer | bar: Q4 (FY 18) Jan. to Q4 (FY 18) Mar.