Department of Energy

National Nuclear Security Administration

Office of Acquisition Management

DNN R&D University Program:

Consortium for Nuclear Forensics

____________________________________________________________________________

Notice for Funding Opportunity Announcement (FOA) Number:

DE-FOA-0002781

FOA Type:  Initial

CFDA Number:  81.113

| FOA Issue Date: | August 4, 2022 |
| --- | --- |
| Submission Deadline for Letter of Intent: | N/A |
| Submission Deadline for Concept Papers: | N/A |
| Submission Deadline for Pre-Applications: | N/A |
| Submission Deadline for Applications: | September 20, 2022 23:59:59 PM ET |
| Expected Date for Selection Notifications: | January 2023 |

TABLE OF CONTENTS

FUNDING OPPORTUNITY ANNOUNCEMENT OVERVIEW	4

Section I - FUNDING OPPORTUNITY DESCRIPTION	8

Section II - AWARD INFORMATION	13

Section III - ELIGIBILITY INFORMATION	14

Section IV - APPLICATION AND SUBMISSION INFORMATION	20

Pre-award terminology	20

Applicant (Prime) – An organization submitting an application to DOE/NNSA for assistance under this Funding Opportunity Announcement.	20

Sub-applicant - An organization submitting a sub-application as part of a larger application package to an Applicant for assistance.	20

Post-award terminology	20

Recipient - An Applicant whose application has been approved and federal award obligated.	20

A.	Application Process	20

B.	Address to Request Application Package	20

C.	Letter of Intent and Pre-Application	21

1.	Letter of Intent	21

2.	Pre-application	21

D.	Content and Application Forms	21

1.	Application for Federal Assistance SF-424 (R&R) [MANDATORY for Prime Applicant and Sub-Applicants]	21

2.	Research and Related Other Project Information [MANDATORY for Prime Applicant]	22

3.	Project Summary/Abstract (Field 7 of the R&R Other Project Information form) [MANDATORY for Prime Applicant]	22

4.	Project Narrative and Appendices (Field 8 of the R&R Other Project Information form) [MANDATORY for Prime Applicant]	23

5.	Other Attachments (Not part of the 30 page limit)	27

6.	SF424 Research and Related Budget and Information	29

7.	Sub-Applicant Submittal Instructions	32

8.	Attachments Form [MANDATORY for Prime Applicant]	33

9.	Financial Assistance Environmental Checklist (Attachment C) [MANDATORY for Prime Applicant if selected for award]	33

10.	Project/Performance Site Location(s) [MANDATORY submittal for Prime Applicant to also include sub-applicant information]	33

11.	Certification Regarding Lobbying or Disclosure of Lobbying Activities	34

12.	List of Assurances and Certifications [MANDATORY for Prime Applicant and Sub-Applicants in SAM.gov]	35

13.	Requirements for Pass-Through Entities [MANDATORY for Prime Applicant]	35

E.	Summary of Required Forms and Files	36

F.	Submissions from Successful Applicants	39

G.	Submission Dates and Times	39

H.	Intergovernmental Review	39

I.	Funding Restrictions (December 2014)	39

Section V - APPLICATION REVIEW INFORMATION	41

A.	Criteria	41

1.	Initial Review Criteria	41

2.	Merit Review Criteria	41

B.	Review and Selection Process	42

1.	Merit Review	42

2.	Selection Official Consideration	43

3.	Review of Risk	43

4.	Reporting of Matters Related to Recipient Integrity and Performance (December 2015)	43

3.	Government Discussions with Applicant (December 2014)	43

C.	Anticipated Notice of Selection and Award Dates	44

Section VI - AWARD ADMINISTRATION INFORMATION	45

A.	Award Notices	45

1.	Notice of Selection	45

2.	Non-selected Notification	45

3.	Notice of Award (December 2014)	45

B.	Administrative and National Policy Requirements	45

C.	Reporting	46

D.	Applicant Representations and Certifications	47

Section VII - QUESTIONS/AGENCY CONTACTS	49

A.	Questions	49

B.	Agency Contact	49

Section VIII - OTHER INFORMATION	50

A.	Modifications	50

B.	Government Right to Reject or Negotiate	50

C.	Commitment of Public Funds	50

D.	Proprietary Application Information	50

E.	Evaluation and Administration by Non-Federal Personnel	51

F.	Intellectual Property Developed Under this Program	51

G.	Notice of Right to Request Patent Waiver	51

H.	Notice Regarding Eligible/Ineligible Activities	51

I.	Protected Personally Identifiable Information	52

J.	Annual Compliance Audits	52

Section IX - APPENDICES/REFERENCE MATERIAL	53

C.	DATA MANAGEMENT PLAN GUIDANCE (SEPT 2015)	53

# FUNDING OPPORTUNITY ANNOUNCEMENT OVERVIEW

Questions

Questions regarding the content of the funding opportunity announcement must be submitted through the FedConnect portal. You must register with FedConnect to respond as an interested party to submit questions, and to view responses to questions. It is recommended that you register as soon after release of the FOA as possible to have the benefit of all responses. DOE/NNSA will try to respond to a question within 3 business days, unless a similar question and answer have already been posted on the website. For instructions on registering for FedConnect, refer to the website: www.fedconnect.net.

Questions relating to the Grants.Gov registration process, system requirements, or how an application form works must be directed to Grants.gov at 1-800-518-4726 or support@grants.gov.

Grants.gov Application Submission and Receipt Procedures

This section provides the application submission and receipt instructions for U.S. Department of Energy/National Nuclear Security Administration (DOE/NNSA) program applications. Please read the following instructions carefully and completely.

- Electronic Delivery

The DOE/NNSA is participating in the Grants.gov initiative to provide the grant community with a single site to find and apply for grant funding opportunities. DOE/NNSA encourages applicants to submit their applications online through Grants.gov.

- How to Register to Apply through Grants.gov

  - Instructions: Read the instructions below about registering to apply for DOE/NNSA funds. Applicants should read the registration instructions carefully and prepare the information requested before beginning the registration process. Reviewing and assembling the required information before beginning the registration process will alleviate last-minute searches for required information.

Organizations must have a Unique Entity Identifier (UEI) number, active System for Award Management (SAM) registration, and Grants.gov account to apply for grants. If individual applicants are eligible to apply for this funding opportunity, then you may begin with step 3, Create a Grants.gov Account, listed below.

Creating a Grants.gov account can be completed online in minutes, but UEI and SAM registrations may take several weeks. Therefore, an organization's registration should be done in sufficient time to ensure it does not impact the entity's ability to meet required application submission deadlines.  Organizations that are already registered will be assigned a UEI number automatically.

Complete organization instructions can be found on Grants.gov here: https://www.grants.gov/web/grants/applicants/organization-registration.html

Additional administrative requirements for DOE grants and cooperative agreements are contained in 2 CFR, Part 25 (See: http://www.eCFR.gov). Prime awardees must keep their data at the System for Award Management (SAM) current at http://www.sam.gov current SAM is the government-wide system that replaced the CCR. If you had an active registration in the CCR, you have an active registration in SAM.  Subawardees at all tiers must obtain UEI (Unique Entity Identifier) numbers and provide the UEI to the prime awardee before the subaward can be issued.

  - Register with SAM: All organizations applying online through Grants.gov must register with the System for Award Management (SAM). Failure to register with SAM will prevent your organization from applying through Grants.gov. SAM registration must be renewed annually. For more detailed instructions for registering with SAM, refer to:
https://www.grants.gov/web/grants/applicants/organization-registration/step-2-register-with-sam.html

  - Create a Grants.gov Account: The next step is to register an account with Grants.gov. Follow the on-screen instructions or refer to the detailed instructions here: https://www.grants.gov/web/grants/applicants/registration.html

  - Add a Profile to a Grants.gov Account: A profile in Grants.gov corresponds to a single applicant organization the user represents (i.e., an applicant) or an individual applicant. If you work for or consult with multiple organizations and have a profile for each, you may log in to one Grants.gov account to access all of your grant applications. To add an organizational profile to your Grants.gov account, enter the UEI Number for the organization in the UEI field while adding a profile. For more detailed instructions about creating a profile on Grants.gov, refer to: https://www.grants.gov/web/grants/applicants/registration/add-profile.html

  - EBiz POC Authorized Profile Roles: After you register with Grants.gov and create an Organization Applicant Profile, the organization applicant's request for Grants.gov roles and access is sent to the EBiz POC. The EBiz POC will then log in to Grants.gov and authorize the appropriate roles, which may include the Authorized Organization Representative (AOR) role, thereby giving you permission to complete and submit applications on behalf of the organization. You will be able to submit your application online any time after you have been assigned the AOR role. For more detailed instructions about creating a profile on Grants.gov, refer to:
https://www.grants.gov/web/grants/applicants/registration/authorize-roles.html

  - Track Role Status: To track your role request, refer to:
https://www.grants.gov/web/grants/applicants/registration/track-role-status.html

  - Electronic Signature: When applications are submitted through Grants.gov, the name of the organization applicant with the AOR role that submitted the application is inserted into the signature line of the application, serving as the electronic signature. The EBiz POC must authorize people who are able to make legally binding commitments on behalf of the organization as a user with the AOR role; this step is often missed and it is crucial for valid and timely submissions.

- How to Submit an Application to DOE/NNSA via Grants.gov

Grants.gov applicants can apply online using Workspace. Workspace is a shared, online environment where members of a grant team may simultaneously access and edit different webforms within an application. For each funding opportunity announcement (FOA), you can create individual instances of a workspace.

Below is an overview of applying on Grants.gov. For access to complete instructions on how to apply for opportunities, refer to:
https://www.grants.gov/web/grants/applicants/workspace-overview.html

- Create a Workspace: Creating a workspace allows you to complete it online and route it through your organization for review before submitting.

- Complete a Workspace: Add participants to the workspace to work on the application together, complete all the required forms online or by downloading PDF versions, and check for errors before submission. The Workspace progress bar will display the state of your application process as you apply. As you apply using Workspace, you may click the blue question mark icon near the upper-right corner of each page to access context-sensitive help.

- Adobe Reader: If you decide not to apply by filling out webforms you can download individual PDF forms in Workspace. The individual PDF forms can be downloaded and saved to your local device storage, network drive(s), or external drives, then accessed through Adobe Reader.

NOTE: Visit the Adobe Software Compatibility page on Grants.gov to download the appropriate version of the software at: https://www.grants.gov/web/grants/applicants/adobe-software-compatibility.html

- Mandatory Fields in Forms: In the forms, you will note fields marked with an asterisk and a different background color. These fields are mandatory fields that must be completed to successfully submit your application.

- Complete SF-424 Fields First: The forms are designed to fill in common required fields across other forms, such as the applicant name, address, and DUNS Number. Once it is completed, the information will transfer to the other forms.

- Submit a Workspace: An application may be submitted through workspace by clicking the Sign and Submit button on the Manage Workspace page, under the Forms tab. Grants.gov recommends submitting your application package at least 24-48 hours prior to the close date to provide you with time to correct any potential technical issues that may disrupt the application submission.

- Track a Workspace Submission: After successfully submitting a workspace application, a Grants.gov Tracking Number (GRANTXXXXXXXX) is automatically assigned to the application. The number will be listed on the Confirmation page that is generated after submission. Using the tracking number, access the Track My Application page under the Applicants tab or the Details tab in the submitted workspace.

For additional training resources, including video tutorials, refer to: https://www.grants.gov/web/grants/applicants/applicant-training.html

Applicant Support: Grants.gov provides applicants 24/7 support via the toll-free number 1-800-518-4726 and email at support@grants.gov. For questions related to the specific grant opportunity, contact the number listed in the application package of the grant you are applying for.

If you are experiencing difficulties with your submission, it is best to call the Grants.gov Support Center and get a ticket number. The Support Center ticket number will assist the DOE/NNSA with tracking your issue and understanding background information on the issue.

- Timely Receipt Requirements and Proof of Timely Submission

Online Submission. All applications must be received by September 20, 2022, Not Later Than 23:59:59 PM Eastern Time on the due date established for each program. Proof of timely submission is automatically recorded by Grants.gov. An electronic date/time stamp is generated within the system when the application is successfully received by Grants.gov.

- The Applicant with the Authorized Organization Representative (AOR).

- AOR role who submitted the application will receive an acknowledgement of receipt and a tracking number (GRANTXXXXXXXX) from Grants.gov with the successful transmission of their application. This applicant with the AOR role will also receive the official date/time stamp and Grants.gov Tracking number in an email serving as proof of their timely submission.

When DOE/NNSA successfully retrieves the application from Grants.gov, and acknowledges the download of submissions, Grants.gov will provide an electronic acknowledgment of receipt of the application to the email address of the applicant with the AOR role who submitted the application. Again, proof of timely submission shall be the official date and time that Grants.gov receives your application. Applications received by Grants.gov after the established due date for the program will be considered late and will not be considered for funding by DOE/NNSA.

Applicants using slow internet, such as dial-up connections, should be aware that transmission can take some time before Grants.gov receives your application. Again, Grants.gov will provide either an error or a successfully received transmission in the form of an email sent to the applicant with the AOR role attempting to submit the application. The Grants.gov Support Center reports that some applicants end the transmission because they think that nothing is occurring during the transmission process. Please be patient and give the system time to process the application.

APPLICATIONS RECEIVED AFTER THE DEADLINE WILL NOT BE REVIEWED OR CONSIDERED FOR AWARD.

# Section I - FUNDING OPPORTUNITY DESCRIPTION

- SUMMARY

The mission  of the U.S. Department of Energy (DOE), National Nuclear Security Administration (NNSA), Office of Defense Nuclear Nonproliferation Research and Development (DNN R&D) is to drive innovative research that develops technologies and expertise to detect foreign nuclear proliferation activities and produces technologies for integration into operational systems by leveraging capabilities at the national laboratories, plants, and sites, as well as at universities and within private industry.  DNN R&D supports U.S. national and nuclear security objectives in reducing global nuclear security threats through the innovation of unilateral and multi-lateral technical capabilities to detect, identify, and characterize: 1) foreign nuclear weapons development activities; 2) illicit diversion of special nuclear materials; 3) nuclear explosions globally; and 4) stewarding U.S. technical capabilities in nuclear nonproliferation.

Throughout this document the term, DOE National Laboratories, is used to collectively refer to DOE and NNSA National Laboratories, Plants, Sites, and Complexes. For DNN R&D, the role of Institutions of Higher Education (IHE; as defined in Section III.A. below) is to innovate, develop, and prove some of the most challenging basic aspects of new technology and methods in coordination with the DOE National Laboratories which can in turn fulfill their unique role to perform mission-specific research and development that improves on capabilities until they are either adopted by operational enterprises or transitioned into private industry for commercialization.  Transparently and effectively linking the roles of these IHE and DOE National Laboratory represents the core of how DNN R&D proposes to meet its objectives.

The intent of this Funding Opportunity Announcement (FOA) is to award ONE five-year cooperative agreement(s) to a consortium consisting of accredited IHE’s to allow them to receive and administer funds for student and faculty research, fellowships, and scholarship funding awarded by DOE/NNSA, DNN R&D.

The cooperative agreement will be awarded to a consortium of IHEs that include the participation of DOE National Laboratories as consortium-members.  Individual consortium-member IHEs shall make specific contributions and shall receive specified portions of the funding.

The consortium may include student and research fellows and must have a long-term objective of building expertise in scientific disciplines directly relevant to nuclear forensics.  Research results should be incorporated readily into IHE curricula.  Students, faculty, and researchers must be able to work unencumbered while moving across organizational and bureaucratic boundaries of the academic and governmental facilities engaged in the consortium, while properly protecting critical information and materials.  The consortium should establish reciprocal arrangements between the lead IHE and other IHEs as well as relationships with appropriate DOE National Laboratories.

- BACKGROUND

The direct outcome of this program is the development of a diverse and highly-talented cadre of nuclear forensics professionals with skill-sets grounded in foundational disciplines including but not limited to radiochemistry, geochemistry, nuclear physics, nuclear engineering, materials science, and analytical chemistry. These professionals will have careers as scientists, engineers, technicians, operational personnel, and intelligence professionals, among others, and will be leaders in active in nuclear forensics, nuclear nonproliferation, nuclear arms control, nuclear incident response, nuclear intelligence activities, nuclear energy, and other nuclear-related fields.  These professionals are expected to benefit academia, private industry, and several US government agencies, including Energy, Homeland Security, Defense, State, Justice, and the Intelligence Community.

- INTEGRATION WITH DEFENSE NUCLEAR NONPROLIFERATION R&D NEEDS

The management plan and structure for the proposed consortium should include mechanisms that support responsiveness to emerging research direction and needs.  New research results and challenges continually emerge from DNN R&D-sponsored research at the DOE National Laboratories, and with small business, and the academic community can and should leveraged these advances.  The management plan should detail novel ideas or formal mechanisms for leveraging these capabilities.  Where topically appropriate, DNN R&D encourages collaboration and innovative thinking across disciplines to develop technologies and approaches that will advance our mission.

Awardees and subawardees should expect that DNN R&D management will be an active partner in the award and that they should participate in DNN R&D’s annual University Program Review (UPR).  Additionally, awardees should expect that DNN R&D will conduct other assessments to verify awardees' progress towards proposed topical/focus areas and their milestones.  These assessments will focus on, but may not be limited to, the IHE's effective and efficient use of provided resources; maintaining disciplines in nuclear forensics through research and development; and, conducting work pertinent to nuclear nonproliferation activities.

The envisioned cooperative agreement will be awarded to a consortium made up of universities with the participation of at least one DOE National Laboratory as a consortium partner.  Individual consortium-member universities will make specified contributions and will receive specified portions of the funding.  The consortium should include student and early career research fellowships and have a long-term vision to build expertise in nuclear forensics and nonproliferation.  Students, faculty, and researchers must be able to work unencumbered across organizational and bureaucratic boundaries of the academic and governmental facilities engaged in the consortium, while properly protecting critical information and materials.  Thus, the consortium should establish reciprocal arrangements between the home academic institution and other degree-granting institutions as well as relationships with appropriate DOE National Laboratories.

- TECHNICAL SCOPE

DNN R&D is looking to establish a university consortium to support topical areas in nuclear forensics.

DNN R&D sponsors research and development across all disciplines of nuclear science and security in support of the Nation’s nuclear security and nonproliferation goals.  The role of universities for nuclear forensics research and development is to innovate and develop some of the most challenging basic aspects of new technology and methods.  Once these basic aspects have been proven at the university level, the DOE National Laboratories can fulfill their unique role to perform mission-specific research and development that improves on capabilities until they are either adopted by operational enterprises or transitioned into private industry for commercialization.  Transparently and effectively linking the roles of these Universities and DOE National Laboratories represents the core of how DNN R&D proposes to meet its objectives.

A successful consortium is a rich collaborative environment between the university members, their student and faculty researchers, and the DOE National Laboratory scientists and staff.  This environment should have a priority on building skill sets in critical disciplines such as, but not limited to:

- radiochemistry;

- geochemistry;

- nuclear physics, science and engineering;

- nuclear material science;

- shock physics;

- quantum-enabled sensing;

- analytical chemistry.

Thus, the proposed consortium should address:

- Producing research results in nuclear forensics science of a basic or fundamental nature;

- Enabling collaborative research relationships between universities, the DOE National Laboratories, and other government agencies;

- Transitioning basic science and technology from universities to U.S. government applications;

- Motivating talented researchers toward careers in universities, the DOE National Laboratories, and government agencies with nuclear missions.

The consortium may support (other concepts are also encouraged):

- Creation of early-career professorial fellowships relating to nuclear forensics to include research support funds;

- Post-doctoral research fellowships relating to nuclear forensics or nonproliferation research at DOE National Laboratories;

- Undergraduate basic research internships and graduate research fellowships relating to nuclear forensics;

- Consortium undergraduate and graduate internships at team member DOE National Laboratory performing nuclear forensics or nonproliferation basic research and development.  This can be in a collaborative environment with or using DOE Laboratory contractor personnel in an adjunct faculty role;

- Improvements to university and college infrastructures for conducting basic research and development relating to nuclear forensics;

- Incorporation of outcomes of sponsored research into continuous nuclear forensics expertise development improvement (e.g., curriculum improvements).

Research is sought in multi-disciplinary pursuits designed to advance the science of nuclear forensics (for an overview, see the referenced National Academies report (2021)). This includes ways to identify diagnostic technical information that resides within material samples and how quickly and accurately that information can be obtained.  Research will improve the accuracy, precision, timeliness, discriminating power, and/or robustness of nuclear forensics methods and will improve scientific understanding of underlying phenomena (e.g., surface interactions of alteration phases of uranium oxides or fallout debris formation in the nuclear fireball), as follows:

- Improve techniques to analyze and evaluate interdicted materials (e.g., samples of uranium or plutonium metals and oxides) found outside of institutional control to identify characteristics that help age-dating and provenance determinations (e.g., time-history of material processing steps or exposures to various environmental conditions).

- Advance current methods (for recent summaries, see Moody et al. (2015), Keegan et al. (2016), and Kristo (2020)) to discover diagnostic features at various length scales (e.g., based on material, physical, chemical, isotopic, and/or other characteristics) probed by modern scientific methods of material analysis (e.g., various microscopies, spectroscopies, and spectrometries, to include quantum-enabled techniques and machine-learning algorithms (see for example Burr et al. (2021)).  This includes improving nuclear fuel-cycle modeling of major, minor, and trace isotopes in various processing steps to interpret measurements of observable effects that persist within a material sample.

- Improve techniques in the nation’s preparedness to analyze and evaluate post-detonation signals and fallout debris samples for technical evidence that identifies and distinguishes device characteristics for answering nuclear forensics questions, such as determining its origin.

- Discover diagnostic information (e.g., in the composition of fallout debris such as Trinitite samples) probed by modern scientific methods of analysis.  This includes improving radiochemistry separations (see for example Straub et al. (2020)) and precision experimental measurements of several nuclear cross sections that are nuclear data parameters used in calculations (e.g., see https://nucleardata.berkeley.edu/wanda and Rundberg (2013)).

The university selected for award will be the lead organization and the prime award recipient and will be held responsible for managing the entire scope, schedule and cost of the project, to include all reporting.

At a minimum:

- the lead university must propose at least three other university partners that meet the above-definition of “university” as consortium member. An integrated approach to the work will be essential in tackling the proposed tasks under the consortium.  The lead university is discouraged from including an overly large number of loosely connected university partners;

- the lead university must also propose one or more DOE National Laboratory as consortium members in accordance with the “Other Eligibility Requirements” under Section III below. It is essential that the IHEs engage DOE National Laboratory partners early in proposal development as to forge a connection in collaborating on future work and having unique and innovative approaches to accomplishing proposed tasks.

This cooperative agreement will provide funding ONLY to the university members of the consortium.  The DOE National Laboratory members will leverage existing DNN R&D funding to support involvement – including any mentoring – to the extent it delivers mutual benefit.  DNN R&D will provide management consortia support funds directly to DOE National Laboratory team members (as done for previous consortia awards) to assist in managing the Laboratory-University interactions.

- IHE Credit for Student: The lead IHE and consortium members should establish a program to acknowledge students who work at DOE National Laboratories with DOE National Laboratory mentors.  This can be done at the discretion of the IHE; for example, by providing a one-semester credit or internship for that student.

- Eligible Students for Direct Benefit: Students who are directly funded and/or provided benefit by assisting with research and associated projects should be undergraduates in at least junior year or graduate students who are pursuing degrees that relate to the topics of this FOA.  The program will periodically request corroborating eligibility data when assembling metrics and various internal reports.

- DOE National Laboratory Rotations: Postdocs (U.S. citizens and permanent residents) will be expected to conduct a lab/site/complex rotation with one of the partner DOE National Laboratories.  A reasonable number of professors should expect to participate via a short detail (4-8 weeks) at the lab with their student(s).  The intent is to motivate professor and student teams in forging new collaborative relationships with the DOE National Laboratories and provide access to varying degrees of professional knowledge, application and equipment. Universities should plan accordingly and budget to participate in these rotations.

# Universities will need to engage with DOE National Laboratories as early as possible in their application process.  Universities are encouraged to engage with a moderate number of well-considered DOE National Laboratory partners who’ve really thought through their participation rather than having labs issue generic partnership letters.

# Section II - AWARD INFORMATION

## A.	TYPE OF AWARD INSTRUMENT

DOE/NNSA anticipates awarding a cooperative agreement under this funding opportunity announcement.

## B.	ESTIMATED FUNDING

Approximately $5 million a year is expected to be available for an award under this announcement, contingent upon the availability of appropriated funds.

## C.	MAXIMUM AND MINIMUM AWARD SIZE

The ceiling amount of $25,000,000 is expected to be available contingent upon the availability of funds for all five years.

## D.	EXPECTED NUMBER OF AWARDS

DOE/NNSA anticipates making one award under this announcement but reserves the right to make more or less than one award.

## E.	ANTICIPATED AWARD SIZE

.

DOE/NNSA may fund $25 million under this FOA, contingent upon the availability of appropriate funds for all five years.

## F.	PERIOD OF PERFORMANCE

DOE/NNSA anticipates notifying the applicant selected for award by January 2023.  The award is expected to start on July 01, 2023, depending on availability of funds. DOE/NNSA anticipates making award(s) that will run no longer than 5 years.

## G.	TYPE OF APPLICATION

DOE/NNSA will only accept new applications under this announcement.

# Section III - ELIGIBILITY INFORMATION

## A.	GENERAL

To be considered for evaluation, an applicant‘s submission must meet the criteria set forth below. If the application does not meet these initial requirements, it will be considered non-responsive, removed from further evaluation, and ineligible for any award. Applicants should submit packages in advance of the deadline to ensure there is time to address and make corrections if needed. No exceptions will be made to the deadline.

## B.	ELIGIBLE APPLICANTS

Restricted Eligibility (DECEMBER 2014)

In accordance with 2 CFR 910.126(b), Competition, eligibility for award is restricted to domestic IHEs (as defined below) because the purpose of the DNN R&D University Program is to support university research and development.  IHEs provide a different, more fundamental, theoretical, innovative perspective on research and development than that provided by the laboratories or industry.  IHEs are also the best sources for innovative, long-term ideas because of their inherent close ties to new developments in the basic sciences, their ability to construct cross-disciplinary teams, and their ability to test new concepts and ideas with theoretical and experimental rigor.  Further, the support provided to IHEs will help foster a recruitment pipeline of future nuclear non-proliferation and other nuclear security professionals who will contribute significantly to the national security of the United States.

For the purpose of this announcement, an IHE is defined as:

(a) A public or private nonprofit educational institution that—

(1) Is in a State;

(2) Admits as regular students only persons who—

(i) Have a high school diploma;

(ii) Have the recognized equivalent of a high school diploma; or

(iii) Are beyond the age of compulsory school attendance in the State in which the institution is physically located;

(3) Is legally authorized to provide an educational program beyond secondary education in the State in which the institution is physically located;

(4)(i) Provides an educational program—

(A) For which it awards an associate, baccalaureate, graduate, or professional degree;

(B) That is at least a two-academic-year program acceptable for full credit toward a baccalaureate degree; or

(C) That is at least a one academic year training program that leads to a certificate, or other non-degree recognized credential, and prepares students for gainful employment in a recognized occupation; and

(ii) May provide a comprehensive transition and postsecondary program, as described in 34 CFR part 668, subpart O; and

(5) Is—

(i) Accredited or pre-accredited; or

(ii) Approved by a State agency listed in the Federal Register in accordance with 34 CFR part 603, if the institution is a public postsecondary vocational educational institution that seeks to participate only in Federal student assistance programs.

The program seeks the long-term development of expertise in the field of the nuclear forensics. One of DNN R&D’s goals within the university program is to support development for nuclear nonproliferation and arms control careers in the DOE National Laboratories and U.S. government. These careers require the ability to attain and maintain a national security clearance. As such, it is important to restrict the eligibility for Senior/Key Persons, such as Principal Investigators, to U.S. citizens or permanent residents.  Several of the DOE/NNSA goals are not achievable by foreign nationals.

In accordance with DOE O 142.3A Chg 1(MinChg) 1-18-2017, applicants selected for award are required to submit/complete a form prior to award that Principal Investigator and Co-Principal Investigator(s) are U.S. citizens or permanent residents (refer to “Research & Related Personal Data” form at https://www.grants.gov/web/grants/forms/r-r-family.html#sortby=1) and resubmit as needed (example: Replacement of a Principal Investigator or Co-Principal Investigator).  The FOA further restricts the eligibility of scholarships and fellowships (Post-doctoral Fellows, graduate students, and undergraduate students) to U.S. citizens or permanent residents. Non-U.S. citizens are not precluded from necessarily assisting with associated work under the selected consortia; however, they are precluded from receiving any type of associated Government funds under this agreement.

A DOE/NNSA Point of Contact (POC) List, as well as links to further information on lab/site/complex research specialties, are as listed:

The POC List identified below is not intended to be all inclusive of all available DOE/NNSA Federally Funded R&D Centers (FFRDC).  Applications collaborating with other DOE/NNSA FFRDCs (including sites/complexes) not listed in the table below will be accepted. Other collaborators may be found at: https://www.energy.gov/maps/department-energy-facilities and https://www.energy.gov/nnsa/locations.

|  | Laboratory and Site/Complex | POC | Email |
| --- | --- | --- | --- |
| 1. | ORNL – Oak Ridge National Laboratory | Jennifer Ladd-Lively | laddjl@ornl.gov |
| Website: https://www.ornl.gov https://www.ornl.gov/sponsored-research https://www.ornl.gov/partnerships |  |  |  |
| 2. | Y12 – Y12 National Security Complex | Martin Williamson, Technical POC, Matthew Smith, Business Partnership POC | martin.williamson@cns.doe.gov matthew.d.smith@cns.doe.gov |
| Website: https://www.y12.doe.gov/ https://www.y12.doe.gov/mission/technologies-and-research-capabilities https://www.y12.doe.gov/contact |  |  |  |
| 3. | SNL – Sandia National Laboratories | David W. Peters, Technical POC | dwpeter@sandia.gov |
| Website: https://www.sandia.gov https://www.sandia.gov/working_with_sandia/technology_partnerships/universities/index.html |  |  |  |
| 4. | INL – Idaho National Laboratory | David Chichester, Technical POC | david.chichester@inl.gov |
| Website: https://inl.gov/research-program/nuclear-nonproliferation/ https://inl.gov/inl-initiatives/education/ |  |  |  |
| 5. | LANL – Los Alamos National Laboratory | Bob Shirey, Technical POC Nina Rosenberg, Partnership POC | shirey@lanl.gov nina@lanl.gov |
| Website: https://www.lanl.gov/collaboration/index.php?source=globalheadernavhttps://www.lanl.gov/collaboration/index.php?source=globalheadernav https://www.lanl.gov/collaboration/research-opportunities/energy-security.php |  |  |  |
| 6. | LLNL – Lawrence Livermore National Laboratory | Scot S. Olivier, Technical POC Christine Zachow, University Relations POC | olivier1@llnl.gov zachow2@llnl.gov |
| Website: https://www.llnl.gov/ https://st.llnl.gov/about-us/university-relations and https://st.llnl.gov/about-us/contact-us |  |  |  |
| 7. | LBNL – Lawrence Berkeley National Laboratory | John Valentine, Technical POC | jdvalentine@lbl.gov |
| Website: https://www.lbl.gov/ |  |  |  |
| 8. | PNNL – Pacific Northwest National Laboratory | Robert Brigantic, Technical POC, Suresh Baskaran, University Partnership POC | robert.brigantic@pnnl.gov suresh.baskaran@pnnl.gov |
| Website: https://www.pnnl.gov/academia ; https://www.pnnl.gov/connect-us |  |  |  |
| 9. | ANL – Argonne National Laboratory | Candido Pereira, Technical POC, Alex Heifetz, University Partnership POC | pereira@anl.gov aheifetz@anl.gov |
| Website: https://www.anl.gov/nse https://www.anl.gov/tcp/collaborative-partnerships and https://www.anl.gov/tcp/meet-our-team |  |  |  |
| 10 | SRNL – Savannah River National Laboratory | James S. Bollinger, Technical POC Martine Duff, University Partnership POC | james02.bollinger@srnl.doe.gov martine.duff@srnl.doe.gov |
| Website: https://srnl.doe.gov/university_programs/index.htm |  |  |  |
| 11 | BNL – Brookhaven National Laboratory | Susan Pepper, University POC | pepper@bnl.gov |
| Website: https://www.bnl.gov/world/ https://www.bnl.gov/partner/ |  |  |  |

## C.	COST SHARING

Cost sharing is not required but may be offered. This will not bolster chances of selection since this will not be a consideration under the merit review criteria.

Voluntary Cost Sharing: Cost share is considered “voluntary” when the applicant describes a quantifiable amount of resources it will contribute to the project.

Voluntary Committed Cost Sharing: DOE/NNSA will consider any voluntary cost sharing offered at the application stage as “committed” cost sharing at the award stage. So any quantified cost sharing offered in any submitted applications become fiscally and/or programmatically auditable and must be documented and reported to DOE/NNSA if the application is funded.  Any IHE who provides voluntary committed cost sharing will be required to provide a revised R&R Fed/NonFed Budget Form. In addition, some universities at their discretion may require sub-awards to cost share.

## D.	OTHER ELIGIBILITY REQUIREMENTS

DOE National Laboratories are not eligible to compete as the prime recipient under this FOA; however, each lead IHE application must propose one or more DOE National Laboratories as collaborators subject to the following guidelines:

- Authorization for DOE National Laboratory Participation: The cognizant Contracting Officer for the DOE National Laboratory must authorize in writing the participation of the DOE National Laboratory on the proposed project and this authorization must be submitted upon selection.  However, collaboration letters (to include a statement that no grant funds will be provided to the lab and/or site/complex from the awarded cooperative agreement) from the collaborating employee must be submitted with the application.

The following wording is acceptable for the aforementioned Contracting Officer authorization to be submitted upon selection.

"Authorization is granted for the [Name] Laboratory and/or Site/Complex to participate in the proposed project.  The work proposed for the laboratory and/or Site/Complex is consistent with or complimentary to the missions of the laboratory and/or site/complex, will not adversely impact execution of the DOE/NNSA assigned programs at the laboratory and/or site/complex, and will not place the laboratory and/or site/complex in direct competition with the domestic private sector."

- Value/Funding: The value of, and funding for, the DOE National Laboratory’s portion of the work should not be included in the prime IHEs proposed budget.

- DOE National Laboratory: The portion of the effort to be performed by all DOE National Laboratory collaborators in aggregate shall not approach or exceed 50% of the total effort.  In addition, the DOE National Laboratory effort should be well thought out rather than having all labs and/or site/complexes issue generic partnership letters to all university applicants. The intent is that the DOE National Laboratory(s) may not play a role comprising the majority of the teaming arrangement and work effort.

A DOE National Laboratory is to provide a Draft of the aforementioned Authorization and Field Work Proposal in accordance with DOE O 412.1A or NNSA SD 412.1 as applicable, Work Authorization System with the lead university consortium application, and a Final to be submitted 30-45 days from notice of selection.

Funding for any work being done by a DOE Laboratory, will be funded directly by the program office.  This funding will be transmitted to the lab via an internal Work Authorization (WA)/Implementation Plan (IP) process.  The amount of funds that a laboratory uses in teaming with the IHE will not be factored into the IHE’s total award amount.

F.	ROLES AND RESPONSIBILITIES

The following roles and responsibilities are not all-inclusive but are being highlighted to better define the expectations of participant organizations.  Upon selection, the following will be added to the consortium’s award:

DOE/NNSA:

- DOE/NNSA will participate in overall program management of the Consortium, and is primarily represented by the DOE/NNSA Program Manager.  The Program Manager coordinates the activities of IHE with Headquarters, the Contracting Officer, and the Grant Specialist.

- The Program Manager reviews all deliverables and reviews/recommends approval of any other changes on the Cooperative Agreement to the Contracting Officer.  The Program Manager also reviews, recommends, and submits a Purchase Requisition (PR) to the Contracting Officer for annual incremental funding on the Cooperative Agreement and assures orderly progression of work from year-to-year.

- DOE/NNSA will examine the continuity and consistency of program objectives, and also assure that the objectives are responsive to the needs of DOE/NNSA and the nation.  DOE/NNSA members will include the Program Manager and other senior DOE/NNSA officials as required.

Consortia:

- As consortia professor/student teams may detail to a laboratory and/or site/complex collaborator for forging new relationships and conducting research, the IHE will cover their own associated fee that may include: stipends, tuition, per diem, lodging and travel expenses.

- Access to the IHE equipment, colleagues and students, and facilities will be coordinated by the IHE and a listed point of contact and/or Principal Investigator at that site.

- Responsibility of Successful Applicant (Lead IHE): The applicant will be the responsible authority regarding the settlement and satisfaction of all contractual and administrative issues, including but not limited to, disputes and claims arising out of any agreement between the applicant and the DOE National Laboratories and other consortium members.

DOE National Laboratories:

- The DOE National Laboratories, participating as a collaborator, will be represented and their participation facilitates coordination of research being conducted by the Laboratories with that of the consortium.

- As laboratory employees may rotate through the IHE to aid in research and assist postdocs, the laboratory will cover their own associated fees that may include: per diem, lodging, and travel expenses.

- Access to lab equipment, mentors, and facilities will be coordinated by the laboratory and a listed point of contact and/or project coordinator at that site.

- The DOE Laboratories are responsible for the cost of equipment or facility usage incurred by Consortia’s Postdocs, Graduate Fellows or Interns, except for reimbursement for use of facilities that require “user fees” in accordance with the labs policies and procedures.

# Section IV - APPLICATION AND SUBMISSION INFORMATION

Application and Submission Definitions

# Pre-award terminology

# Applicant (Prime) – An organization submitting an application to DOE/NNSA for assistance under this Funding Opportunity Announcement.

# Sub-applicant - An organization submitting a sub-application as part of a larger application package to an Applicant for assistance.

# Post-award terminology

# Recipient - An Applicant whose application has been approved and federal award obligated.

Subrecipient - A Sub-applicant whose sub-application has been approved and sub-award obligated.

## Application Process

DOE/NNSA performs an initial eligibility review of applicant submissions to determine whether they meet the eligibility requirements of Section III of the FOA. DOE/NNSA will not review or consider submissions that do not meet the eligibility requirements of Section III.

All submissions must conform to the following form and content requirements, including maximum page lengths (described below) and must be submitted as specifically stated. DOE/NNSA will not review or consider submissions submitted through means other than specifically stated in the FOA, submissions submitted after the applicable deadline, and incomplete submissions. DOE will not extend deadlines for applicants who fail to submit required information and documents due to server/connection congestion.

Problems with computer systems at the applicant organization, Adobe compatibility settings issues, failure to follow instructions in the Request for Applications (RFA), or failure to attach documents to the application package correctly are not considered system issues.

NOTE:  All Applicant and Sub-Applicant application requirements, regardless if the applicant or sub-applicant is listed as, or a part of a University System, or integrated by, or under a university organization or listed as a member university under a Board of Regents, or considered inclusive to a university system, must provide all mandatory application documents as outlined in the FOA.  Under no circumstances will deviations or exceptions from FOA requirements be allowed. Failure to provide the required application documents per the FOA requirements, will deem your application to be non-responsive and dropped from further consideration or review.

## Address to Request Application Package

Application forms and instructions are available at Grants.gov.  To access these materials, go to http://www.grants.gov, select "APPLICANTS”, then select “Apply for Grants," and then select "Get Application Package” button. Enter the funding opportunity number (DE-FOA-000XXXX). Under the PACKAGE tab, select “Apply” under the Actions column, and under Option: 1 Apply Now Using Workspace, select the Login to Apply Now button. Follow the prompts in Workspace to complete the application package. You are encouraged to review the Applicant FAQs in Grants.gov as you prepare and submit your application.

## Letter of Intent and Pre-Application

### Letter of Intent

Letter of Intent not required.

### Pre-application

Pre-applications are not required.

## Content and Application Forms

All applicants including sub-applicants must complete the mandatory forms and any applicable optional forms in accordance with the instructions on the forms and the additional instructions below. Files that are attached to the forms must be in Adobe Portable Document Format (PDF) unless otherwise specified in this announcement. Attached PDF files must be plain files consisting of text, numbers, and images without editable fields, signatures, passwords, redactions, or other advanced features available in some PDF-compatible software. Do not use PDF portfolios or binders.

Please note: you may only use the following UTF-8 characters when naming your application attachments: A-Z, a-z, 0-9, underscore (_), hyphen (-), space, period. You must limit the file name to 50 or fewer characters. Attachments that do not follow this rule may cause the entire application to be rejected or cause issues during processing.

To avoid interfering with the selection of peer reviewers, please do NOT include general letters of support for the proposal or list collaborators that do not have an active part in the project. General letters of support will not be used in making funding decisions.

Optional letters of collaboration for unfunded or funded collaborations may be placed in

Appendix 6 (Other Attachments). Letters of collaboration should state the intention to participate, but they should not be written as recommendation or endorsement letters, which are not allowed.

### Application for Federal Assistance SF-424 (R&R) [MANDATORY for Prime Applicant and Sub-Applicants]

For the Prime applicant, in Grants.gov Workspace, Complete SF-424 Fields First: The forms are designed to fill in common required fields across other forms, such as the applicant name, address, and DUNS number. To trigger this feature, an applicant must complete the SF-424 information first. Once it is completed, the information will transfer to the other forms.

NOTE: If sub-applicants will participate in this award, this form is mandatory and must be submitted for all sub-applicants. See Section IV – Application and Submission Information, sub-section D. 7. Sub-Applicant Submittal Instructions below for instructions. Also, see Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

IMPORTANT UPDATE FOR PRIME AND SUB-APPLICANTS The certifications and assurances referenced in Field 17 of the Application for Federal Assistance are now contained in the System for Award Management (SAM) as Financial Assistance General Certifications and Representations.

### Research and Related Other Project Information [MANDATORY for Prime Applicant]

For the Prime applicant, the Research and Related (R&R) Other Project Information form is part of the Application Package that must be completed in Grants.gov Workspace. The special instructions for completing this form follow:

- Fields 1 to 6.b: Applicant must complete the entries to these fields.

- Field 7: Applicant must attach completed file for Project Summary/Abstract.

- Field 8: Applicant must attach completed file for Project Narrative plus required appendices.

- Field 12: Applicant must attach completed file for Project Management Plan.

- Field 12: Applicant must attach completed National Environmental Policy Act (NEPA) compliance form in addition to the other forms as referenced below.

### Project Summary/Abstract (Field 7 of the R&R Other Project Information form) [MANDATORY for Prime Applicant]

For the Prime applicant, the project summary/abstract must be submitted and must contain a summary of the proposed activity suitable for dissemination to the public.  It must be a self-contained document that identifies:

- the name of the applicant,

- the project director/principal investigator(s),

- the project title,

- the objectives of the project,

- the milestones of the project listed by year, and

- a description of the project, including methods to be employed, the potential impact of the project (i.e., benefits, outcomes), and major participants (for collaborative projects).

This document must not include any proprietary or sensitive business information as the DOE/NNSA may make it available to the public after awards are made. The project summary must not exceed 2 pages when printed using standard 8.5" by 11" paper with 1" margins (top, bottom, left and right) {single spaced} with font not smaller than 11 point.

The Project Summary/Abstract file must be saved in PDF format and uploaded to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the completed Project Summary/Abstract in PDF format, click the "Add Attachment" button next to Field 7 of the R&R Other Project Information form in Grants.gov Workspace.

### Project Narrative and Appendices (Field 8 of the R&R Other Project Information form) [MANDATORY for Prime Applicant]

Project Narrative

The project narrative must not exceed 30 pages, including cover page, table of contents, charts, graphs, maps, photographs, tables, and other pictorial presentations, when printed using standard 8.5" by 11" paper with 1 inch margins (top, bottom, left, and right) {single spaced} with font not smaller than 11 point.

EVALUATORS WILL ONLY REVIEW THE NUMBER OF PAGES SPECIFIED IN THE PRECEDING SENTENCE. Do not include any Internet addresses (URLs) that provide information necessary to review the application, because the information contained in these sites will not be reviewed. See Section VIII – Other Information – Part D for instructions on how to mark proprietary application information.

Instructions: The Project Narrative Cover Page, Project Narrative, and Appendices must be saved as one single document in PDF format and uploaded to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the completed Project Narrative in PDF format, click "Add Attachment" button next to field 8 of the R&R Other Project Information form in Grants.gov Workspace.

- The Project Narrative Cover Page (NTE 1-page)

Comprised of the following required components:

- FOA Number;

- Topic Area;

- Application Title;

- Type of organization (i.e. U.S. university/academic institution of higher learning or not-for-profit, non-degree-granting domestic U.S. organization;

- Type of proposed award: New Award or Renewal of Existing Award (specify award number for existing award);

- Name of Lead Institution;

- Name, email address, and telephone number of organization’s business point of contact or Grants office point of contact.

- Name, mailing address, telephone number, fax number, and electronic mail address of Lead Project Director;

- Name(s), mailing addresses, telephone numbers, fax numbers, and electronic mail addresses of Team Members (institutional collaborators);

- Previous DOE/NNSA Grant numbers. If applicable, provide DOE grant number for projects currently funded under the DNN R&D University Program.

- Listing of any DOE National Laboratory personnel collaborating on the project.

- Projective Narrative - (NTE 29 total pages)

The Project Narrative portion is to provide a detailed description of the following:

- Project Objectives: This section should provide a clear, concise statement of the specific objectives/aims of the proposed project.

- Merit Review Criterion Discussion: The section should be formatted to address each of the merit review criterion and sub-criterion listed in Part V.A. Provide sufficient information so that reviewers will be able to evaluate the application in accordance with these merit review criteria. NNSA WILL EVALUATE AND CONSIDER ONLY THOSE APPLICATIONS THAT ADDRESS SEPARATELY EACH OF THE MERIT REVIEW CRITERION AND SUB-CRITERION.

- Relevance and Outcomes/Impacts: This section should explain the relevance of the effort to the DNN R&D Program Objectives in the program announcement and the expected outcomes and/or impacts.

- Roles of Participants: For multi-organizational or multi-investigator projects, describe the roles and the work to be performed by each participant/investigator, business agreements between the applicant and participants, and how the various efforts will be integrated and managed.

- Integration with DOE National Laboratories: Describe management and coordination mechanisms and how the work of the consortia shall be coordinated and integrated with the partner DOE National Laboratories.

- Facilities And Other Resources: Identify the facilities (e.g., office, laboratory, computer, etc.) to be used at each performance site listed and, if appropriate, indicate their capacities, pertinent capabilities, relative proximity, and extent of availability to the project. Describe only those resources that are directly applicable to the proposed work. Provide any information describing the other resources available to the project such as machine and electronics shops.

- Equipment: List important items of equipment already available for this project and, if appropriate, note the location and pertinent capabilities of each.  If you are proposing to acquire equipment, describe comparable equipment, if any, already at your organization and explain why it cannot be used.

- Statement of Project Objectives (SOPO): The project narrative must contain a single, detailed Statement of Project Objectives that addresses how the project objectives will be met. The Statement of Project Objectives must contain a clear, concise description of all activities to be completed during project performance and follow the structure discussed below. The Statement of Project Objectives may be released to the public by DOE in whole or in part after award. It is therefore required that it shall not contain proprietary or confidential business information.

The Statement of Project Objectives is generally less than 4 pages in total for the proposed work. Applicants shall prepare the Statement of Project Objectives in the following format:

TITLE OF WORK TO BE PERFORMED (Insert the title of work to be performed.  Be concise and descriptive.)

A.  OBJECTIVES

Include one paragraph on the overall objective(s) of the work. Also, include objective(s) for each phase of the work.

B.  SCOPE OF WORK

This section should not exceed one-half page and should summarize the effort and approach to achieve the objective(s) of the work for each Phase.

C.  TASKS TO BE PERFORMED

Tasks, concisely written, should be provided in a logical sequence and should be divided into the phases of the project, as appropriate. This section provides a brief summary of the planned approach to this project. An outline of the Project Management Plan (referenced in Task 1.0 below and required to be submitted with your application) is provided later in this Section.

PHASE I

Task 1.0 - Project Management and Planning

(Description includes work elements required to revise and maintain the Project Management Plan and to manage and report on activities in accordance with the plan)

Subtask 1.1

(Description)

Task 2.0 - (Title)

PHASE II (Optional)

Task 3.0 - (Title)

D.   DELIVERABLES

The periodic, topical, and final reports shall be submitted in accordance with the attached "Federal Assistance Reporting Checklist" and the instructions accompanying the checklist.

[Note: The Recipient shall provide a list of deliverables other than those identified on the "Federal Assistance Reporting Checklist" that will be delivered. These reports shall also be identified within the text of the Statement of Project Objectives. See the following examples:

1.   Task 1.1 - (Report Description)

2.   Task 2.2 - (Report Description)

- Appendices to Project Narrative Information [MANDATORY]

All applicants [lead university (prime applicant) and university partners (subawardees)] must complete the following appendices and attach them to the final Project Narrative document. Do not attach any of the requested appendices described below as files for fields 9, 10, 11, and 12 in Grants.gov workspace. Follow the below instructions to include the information as appendices in the single, bundled project narrative file. This attachment process should be completed prior to appending the Project Narrative document to Field 8 in the R&R Other Project Information form. All of the requested information for the following appendices will not count in the Project Narrative page limitation.

Appendix 1 - Biographical Sketch: (Not part of the 30 page limit)

Provide a biographical sketch for the project director/principal investigator (PD/PI) and each senior/key person listed in Section A on the R&R Budget form, including the sub-applicant senior/key persons. Provide the biographical sketch information as an appendix to your project narrative. Do not attach a separate file. The biographical information for each person must not exceed 2 pages when printed on 8.5" by 11"paper with 1 inch margins (top, bottom, left, and right) {single spaced} with font not smaller than 11 point and must include:

Education and Training: Undergraduate, graduate and postdoctoral training, provide institution, major/area, degree, and year.

Research and Professional Experience: Beginning with the current position list, in chronological order, professional/academic positions with a brief description.

Publications: Provide a list of up to 10 publications most closely related to the proposed project. For each publication, identify the names of all authors (in the same sequence in which they appear in the publication), the article title, book or journal title, volume number, page numbers, year of publication, and website address if available electronically.

Patents, copyrights, and software systems developed may be provided in addition to or substituted for publications.

Synergistic Activities: List no more than 5 professional and scholarly activities related to the effort proposed.

Appendix 2 - Current and Pending Support:  (Not part of the 30 page limit)

Provide a list of all current and pending support (both Federal and non-Federal) for the Project Director/Principal Investigator(s) (PD/PI) and senior/key persons, including subrecipients, for ongoing projects and pending applications.  For each organization providing support, show the total award amount for the entire award period (including indirect costs) and the number of person-months per year to be devoted to the project by the senior/key person.  Concurrent submission of an application to other organizations for simultaneous consideration will not prejudice its review.

Appendix 3 - Identification of Potential Conflicts of Interest or Bias in Selection of Reviewers:  (Not part of the 30 page limit)

Provide the following information in this section:

- Collaborators and Co-editors: List in alphabetical order all persons, including their current organizational affiliation, who are, or who have been, collaborators or co-authors with you on a research project, book or book article, report, abstract, or paper during the 48 months preceding the submission of this application. Also, list any individuals who are currently, or have been, co-editors with you on a special issue of a journal, compendium, or conference proceedings during the 24 months preceding the submission of this application. If there are no collaborators or co-editors to report, state "None."

- Graduate and Postdoctoral Advisors and Advisees: List the names and current organizational affiliations of your graduate advisor(s) and principal postdoctoral sponsor(s) during the last 5 years. Also, list the names and current organizational affiliations of your graduate students and postdoctoral associates

Appendix 4 - Bibliography & References Cited:  (Not part of the 30 page limit)

Provide a bibliography of any references cited in the Project Narrative. Each reference must include the names of all authors (in the same sequence in which they appear in the publication), the article and journal title, book title, volume number, page numbers, and year of publication. Include only bibliographic citations. Applicants should be especially careful to follow scholarly practices in providing citations for source materials relied upon when preparing any section of the application. In order to reduce the number of files attached to your application, please provide the Bibliography and References Cited information as an appendix to your project narrative. Do not attach file to Field 9 of the R&R Other Project Information.

Appendix 5 - Facilities & Other Resources:  (Not part of the 30 page limit)

This information is used to assess the capability of the organizational resources, including sub-applicant resources, available to perform the effort proposed. Identify the facilities to be used (Laboratory, Animal, Computer, Office, Clinical, and Other). If appropriate, indicate their capacities, pertinent capabilities, relative proximity, and extent of availability to the project.  Describe only those resources that are directly applicable to the proposed work.  Describe other resources available to the project (e.g., machine shop, electronic shop) and the extent to which they would be available to the project. In order to reduce the number of files attached to your application, please provide the Facility and Other Resource information as an appendix to your project narrative. Do not attach a file in Field 10 of the R&R Other Project Information.

Appendix 6 - Equipment:  (Not part of the 30 page limit)

List major items of equipment already available for this project and, if appropriate identify location and pertinent capabilities. In order to reduce the number of files attached to your application, please provide the Equipment information as an appendix to your project narrative. Do not attach a file in Field 11 of the R&R Other Project Information form.

### Other Attachments (Not part of the 30 page limit)

Attach the following files (Project Management Plan and Letters of Collaboration) to field 12 of the Other Project Information:

- Project Management Plan [MANDATORY] - (Not part of the 30 page limit)

This plan should be formatted to include the following sections with each section to include the information as described below. This plan should describe the structure of the proposed partnership and roles of each member organization including DOE National Laboratory collaborator. This section should also include management/monitoring plans for all sub-awards under this grant and mechanisms for verifying completed milestones:

Executive Summary: Provide a description of the project that includes the objective, project goals, and expected results. For purposes of the application, this information is included in the Project Narrative and should be simply copied to this document for completeness, so that the Project Management Plan is a stand-alone document.

Management Process: Provide a description of the proposed approach to manage the coordination of activities within and amongst the IHE and DOE National Laboratories in the consortia; prioritization, quality, and out-year selection of research including multi-site research; and dialog among, and if needed replenishment of, key personnel.

Success Criteria at Decision Points: Provide success criteria for each decision point in the project, including go/no-go decision points and the conclusions of budget periods and the entire project. The success criteria should be objective and stated in terms of specific, measurable, and repeatable data. Usually, the success criteria pertain to desirable outcomes, results, and observations from the project.

[Note: As the first task in the Statement of Project Objectives, successful applicants will revise the version of the Project Management Plan that is submitted with their applications by including details from the negotiation process. This Project Management Plan will be updated by the Recipient as the project progresses, and the Recipient must use this plan to report schedule and budget variances.]

Risk Management: Provide a summary description of the proposed approach to identify, analyze, and respond to perceived risks associated with the proposed project. Project risk events are uncertain future events that, if realized, impact the success of the project. As a minimum, include the initial identification of significant technical, resource, and management issues that have the potential to impede project progress and strategies to minimize impacts from those issues.

Milestone Log: Provide milestones for each budget period (or phase) of the project. Each milestone should include a title and planned completion date. Milestones should be quantitative and show progress toward budget period and/or project goals.

[Note: During project performance, the Recipient will report the Milestone Status as part of the required quarterly Progress Report as prescribed under Attachment 4, Reporting Requirements Checklist.  The Milestone Status will present actual performance in comparison with Milestone Log, and include:

(1)    the actual status and progress of the project,

(2)    specific progress made toward achieving the project's milestones, and,

(3)    any proposed changes in the project's schedule required to complete

milestones.]

Funding and Costing Profile: Provide a table (the Project Funding Profile) that shows, by budget period, the amount of government funding going to each project team member. Also provide a table (the Project Costing Profile) that projects, by month, the expenditure of government funds for the first budget period, at a minimum.

Project Timeline: Provide a milestone schedule, as described in the Statement of Project Objectives. The timeline should include for each task, a start date, and end date. The timeline should show interdependencies between tasks and include the milestones that are identified in the Milestone Log (Section C).

Save the Project Management Plan in a single file named “PMP.pdf” and upload to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the completed Project Management Plan in PDF format, click the "Add Attachments" button next to item 12 Other Attachments of the R&R Other Project Information form in Grants.gov Workspace.

- Letters of Collaboration [MANDATORY]

Letters of collaboration for unfunded or funded collaborations must state the intention to participate, but they should not be written as recommendation or endorsement letters, which are not allowed. See Section III – Eligibility Information, C. Other Eligibility Requirements for collaborations with DOE National Laboratory Contractors.

Save the Letters of Collaboration in a single file named “Collaboration Letters.pdf” and upload to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the Collaboration Letters in PDF format, click the "Add Attachments" button next to item 12 Other Attachments of the R&R Other Project Information form in Grants.gov Workspace.

If you need to elaborate on your responses to questions 1-6 on the "Other Project Information" document, attach a file in field 12 of the R&R Other Project Information form in Grants.gov Workspace.

### SF424 Research and Related Budget and Information

- SF424 Research and Related (R&R) Budget Form in Grants.gov Workspace [MANDATORY for Prime Applicant and Sub-Applicants (see Note below)]

The R&R Budget Form is part of the Application Package that must be completed in Grants.gov Workspace. The special instructions for completing this form follow:

Applicant must complete a separate budget for each year of support requested. The form will generate a cumulative budget for the total project period. Applicant must complete all the mandatory information on the form before the NEXT PERIOD button is activated. Applicant may request funds under any of the categories listed as long as the item and amount are necessary to perform the proposed work, meet all the criteria for allowability under the applicable Federal cost principles, and are not prohibited by the funding restrictions in this announcement (See Section IV.H). Categories in the Research and Related Budget include:

Section A: Senior/Key Personnel

Section B: Other Personnel

Section C: Equipment Description

Section D: Travel

Section E: Participant/Trainee Costs

Section F: Other Direct Costs

Section G: Indirect Costs

Applicant can hover over the specific fields to view instructions for completing the fields.

NOTE: If sub-applicants will participate in this award, the R&R Subaward Budget Form is mandatory and must be submitted for all sub-applicants. See Section IV – Application and Submission Information, sub-section D. 7. Sub-Applicant Submittal Instructions below for instructions. Also, see Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

- Budget Justification Summary (Attachment A) [MANDATORY for Prime Applicant and Sub-Applicants]

Complete the attached Budget Justification Summary with supporting information requested in the instructions.

Within the Budget Justification Summary form there are several tabs to complete including the Equipment Estimates Summary, Travel Summary, and Materials and Supplies Summary. If funding is requested on the R&R Budget form for equipment, travel, or materials and supplies, these tabs must be completed with the requested information.

- Equipment Summary Estimates tab

If funds are requested for equipment, this form is mandatory and must be completed. Equipment defined as tangible personal property (including information technology systems) having a useful life of more than one year and a per-unit acquisition cost which equals or exceeds the lesser of the capitalization level established by the applicant’s institution for financial statement purposes, or $5,000 must be identified in the Equipment Estimate Summary tab within the Budget Justification form. Please follow the instructions on the form. Quotations must be provided to support the requested funding.

- Travel Estimates Summary tab

If funds are requested for travel, this form is mandatory and must be completed. Awardees and subawardees will also be required to participate in DNN R&D’s annual University Program Review (UPR), the locations and dates to be provided by the Program Office. PIs, or their representative, will be required to give a brief overview of accomplishments. The website address for the institution’s travel policy must be provided in the budget justification.

Information for all travel, including foreign travel must be provided. All requests for foreign travel during performance of an awarded grant not initially provided with your application, must be submitted in advance in writing, to the Grants Officer for approval, and must include the travel dates, location (including any personal travel during the trip), purpose, justification and cost.

- Materials and Supplies Summary tab

If funds are requested for materials and supplies, this form is mandatory and must be completed. Please follow the instructions for completing the Materials and Supplies Summary form. Material & Supplies with an Aggregate Total (the grand total of all Materials and Supplies for the entire project period of performance) exceeding $3,000 requires source documents (vendor quote, quote from internet market research) to be provided if selected for award.

Instructions for attaching Budget Justification to the R&R Budget:

- For the Prime Applicant, to attach the completed Budget Justification Summary in Excel format, click "Add Attachment" in Field L – Budget Justification of the Research and Related Budget form in Grants.gov Workspace.

- For the Sub-Applicants, to attach the completed Budget Justification Summary in Excel format, attach to the R&R Subaward Budget Form, Field L (see Section IV – Application and Submission Information, sub-section D. 7. Sub-Applicant Submittal Instructions below for instructions. Also, see Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

- Government Approved Indirect Rates and Cost Allocations [MANDATORY for Prime Applicant and Sub-Applicants]

If a Negotiated Rate Agreement with Government approved Indirect Rates and Cost Allocations Agreement has been executed with a Governmental cognizant agency, upload the Agreement to the Grants.gov Workspace Attachment form (see instructions on next page). If a Negotiated Rate Agreement does not exist, provide supporting documentation for proposed indirect rates.

The Negotiated Rate Agreement attachment must be uploaded in PDF format to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the Negotiated Indirect Rate Agreement, click the "Add Attachments" button next to item 12 Other Attachments of the R&R Other Project Information form in Grants.gov Workspace.

NOTE: If sub-applicants will participate in this award, this document is mandatory and must be submitted for all sub-applicants. See Section IV – Application and Submission Information, sub-section D. 7. Sub-Applicant Submittal Instructions below for instructions. Also, see Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

### Sub-Applicant Submittal Instructions

If sub-applicants will participate in this award, the following information discussed in detail must be submitted with your application package.

- R&R Subaward Budget Extracted from R&R Subaward Budget Attachments Form [MANDATORY]

If sub-applicants will participate in this award, a separate R&R budget is mandatory for each sub-applicant and must be submitted. The R&R Subaward Budget Attachment is extracted from the R&R SUBAWARD BUDGET ATTACHMENT(S) FORM which is part of the Application Package in Grants.gov Workspace. The extracted R&R subaward budget form should be e-mailed to each sub-applicant that is required to submit a separate budget.

The R&R Subaward Budget form for each sub-applicant must include their Budget Justification Summary Form (Attachment A) in Excel format in Field L of the R&R Subaward Budget form as described in sub-section D. 6. b. Budget Justification Summary above.

After the sub-applicant has e-mailed its completed budget back to you, you must ensure that the R&R Subaward Budget files received from the sub-applicants are the PDF files extracted from the SUBAWARD BUDGET ATTACHMENT(S) FORM. Errors will be created if a sub-applicant sends a prime applicant a budget form that was not extracted from the application package. In addition, ONLY attach the R&R Subaward Budget form for each sub-applicant to the blocks provided on the R&R SUBAWARD BUDGET ATTACHMENT(S) FORM in Grants.gov Workspace. Use up to 10 letters of the sub-applicant’s name as the file name. Filenames should not exceed 50 characters.

- Additional Mandatory Sub-Applicant Documents

When submitting the R&R Subaward Budget form to the sub-applicants, your email should also include a request for the additional sub-applicant documents listed below:

- Application for Federal Assistance SF 424 (R&R) (mandatory);

- Budget Justification Summary (Attachment A) (mandatory);

- Indirect Cost Rate Agreement (mandatory);

- Supporting Information as described above;

- Grants.gov Lobbying Form/Certification Regarding Lobbying (mandatory);

- Disclosure of Lobbying Activities (if applicable); and

The Application for Federal Assistance SF 424 (R&R), the Grants.gov Lobbying Form/Certification Regarding Lobbing, and the Disclosure of Lobbying Activities are available for sub-applicants at https://www.grants.gov/web/grants/forms/r-r-family.html.

The Application for Federal Assistance SF 424 (R&R), Indirect Cost Rate Agreement, Grants.gov Lobbying Form/Certification Regarding Lobbying, and Disclosure of Lobbying Activities (if applicable), for each sub-applicant should be consolidated into a single PDF document and attached to the available blocks in the Attachments Form (see sub-section C. 8 Attachments Form below) in Grants.gov Workspace by clicking “Add Attachment.” Use up to 10 letters of the subawardee’s name as the file name.

See Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

### Attachments Form [MANDATORY for Prime Applicant]

The ATTACHMENTS FORM, which is part of the Application Package in Grants.gov Workspace, will be used for submitting the following files with your application:

- The Sub-Applicant Files other than the R&R Subaward Budget and justification listed below:

- Application for Federal Assistance SF 424 (R&R) (mandatory);

- Indirect Cost Rate Agreement (mandatory);

- Supporting Information as described above;

- Grants.gov Lobbying Form/Certification Regarding Lobbying (mandatory); and

- Disclosure of Lobbying Activities (if applicable);

See Section IV – Application and Submission Information, sub-section D. 7. Sub-Applicant Submittal Instructions above for instructions. Also see Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 2 - Sub-Applicant Mandatory Forms for additional instructions.)

### Financial Assistance Environmental Checklist (Attachment C) [MANDATORY for Prime Applicant if selected for award]

All NNSA grants must comply with the National Environment Policy Act (NEPA) compliance requirements. An applicant who’s Full Application is selected for award negotiations will be required to submit a Financial Assistance Environmental Checklist during the award negotiations phase. All activities – including those conducted by the awardee, sub-awardees, and any other parties – proposed to be funded under the financial assistance award must be described in a single Financial Assistance Environmental Checklist provided in Attachment C (Microsoft Word document) to this announcement in accordance with the instructions contained within the form and Interim Requirements for Completion of Key Sections of the Financial Assistance NEPA Checklist.

NOTE: If selected for award, this form is mandatory, must include activities of the awardee, sub-awardees, and any other parties, and must be submitted. See Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms for additional instructions. Failure to submit the Financial Assistance Environmental Checklist may result in the termination of the award negotiations.

### Project/Performance Site Location(s) [MANDATORY submittal for Prime Applicant to also include sub-applicant information]

The Project/Performance Site Location(s) form is part of the Application Package that should be completed in Grants.gov Workspace. The special instructions for completing this form follow:

Indicate the primary site where the work will be performed. If a portion of the project will be performed at any other site(s) (sub-applicants), identify the site location(s) in the blocks provided.

Note: Be sure to provide the Project/Performance Site Congressional District which is entered in the format of the 2 digit state code followed by a dash and a 3 digit Congressional district code, for example VA-001. Hover over this field for additional instructions. For the Zip/Postal code, be sure to enter the nine-digit postal code.

Use the Next Site button to expand the form to add additional Project/Performance Site Locations.

NOTE: This form is mandatory, must include prime applicant and sub-applicant site locations, and must be submitted. See Section IV – Application and Submission Information, sub-section E. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms for additional instructions.

### Certification Regarding Lobbying or Disclosure of Lobbying Activities

- Certification Regarding Lobbying Form [MANDATORY for Prime Applicant and Sub-Applicants]

Prime Recipients and Subawardees may not use any Federal funds to influence or attempt to influence, directly or indirectly, congressional action on any legislative or appropriation matters.

Complete the “Certification Regarding Lobbying” form to certify that no appropriated funds have been used for lobbying activities. This form is part of the Application Package that should be completed in Grants.gov Workspace.

NOTE: If sub-applicants will participate in this award, this form is mandatory and must be submitted for all sub-applicants. See Section IV – Application and Submission Information, sub-section C. 7. Sub-Applicant Submittal Instructions above for instructions. Also, see Section IV – Application and Submission Information, sub-section D. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

- Disclosure of Lobbying Activities Form (SF-LLL) [MANDATORY – IF APPLICABLE]

If applicable, complete the Disclosure of Lobbying Activities (SF-LLL) form which is part of the Application Package that should be completed in Grants.gov Workspace.  Applicability:  If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the grant/cooperative agreement, you must complete and submit Standard Form – LLL, “Disclosure Form to Report Lobbying.”

NOTE: If sub-applicants will participate in this award and if applicable, this form is mandatory and must be submitted for all sub-applicants. See Section IV – Application and Submission Information, sub-section C. 7. Sub-Applicant Submittal Instructions above for instructions. Also, see Section IV – Application and Submission Information, sub-section D. Summary of Required Forms and Files, Table 1 - Prime Applicant Mandatory Forms and Table 2 - Sub-Applicant Mandatory Forms for additional instructions.

### List of Assurances and Certifications [MANDATORY for Prime Applicant and Sub-Applicants in SAM.gov]

In accordance with the Federal Government’s efforts to reduce reporting burdens for recipients of federal financial assistance, the general certification and representation requirements contained in the Standard Form 424B (SF-424B) – Assurances – Non-Construction Programs, and the Standard Form 424D (SF-424D) – Assurances – Construction Programs, have been standardized federal-wide. On February 2, 2019, GSA implemented a new process in SAM that allows non-federal entity registrants to submit common federal government-wide Representations and Certifications for financial assistance. Non-federal entities creating new SAM registrations and existing non-federal entities completing their annual SAM registration renewals will be required to review and certify their financial assistance Certifications and Representations. Registration in SAM is required prior to receipt of federal awards and must be updated annually by non-federal entities; therefore federal agencies will use the SAM registration information to verify non-federal entity compliance with application and award requirements.

Effective January 1, 2020, the updated general certification and representation requirements will be stored and maintained within the System for Award Management and the SF-424B and SF-424C forms will no longer be requested as mandatory forms from the applicants. The Prime and Sub-Applicants applying under this FOA are required to certify compliance with the standard certifications in SAM as the acknowledgement of compliance will be verified during the Initial Compliance Review. To view instructions on how to submit Representations and Certifications for Financial Assistance in SAM, see the user guide at https://sam.gov/SAM/transcript/SAM_Non_Federal_User_Guide.pdf under section 4.3.2 Entering Representations and Certifications on pages 51-53.

### Requirements for Pass-Through Entities [MANDATORY for Prime Applicant]

The prime applicant (pass-through entity) will be required to perform and provide the results of a budget evaluation and a risk assessment for all sub-applicants.

- Sub-Applicant Budget Evaluation [MANDATORY if selected for award]

If selected for award, the prime applicant must submit the evaluation, which should include an assessment of each sub-applicant’s budget request by cost category. Budget evaluations will help ensure all budget justifications are complete and that the proper attachments are included, for example quotes, and labor verification files. The budget evaluation should also verify that the budget justification explicitly matches the primary budget document and that all indirect expenses are properly calculated.

NOTE: This document must be submitted if selected for award.

- Sub-Applicant Risk Assessment [MANDATORY upon submission of application]

Using the prime applicant’s institutional process (if one is available), evaluate each sub-applicant’s risk of noncompliance to include an assessment of:

  - The sub-applicant’s eligibility to receive federal funding, which can be verified via the government’s System for Award Management.

  - The sub-applicant’s acknowledgment of Representations and Certifications in SAM.

  - The sub-applicant's prior experience with the same or similar sub-awards.

  - The results of previous audits including whether or not the sub-applicant receives a Single Audit in accordance with Subpart F - Audit Requirements of this part, and the extent to which the same or similar sub-award has been audited as a major program;

  - The extent and results of Federal awarding agency monitoring (e.g., if the sub-applicant also receives Federal awards directly from a Federal awarding agency).

NOTE: This document must be submitted for each sub-applicant with the prime-applicant’s application package.

Save all Sub-Applicant Risk Assessments in a single file named “Sub-Applicant Risk Assessments.pdf” and upload to the Grants.gov R&R Other Project Information form, which is part of the Application Package in Grants.gov Workspace. To attach the completed Sub-Applicant Risk Assessments document, click the "Add Attachments" button next to item 12 Other Attachments of the R&R Other Project Information form in Grants.gov Workspace.

## Summary of Required Forms and Files

Your application must include the mandatory documents in the following tables. If forms identified as mandatory are not submitted with the application package by both the Prime applicant and sub-applicants, the application package will be considered non-responsive during the initial compliance review, will not be forwarded for merit review, and will be eliminated from further consideration. For additional information, see Section V – Application Review Information, Initial Review Criteria, and Application Award Eligibility.

| TABLE 1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PRIME APPLICANT MANDATORY FORMS |  |  |  |  |  |  |
|  |  |  |  | Form |  |  |
| √ | # | Document Name | Mandatory? (Yes / No) | Location | Submission Format | Submission Attached to: |
|  | 1 | SF 424 Application for Federal Assistance (R&R) | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 2 | Research and Related (R&R) Other Project Information | Yes | Grants.gov Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 3 | Project Summary/Abstract | Yes | FOA – See Pages 22 for format | PDF | R&R Other Project Information form in Grants.gov Workspace Field 7 - Project Summary/Abstract |
|  | 4a & b | Project Narrative Cover Sheet and Narrative | Yes | FOA – See Pages 23-27 for format | PDF | R&R Other Project Information form in Grants.gov Workspace Field 8 – Project Narrative |
|  | 4c | Appendices |  |  |  |  |
|  |  | - Appendix 1 | Yes |  |  |  |
|  |  | - Appendix 2 | Yes |  |  |  |
|  |  | - Appendix 3 | Yes |  |  |  |
|  |  | - Appendix 4 | Yes |  |  |  |
|  |  | - Appendix 5 | Yes |  |  |  |
|  |  | - Appendix 6 | Yes |  |  |  |
|  | 5a | Project Management Plan | Yes | FOA – See pages 27-28 for format | PDF | Research and Related (R&R) other Project Information form in Grants.gov Workspace Field 12 – Other Attachments |
|  | 5b | Collaboration Letters | Yes | Collaborating Partner | PDF | Research and Related (R&R) other Project Information form in Grants.gov Workspace Field 12 – Other Attachments |
|  | 6a | SF424 Research and Related Budget | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 6b | Budget Justification | Yes | Fedconnect.net Attachment A. | EXCEL | R&R Budget Form in Grants.gov Workspace Field L |
|  | 6c | Government Approved Indirect Rates and Allocations | Yes | From Cognizant Gov’t agency | PDF | Research and Related (R&R) other Project Information form in Grants.gov Workspace Field 12 – Other Attachments |
|  | 7 | R&R Subaward Budget Attachment(s) Form | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | PDF | This form is part of the Grants.gov Workspace Application Package |
|  | 8 | Attachments Form | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | PDF | This form is part of the Grants.gov Workspace Application Package |
|  | 9 | Financial Assistance Environmental Checklist (NEPA) | Yes – If selected for award | Fedconnect.net Attachment B Follow Environmental Checklist Guidance Instructions | PDF | Submission required during the negotiation process. |
|  | 10 | Project/Performance Site Location(s) | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 11a | Certification Regarding Lobbying | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 11b | Disclosure of Lobbying Activities | Yes – If applicable | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 12 | Assurances for Non-Construction Programs | Yes | System for Award Management See FOA page 35, Section IV 12 - List of Assurances and Certifications for SAM instructions | SAM.gov format | SAM.gov NOTE: Will be checked by NNSA Grant Staff in SAM.gov during Compliance Review |
|  | 13a | Sub-Applicant Budget Evaluation | Yes – If selected for award | FOA – See page 35 for requirements | PDF | Submission required during the negotiation process. |
|  | 13b | Sub-Applicant Risk Assessment | Yes | FOA – See page 36 for requirements | PDF | Research and Related (R&R) other Project Information form in Grants.gov Workspace Field 12 – Other Attachments |
|  |  | Data Management Plan Guidance | Yes-If selected for award | Fedconnect.net Attachment C or see FOA-See page 53 for requirements | PDF | Submission required during the negotiation process. |

Link for Fedconnect.net: 	https://www.fedconnect.net/FedConnect/default.htm

| TABLE 2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| SUB-APPLICANT MANDATORY FORMS |  |  |  |  |  |  |
|  |  |  |  | Form |  |  |
| √ | # | Document Name | Mandatory? (Yes / No) | Location | Submission Format | Submission Attached to: |
|  | 1 | SF 424 Application for Federal Assistance (R&R) | Yes | Grants.gov Forms R&R Family | PDF | ATTACHMENTS FORM in Grants.gov Workspace For each sub-applicant submit all required documents of items 1 and 7b as one single PDF document and attach to the Attachment(s) Form in Workspace |
|  | 4a & b | Project Narrative Cover Sheet and Narrative | No | FOA – See Pages 23 – 27 for format | PDF | R&R Other Project Information form in Grants.gov Workspace Field 8 – Project Narrative |
|  | 4c | Appendices ­ Appendix 1 ­ Appendix 2 ­ Appendix 3 ­ Appendix 4 ­ Appendix 5 ­ Appendix 6 | Yes Yes Yes Yes Yes Yes Yes |  |  |  |
|  | 7a | R&R Subaward Budget Form | Yes | Extracted from R&R Subaward Budget Attachment(s) Form from Grants.gov Workspace tab and emailed to subawardee to complete | PDF | R&R Subaward Budget Attachment(s) Form in Grants.gov Workspace. |
|  |  | Budget Justification | Yes | Fedconnect.net Attachment A | EXCEL | Attach to the R&R Subaward Budget Form Field L |
|  | 7b | Certification Regarding Lobbying | Yes | Grants.gov Forms R&R Family | PDF | ATTACHMENTS FORM in Grants.gov Workspace For each sub-applicant submit all required documents of items 1 and 7b as one single PDF document and attach to the Attachment(s) Form in Workspace |
|  |  | Disclosure of Lobbying Activities | Yes - If applicable | Grants.gov Forms R&R Family | PDF |  |
|  |  | Government Approved Indirect Rates and Allocations | Yes | From Cognizant Gov’t agency | PDF |  |
|  | 10 | Project/Performance Site Location(s) | Yes | Grants.gov Workspace under Manage Workspace Tab, Forms Tab | Grants.gov Workspace format | This form is part of the Grants.gov Workspace Application Package |
|  | 12 | Assurances for Non-Construction Programs | Yes | System for Award Management See FOA page 35, Section IV 12 - List of Assurances and Certifications for SAM instructions | SAM.gov format | SAM.gov NOTE: Will be checked by NNSA Grant Staff in SAM.gov during Compliance Review |

Link for Grants.gov:   	https://www.grants.gov/web/grants/forms/r-r-family.html

## Submissions from Successful Applicants

If selected for award, DOE/NNSA reserves the right to request additional or clarifying information for any reason deemed necessary, including, but not limited to:

- Indirect cost information

- Other budget information including Equipment and Material and Supplies supporting documentation (purchase orders, quotes, invoices, etc).

- Name and phone number of the Designated Responsible Employee for complying with national policies prohibiting discrimination (See 2 CFR 200.300(a))

- Representation of Limited Rights Data and Restricted Software, if applicable

- Upon selection, prior written approval from the Contracting Officer having cognizance over the DOE/NNSA Site Facility Management Contractors, for use, under this award, of any equipment, facility, or personnel at the DOE National Laboratory Contractors.

Budget Revision, as needed to align with funding or voluntary committed cost sharing.

## Submission Dates and Times

Applications should be received by September 20, 2022, not later than 23:59:59 PM Eastern Time. You are encouraged to transmit your application well before the deadline. The Grants.gov Helpdesk is available for extended periods, please check their website for the Helpdesk hours of operation.  APPLICATIONS RECEIVED AFTER THE DEADLINE WILL NOT BE REVIEWED OR CONSIDERED FOR AWARD.

## Intergovernmental Review

This program is not subject to Executive Order 12372 - Intergovernmental Review of Federal Programs.

## Funding Restrictions (December 2014)

Funding for all awards and future budget periods are contingent upon the availability of funds appropriated by Congress for the purpose of this program and the availability of future-year budget authority.

Cost Principles. Costs must be allowable, allocable and reasonable in accordance with the applicable Federal cost principles referenced in 2 CFR part 200 as amended by 2 CFR part 910 [DOE Financial Assistance Regulation].  The cost principles for commercial organization are in FAR Part 31.

Pre-award Costs. Recipients may charge to an award resulting from this announcement pre-award costs that were incurred within the ninety (90) calendar day period immediately preceding the effective date of the award, if the costs are allowable in accordance with the applicable Federal cost principles referenced in 2 CFR part 200 as amended by 2 CFR part 910 [DOE Financial Assistance Regulation].  Recipient must notify the Grants Management Specialist in writing if the 90-day pre-award cost option will be used. Recipients must obtain the prior approval of the contracting officer for any pre-award costs that are for periods greater than this 90 day calendar period.

Recipients must obtain the prior approval from the Contracting Officer for any pre-award costs that are for periods greater than this 90 day calendar period.  Upon selection, requests for pre-award costs greater than 90 days should include a justification needed to cover requested pre-award costs along with a detailed breakdown of budget by cost element (ex:  labor, travel, materials, supplies, etc).  Pre-award costs are allowable only to the extent that they would have been allowable if incurred after the date of the Federal award.

IHEs are encouraged to start recruitment of students and postdocs early and be prepared for an immediate start at the beginning of Period of Performance.  Consequently, there may be a substantial lead time necessitating the aforementioned request for pre-award costs beyond 90 days.

Pre-award costs are incurred at the applicant's risk. DOE is under no obligation to reimburse such costs if for any reason the applicant does not receive an award or if the award is made for a lesser amount than the applicant expected.

# Section V - APPLICATION REVIEW INFORMATION

## Criteria

### Initial Review Criteria

Application Award Eligibility

Prior to a comprehensive merit evaluation, DOE will perform an initial review to determine that (1) the applicant is eligible for an award; (2) the mandatory information required by the funding opportunity announcement has been submitted; and (3) the proposed project is responsive to the objectives of the funding opportunity announcement. Applications that fail to pass the initial review will not be forwarded for merit review and will be eliminated from further consideration.

### Merit Review Criteria

All applications passing the initial review will be evaluated in accordance with the following Merit Review Criteria:

#### Criterion 1 – Technical Merit – 40%

- Innovative nature of the proposed nuclear forensic research (innovation is a plus)

- Does the proposed research complement on-going research at the DOE National Laboratories?

- What is the likelihood the stated research objectives are achievable?  Is the risk well understood?

- Extent to which the application supports the continued development of nuclear forensic-related disciplines

- Extent to which the application supports the development and sustainment of the next generation of nuclear forensics professionals

- Extent to which the plan integrates multiple scientific, engineering and other disciplines to achieve stated objectives, and that proposed activities are well-reasoned, well-organized, and based on a sound rationale.

#### Criterion 2 – Applicant Team Capabilities – 40%

- The likelihood that the applicant’s described approach and structure (e.g., communication, coordination, and integration) to managing the consortium, including a framework for coordinating DOE National Laboratory interactions, will lead to the successful performance of the proposed work and objectives under this FOA

- Qualifications, capabilities and experience of the principal investigators, team leaders, and key personnel involved

- PI time commitment to the project (refer to Current and Pending Support):  If the same PI is already working on multiple awards, consideration should be given if the PI can make significant contribution to the proposed project considering time commitments to other project awards.

- The likelihood that the applicant’s resources and facilities, including key and unique facilities, as identified by the applicant, will lead to the successful achievement of the proposed work and objectives under this FOA

#### Criterion 3 – Past Experience – 20%

- Extent of experience the lead institution has in implementing and managing similar programs of this size

- Extent of experience the lead institution has with building and managing a multi-component consortium/organization, and to what extent has the applicant had past or on-going working relationships with the DOE National Laboratory system

- Likelihood the consortium’s relevant experience and past, and on-going relationships with the DOE National Laboratory system will lead to success.

# Other Selection Factors - Program Policy Factors

The Selection Official will evaluate applications on the following Program Policy Factors:

- Preference will be given to applications which propose a group of projects which represent a diversity of technical approaches and methods; and

- Preference will be given to applications which complement existing funded efforts or projects, which, when considered together, will better advance overall research goals and objectives.

The Selection Official will place special emphasis on applications that include the participation of Historically Black Colleges and Universities and other Minority Serving Institutions.

Proposed budgets and costs will be evaluated for those applications which receive the highest merit review ratings to determine whether the budgets are substantiated and reasonable.  NNSA reserves the right to request applicants to provide additional/supplemental information to verify costs and to justify proposed budgets.  NNSA also reserves the right to negotiate changes to any proposed budget and/or project scope prior to making award to any applicant.  NNSA shall not make awards based on unreasonable budgets or where costs outweigh any advantages in the technical approach.

## Review and Selection Process

### Merit Review

Applications Subject to Merit Review

Applications that pass the initial review will be subjected to a merit review in accordance with the guidance provided in the "Department of Energy Merit Review Guide for Financial Assistance."  This guide is available at https://energy.gov/management/office-management/operational-management/financial-assistance under Financial Assistance Policy and Guidance.

### Selection Official Consideration

The Selection Official will consider the merit review recommendation, program policy factors, and the amount of funds available.

### Review of Risk

Pursuant to 2 CFR 200.205, DOE will conduct an additional review of the risk posed by applications submitted under this FOA. Such review of risk will include:

- Technical merit of the application,

- Reports and findings from audits performed under 2 CFR 200 or OMB Circular A-133, and

- Systems maintained under 2 CFR 180, including the SAM “Exclusions” and “Do Not Pay” systems.

DOE may make use of other publicly available information and the history of an applicant’s performance under DOE or other Federal agency awards.

Applicants with no prior performance of DOE awards may be asked to provide information about their financial stability and or their ability to comply with the management standards of 2 CFR 200.

### Reporting of Matters Related to Recipient Integrity and Performance (December 2015)

DOE, prior to making a Federal award with a total amount of Federal share greater than the simplified acquisition threshold, is required to review and consider any information about the applicant that is in the designated integrity and performance system accessible through SAM (currently FAPIIS) (see 41 U.S.C. 2313).

The applicant, at its option, may review information in the designated integrity and performance systems accessible through SAM and comment on any information about itself that a Federal awarding agency previously entered and is currently in the designated integrity and performance system accessible through SAM.

DOE will consider any written comments by the applicant, in addition to the other information in the designated integrity and performance system, in making a judgment about the applicant's integrity, business ethics, and record of performance under Federal awards when completing the review of risk posed by applicants as described in 2 CFR 200.205 - Federal awarding agency review of risk posed by applicants.

### Government Discussions with Applicant (December 2014)

The Government may enter into discussions with a selected applicant for any reason deemed necessary, including but not limited to: (1) the budget is not appropriate or reasonable for the requirement; (2) only a portion of the application is selected for award; (3) the Government needs additional information to determine that the recipient is capable of complying with the requirements in 2 CFR part 200 as amended by 2 CFR part 910 [DOE Financial Assistance Regulation]; and/or (4) special terms and conditions are required.  Failure to resolve satisfactorily the issues identified by the Government will preclude award to the applicant.

## Anticipated Notice of Selection and Award Dates

DOE/NNSA anticipates notifying the applicant selected for award by January 2023.  The award is expected to start on July 01, 2023, depending on availability of funds.

# Section VI - AWARD ADMINISTRATION INFORMATION

## Award Notices

### Notice of Selection

DOE will notify applicants selected for award. This notice of selection is not an authorization to begin performance. (See Section IV.H with respect to the allowability of pre-award costs.)

### Non-selected Notification

Organizations whose applications have not been selected will be advised as promptly as possible.  This notice will explain why the application was not selected.

### Notice of Award (December 2014)

An Assistance Agreement issued by the contracting officer is the authorizing award document.  It normally includes either as an attachment or by reference: (1) Special Terms and Conditions; (2) Intellectual Property Provisions; (3) Federal Assistance Reporting Checklist, which identifies the reporting requirements; (4) R&R Budget; (5) 2 CFR part 200 as amended by 2 CFR part 910 [DOE Financial Assistance Regulation]; and (6) National Policy Assurances To Be Incorporated As Award Terms.

## Administrative and National Policy Requirements

Administrative Requirements

The administrative requirements for DOE grants and cooperative agreements are contained in 2 CFR Part 200 as amended by 2 CFR Part 910 (See: http://www.eCFR.gov).

DOE Special Terms and Conditions for Use in Most Grants and Cooperative Agreements. The DOE Special Terms and Conditions for Use in Most Grants and Cooperative Agreements are located at http://energy.gov/management/office-management/operational-management/financial-assistance/financial-assistance-forms under Award Terms.

National Policy Requirements. The National Policy Assurances that are incorporated as a term and condition of award are located at: https://energy.gov/management/office-management/operational-management/financial-assistance/financial-assistance-forms.

Intellectual Property Provisions.  The standard DOE financial assistance intellectual property provisions applicable to the various types of recipients are located at:

http://energy.gov/gc/standard-intellectual-property-ip-provisions-financial-assistance-awards.

Statement of Federal Stewardship

DOE will exercise normal Federal stewardship in overseeing the project activities performed under DOE Awards. Stewardship Activities include, but are not limited to, conducting site visits; reviewing performance and financial reports, providing assistance and/or temporary intervention in usual circumstances to correct deficiencies that develop during the project; assuring compliance with terms and conditions; and reviewing technical performance after project completion to ensure that the project objectives have been accomplished.

DUNS and SAM Requirements

Additional administrative requirements for DOE grants and cooperative agreements are contained in 2 CFR, Part 25 (See: http://www.eCFR.gov). Prime awardees must keep their data at the System for Award Management (SAM) current at http://www.sam.gov current SAM is the government-wide system that replaced the CCR. If you had an active registration in the CCR, you have an active registration in SAM. Subawardees at all tiers must obtain DUNS numbers and provide the DUNS to the prime awardee before the subaward can be issued.

Foreign National Access to DOE National Laboratories

All applicants that ultimately enter into an award resulting from this FOA will be subject to the following requirement concerning foreign national involvement. Upon DOE’s request, Prime Recipients must provide information to facilitate DOE’s responsibilities associated with foreign national access to DOE sites, information, technologies, and equipment. A foreign national is defined as any person who was born outside the jurisdiction of the United States, is a citizen of a foreign government, and has not been naturalized under U.S. law. If the Prime Recipient or Subrecipients, contractors or vendors under the award, anticipate utilizing a foreign national person in the performance of an award, the Prime Recipient is responsible for providing to the Contracting Officer specific information of the foreign national(s) to satisfy compliance with all of the requirements for access approval.

## Reporting

Reporting requirements are identified on the Federal Assistance Reporting Checklist, DOE F 4600.2, attached to the award agreement. The checklist is available at: http://energy.gov/management/office-management/operational-management/financial-assistance/financial-assistance-forms under Award Forms.

Awardees are also required to submit quarterly reports and yearly metrics when the program is assembling IUP metrics and various internal reports.

Dissemination of scientific/technical reports. Scientific/technical reports submitted under this

award will be disseminated on the Internet via the DOE Information Bridge (www.osti.gov/bridge), unless

the report contains patentable material, protected data, or SBIR/STTR data. Citations for journal articles

produced under the award will appear on the DOE Energy Citations Database

(www.osti.gov/energycitations).

Restrictions. Reports submitted to the DOE Information Bridge must not contain any Protected

Personal Identifiable Information (PII), limited rights data (proprietary data), classified information,

information subject to export control classification, or other information not subject to release.

## Applicant Representations and Certifications

Lobbying Restrictions

By accepting funds under this award, you agree that none of the funds obligated on the award shall be expended, directly or indirectly, to influence congressional action on any legislation or appropriation matters pending before Congress, other than to communicate to Members of Congress as described in 18 U.S.C. 1913. This restriction is in addition to those prescribed elsewhere in statute and regulation.

Corporate Felony Conviction and Federal Tax Liability Representations (March 2014)

In submitting an application in response to this FOA the Applicant represents that:

(1) It is not a corporation that has been convicted of a felony criminal violation under any Federal law within the preceding 24 months; and

(2) It is not a corporation that has any unpaid Federal tax liability that has been assessed, for which all judicial and administrative remedies have been exhausted or have lapsed, and that is not being paid in a timely manner pursuant to an agreement with the authority responsible for collecting the tax liability.

For purposes of these representations the following definition applies:

A Corporation includes any entity that has filed articles of incorporation in any of the 50 states, the District of Columbia, or the various territories of the United States [but not foreign corporations]. It includes both for-profit and non-profit organizations.

Nondisclosure and Confidentiality Agreements Representations (June 2015)

In submitting an application in response to this FOA the Applicant represents that:

(1) It does not and will not require its employees or contractors to sign internal nondisclosure or confidentiality agreements or statements prohibiting or otherwise restricting its employees or contactors from lawfully reporting waste, fraud, or abuse to a designated investigative or law enforcement representative of a Federal department or agency authorized to receive such information.

(2) It does not and will not use any Federal funds to implement or enforce any nondisclosure and/or confidentiality policy, form, or agreement it uses unless it contains the following provisions:

a.	‘‘These provisions are consistent with and do not supersede, conflict with, or otherwise alter the employee obligations, rights, or liabilities created by existing statute or Executive order relating to (1) classified information, (2) communications to Congress, (3) the reporting to an Inspector General of a violation of any law, rule, or regulation, or mismanagement, a gross waste of funds, an abuse of authority, or a substantial and specific danger to public health or safety, or (4) any other whistleblower protection. The definitions, requirements, obligations, rights, sanctions, and liabilities created by controlling Executive orders and statutory provisions are incorporated into this agreement and are controlling.’’

b.	The limitation above shall not contravene requirements applicable to Standard Form 312, Form 4414, or any other form issued by a Federal department or agency governing the nondisclosure of classified information.

Notwithstanding provision listed in paragraph (a), a nondisclosure or confidentiality policy form or agreement that is to be executed by a person connected with the conduct of an intelligence or intelligence-related activity, other than an employee or officer of the United States Government, may contain provisions appropriate to the particular activity for which such document is to be used. Such form or agreement shall, at a minimum, require that the person will not disclose any classified information received in the course of such activity unless specifically authorized to do so by the United States Government. Such nondisclosure or confidentiality forms shall also make it clear that they do not bar disclosures to Congress, or to an authorized official of an executive agency or the Department of Justice, that are essential to reporting a substantial violation of law.

Subaward and Executive Reporting

Prime Recipients awarded a new Federal financial assistance award greater than or equal to $25,000 as of October 1, 2010 are subject to Federal Funding and Transparency Act of 2006 (FFATA) sub-award reporting requirements as outlined in 2 CFR Chapter 1, Part 170 REPORTING SUB-AWARD AND EXECUTIVE COMPENSATION INFORMATION.

The FFATA Subaward Reporting System (FSRS) is the reporting tool Federal prime awardees (i.e. prime contractors and prime grants recipients) use to capture and report subaward and executive compensation data regarding their first-tier subawards to meet the FFATA reporting requirements. Prime awardees must register with the new FSRS database and report the required data on their first tier subawardees at http://www.fsrs.gov.

Prime awardees must report the executive compensation for their own executives as part of their registration profile in the System for Award Management (SAM).  The sub-award information entered in FSRS will then be displayed on www.USASpending.gov associated with the prime award furthering Federal spending transparency.

Applicants must ensure they have the necessary processes and systems in place to comply with the reporting requirements should they receive funding.

### Statement of Substantial Involvement

The Contracting Officer and Program Manager will negotiate a Statement of Substantial Involvement prior to award of the cooperative agreement.

Conference Spending

The recipient shall not expend any funds on a conference not directly and programmatically related to the purpose for which the grant or cooperative agreement was awarded that would defray the cost to the United States Government of a conference held by any Executive branch department, agency, board, commission, or office for which the cost to the United States Government would otherwise exceed $20,000, thereby circumventing the required notification by the head of any such Executive Branch department, agency, board, commission, or office to the Inspector General (or senior ethics official for any entity without an Inspector General), of the date, location, and number of employees attending such conference.

# Section VII - QUESTIONS/AGENCY CONTACTS

## Questions

Questions regarding the content of the announcement must be submitted through the FedConnect portal. You must register with FedConnect to respond as an interested party to submit questions, and to view responses to questions. It is recommended that you register as soon after release of the FOA as possible to have the benefit of all responses. DOE/NNSA will try to respond to a question within 3 business days, unless a similar question and answer have already been posted on the website.

Questions and comments concerning this FOA shall be submitted not later than 3 calendar days prior to the application due date.

Questions relating to the registration process, system requirements, how an application form works, or the submittal process must be directed to Grants.gov at 1-800-518-4726 or support@grants.gov. DOE/NNSA cannot answer these questions.

## Agency Contact

Name:	Paul Herrera

Via:	https://www.fedconnect.net

# Section VIII - OTHER INFORMATION

## Modifications

Notices of any modifications to this announcement will be posted on Grants.gov and the FedConnect portal. You can receive an email when a modification or an announcement message is posted by registering with FedConnect as an interested party for this FOA. It is recommended that you register as soon after release of the FOA as possible to ensure you receive timely notice of any modifications or other announcements.

## Government Right to Reject or Negotiate

DOE reserves the right, without qualification, to reject any or all applications received in response to this announcement and to select any application, in whole or in part, as a basis for negotiation and/or award.

## Commitment of Public Funds

The Contracting Officer is the only individual who can make awards or commit the Government to the expenditure of public funds. A commitment by other than the Contracting Officer, either explicit or implied, is invalid.

Funding for all awards and future budget periods are contingent upon the availability of funds appropriated by Congress for the purpose of this program and the availability of future-year budget authority.

## Proprietary Application Information

Patentable ideas, trade secrets, proprietary or confidential commercial or financial information, disclosure of which may harm the applicant, should be included in an application only when such information is necessary to convey an understanding of the proposed project. The use and disclosure of such data may be restricted, provided the applicant includes the following legend on the first page of the project narrative and specifies the pages of the application which are to be restricted:

"The data contained in pages [Insert pages] of this application have been submitted in confidence and contain trade secrets or proprietary information, and such data shall be used or disclosed only for evaluation purposes, provided that if this applicant receives an award as a result of or in connection with the submission of this application, DOE shall have the right to use or disclose the data herein to the extent provided in the award. This restriction does not limit the government's right to use or disclose data obtained without restriction from any source, including the applicant."

To protect such data, each line or paragraph on the pages containing such data must be specifically identified and marked with a legend similar to the following:

"The following contains proprietary information that (name of applicant) requests not be released to persons outside the Government, except for purposes of review and evaluation."

## Evaluation and Administration by Non-Federal Personnel

In conducting the merit review evaluation, the Government may seek the advice of qualified non Federal personnel as reviewers. The Government may also use non-Federal personnel to conduct routine, nondiscretionary administrative activities. The applicant, by submitting its application, consents to the use of non-Federal reviewers/administrators. Non-Federal reviewers must sign conflict of interest and non-disclosure agreements prior to reviewing an application.  Non-Federal personnel conducting administrative activities must sign a non-disclosure agreement.

## Intellectual Property Developed Under this Program

Patent Rights.  The government will have certain statutory rights in an invention that is conceived or first actually reduced to practice under a DOE award. 42 U.S.C. 5908 provides that title to such inventions vests in the United States, except where 35 U.S.C. 202 provides otherwise for nonprofit organizations or small business firms.  However, the Secretary of Energy may waive all or any part of the rights of the United States subject to certain conditions. (See "Notice of Right to Request Patent Waiver" in paragraph G below.)

Rights in Technical Data. Normally, the government has unlimited rights in technical data created under a DOE agreement. Delivery or third party licensing of proprietary software or data developed solely at private expense will not normally be required except as specifically negotiated in a particular agreement to satisfy DOE's own needs or to insure the commercialization of technology developed under a DOE agreement.

## Notice of Right to Request Patent Waiver

Applicants may request a waiver of all or any part of the rights of the United States in inventions conceived or first actually reduced to practice in performance of an agreement as a result of this announcement, in advance of or within 30 days after the effective date of the award. Even if such advance waiver is not requested or the request is denied, the recipient will have a continuing right under the award to request a waiver of the rights of the United States in identified inventions, i.e., individual inventions conceived or first actually reduced to practice in performance of the award. Any patent waiver that may be granted is subject to certain terms and conditions in 10 CFR 784 see http://www.energy.gov/gc/services/technology-transfer-and-procurement/office-assistant-general-counsel-technology-transf-1 for further information. Domestic small businesses and domestic nonprofit organizations will receive the patent rights clause at 37 CFR 401.14, i.e., the implementation of the Bayh-Dole Act.  This clause permits domestic small business and domestic nonprofit organizations to retain title to subject inventions. Therefore, small businesses and nonprofit organizations do not need to request a waiver.

## Notice Regarding Eligible/Ineligible Activities

Eligible activities under this program include those which describe and promote the understanding of scientific and technical aspects of specific energy technologies, but not those which encourage or support political activities such as the collection and dissemination of information related to potential, planned or pending legislation.

## Protected Personally Identifiable Information

In responding to this FOA, applicants must ensure that Protected Personally Identifiable Information (PII) is not included in the application documents. These documents will be used by the Merit Review Committee in the review process to evaluate each application. PII is defined by the Office of Management and Budget (OMB) as:

Any information about an individual maintained by an agency, including but not limited to, education, financial transactions, medical history, and criminal or employment history and information that can be used to distinguish or trace an individual’s identity, such as their name, social security number, date and place of birth, mother’s maiden name, biometric records, etc., including any other personal information that is linked or linkable to an individual.

This definition of PII can be further defined as: (1) Public PII and (2) Protected PII.

1. Public PII: PII found in public sources such as telephone books, public websites, business cards, university listing, etc. Public PII includes first and last name, address, work telephone number, email address, home telephone number, and general education credentials.

2. Protected PII: PII that requires enhanced protection. This information includes data that if compromised could cause harm to an individual such as identity theft.

## Annual Compliance Audits

If an institute of higher education, non-profit organization, or state/local government is a Prime Recipient or Subrecipient and has expended $750,000 or more of Federal funds during the non-Federal entity's fiscal year, then a single or program-specific audit is required.  For additional information, please refer to 2 C.F.R. § 200.501 and Subpart F.

If a for-profit entity is a Prime Recipient or Subrecipient and has expended $750,000 or more of DOE funds during the entity's fiscal year, an annual compliance audit performed by an independent auditor is be required.  For additional information, please refer to 2 C.F.R. § 910.501 and Subpart F.

Applicants and sub-recipients (if applicable) should propose sufficient costs in the project budget to cover the costs associated with the audit. DOE will share in the cost of the audit at its applicable cost share ratio.

# Section IX - APPENDICES/REFERENCE MATERIAL

Attachments in FedConnect.Net

  - Budget Justification Form

  - Financial Assistance Environmental Checklist

## DATA MANAGEMENT PLAN GUIDANCE (SEPT 2015)

An applicant who’s Full Application is selected for award will be required to submit a Data Management Plan within ninety 90 days of the award notification. A Data Management Plan (“DMP”) explains how data generated in the course of the research or work performed under an assistance award will be shared and preserved or, when justified, explains why data sharing or preservation is not possible or scientifically appropriate.  Failure to submit the Data Management Plan may result in the termination of the award.

DMP Requirements

In order for a DMP to be considered acceptable, the DMP must address the following:

At a minimum, the DMP must describe how data sharing and preservation will enable validation of the results from the proposed work, or how results could be validated if data are not shared or preserved.

The DMP must provide a plan for making all research data displayed in publications resulting from the proposed work digitally accessible at the time of publication. This includes data that are displayed in charts, figures, images, etc. In addition, the underlying digital research data used to generate the displayed data should be made as accessible as possible in accordance with the principles stated above. This requirement could be met by including the data as supplementary information to the published article, or through other means. The published article should indicate how these data can be accessed.

The DMP should consult and reference available information about data management resources to be used in the course of the proposed research work. In particular, a DMP that explicitly or implicitly commits data management resources at a facility beyond what is conventionally made available to approved users should be accompanied by written approval from that facility. In determining the resources available for data management at DOE User Facilities, researchers should consult the published description of data management resources and practices at that facility and reference it in the DMP. Information about other DOE facilities can be found in the additional guidance from the sponsoring program.

The DMP must protect confidentiality, personal privacy, Personally Identifiable Information, and U.S. national, homeland, and economic security; recognize proprietary interests, business confidential information, and intellectual property rights; avoid significant negative impact on innovation, and U.S. competitiveness; and otherwise be consistent with all laws (e.g., export control laws), and DOE regulations, orders, and policies.

Data Determination for a DMP

The Principal Investigator should determine which data should be the subject of the DMP and, in the DMP, propose which data should be shared and/or preserved in accordance with the DMP Requirements noted above.

For data that will be generated through the course of the proposed research/work, the Principal Investigator should indicate what types of data should be protected from immediate public disclosure by DOE (referred to as “protected data”) and what types of data that DOE should be able to release immediately.  Similarly, for data developed outside of the proposed research work at private expense that will be used in the course of the proposed research work, the Principal Investigator should indicate whether that type of data will be subject to public release or kept confidential (referred to as “limited rights data”).   Any use of limited rights data or labeling of data as “protected data” must be consistent with the DMP Requirements noted above.

Suggested Elements for a DMP

The following list of elements for a DMP provides suggestions regarding the data management planning process and the structure of the DMP:

Data Types and Sources: A brief, high-level description of the data to be generated or used through the course of the proposed research work and which of these are considered digital research data necessary to validate the research findings or results.

Content and Format:  A statement of plans for data and metadata content and format including, where applicable, a description of documentation plans, annotation of relevant software, and the rationale for the selection of appropriate standards. Existing, accepted community standards should be used where possible. Where community standards are missing or inadequate, the DMP could propose alternate strategies for facilitating sharing, and should advise the sponsoring program of any need to develop or generalize standards.

Sharing and Preservation: A description of the plans for data sharing and preservation. This should include, when appropriate: the anticipated means for sharing and the rationale for any restrictions on who may access the data and under what conditions; a timeline for sharing and preservation that addresses both the minimum length of time the data will be available and any anticipated delay to data access after research findings are published; any special requirements for data sharing, for example, proprietary software needed to access or interpret data, applicable policies, provisions, and licenses for re-use and re-distribution, and for the production of derivatives, including guidance for how data and data products should be cited; any resources and capabilities (equipment, connections, systems, software, expertise, etc.) requested in the research proposal that are needed to meet the stated goals for sharing and preservation (this could reference the relevant section of the associated research proposal and budget request); and whether/where the data will be preserved after direct project funding ends and any plans for the transfer of responsibilities for sharing and preservation.

Protection:  A statement of plans, where appropriate and necessary, to protect confidentiality, personal privacy, Personally Identifiable Information, and U.S. national, homeland, and economic security; recognize proprietary interests, business confidential information, and intellectual property rights; and avoid significant negative impact on innovation, and U.S. competitiveness.

Rationale: A discussion of the rationale or justification for the proposed data management plan including, for example, the potential impact of the data within the immediate field and in other fields, and any broader societal impact.

Additional Guidance:

In determining which data should be shared and preserved, researchers must consider the data needed to validate research findings as described in the DMP Requirements, and are encouraged to consider the potential benefits of their data to their own fields of research, fields other than their own, and society at large.

DMPs should reflect relevant standards and community best practices and make use of community accepted repositories whenever practicable.

Costs associated with the project description/scope of work and resources articulated in a DMP may be included in the proposed research budget as permitted by the applicable cost principles.

To improve the discoverability of and attribution for datasets created and used in the course of research, DOE encourages the citation of publicly available datasets within the reference section of publications, and the identification of datasets with persistent identifiers such as Digital Object Identifiers (DOIs). In most cases, DOE can provide DOIs free of charge for data resulting from DOE-funded research through its Office of Scientific and Technical Information (OSTI) Data ID Service.

Definitions:

Data Preservation: Data preservation means providing for the usability of data beyond the lifetime of the research activity that generated them.

Data Sharing: Data sharing means making data available to people other than those who have generated them. Examples of data sharing range from bilateral communications with colleagues, to providing free, unrestricted access to anyone through, for example, a web-based platform.

Digital Research Data: The term digital data encompasses a wide variety of information stored in digital form including: experimental, observational, and simulation data; codes, software and algorithms; text; numeric information; images; video; audio; and associated metadata. It also encompasses information in a variety of different forms including raw, processed, and analyzed data, published and archived data.

Research Data: The recorded factual material commonly accepted in the scientific community as necessary to validate research findings, but not any of the following: preliminary analyses, drafts of scientific papers, plans for future research, peer reviews, or communications with colleagues. This 'recorded' material excludes physical objects (e.g., laboratory samples). Research data also do not include:

(A) Trade secrets, commercial information, materials necessary to be held confidential by a researcher until they are published, or similar information which is protected under law; and

(B) Personnel and medical information and similar information the disclosure of which would constitute a clearly unwarranted invasion of personal privacy, such as information that could be used to identify a particular person in a research study.”

Validate: In the context of DMPs, validate means to support, corroborate, verify, or otherwise determine the legitimacy of the research findings. Validation of research findings could be accomplished by reproducing the original experiment or analyses; comparing and contrasting the results against those of a new experiment or analyses; or by some other means.