FORSATY Global Performance FY2013 to FY2019

Global Objective: Marginalized youth are integrated, productive citizens
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	POI.1 % of marginalized youth who, after exposure to project, are productively engaged m/f 
	
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	60%
	53%
	60%
	53%

	POI. 2: % of target youth who improve their score on the project Internal asset self-assessment  (m/f)
	42%
youth with negative perception
	NA
	NA
	NA
	NA
	75%
	70%
	NA
	NA
	NA
	NA
	75%
	38%
	73%
	54%

	POI. 3: Proportion of target population reporting increased agreement with the concept that males and females should have equal access to social, economic and political opportunities
	59%
Youth with positive perception
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	NA
	50%
	77%
	50%
	77%







Sub-Purpose 1: Youth are full-fledged citizens in their neighborhoods and cities
Outcome 1.1 Neighborhoods empower and bond youth
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.1 # of community improvement actions implemented by FORSATY implementing partners in collaboration with CBOs in target neighborhoods as a result of program support.
	0
	NA
	NA
	4
	50
	4
	24
	29
	47
	35
	75
	18
	73
	90
	269

	1.1.1 Youth are empowered through organized activities

	OTP.1 # of community youth leaders in target neighborhoods who participate in project supported training activities. (m/f) performance indicator for PPR starting FY18 
	0
	NA
	NA
	75
	0
	90
	117
(24F; 26M)
	105
	134
 (32F, 102M)
	150
	126           (44F, 82M)
	150
	161 (58F, 103M)
	570
	538 (158F, 380M)

	1.1.2 Youth have access to relevant opportunities and services

	OTP.2 # of target youth participating in community activities organized by FORSATY implementing partners who receive orientation, referral, counseling or and placement services. (m/f)  (newly added starting FY17)
	0
	NA
	NA
	NA
	NA
	NA
	NA
	150
	298 
(51F, 247M) 
	200
	281          (53F, 288M)
	100
	152 (09F, 143M)
	450
	731 (113F, 618M)



Outcome 1.2 Youth are engaged in their social and political environment
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.2 # of advocacy actions in favor of marginalized youth needs carried out by project supported community youth leaders
	0
	NA
	NA
	5
	0
	10
	13
	15
	16
	15
	22
	4
	2
	49
	53

	1.2.1  Disadvantaged youth develop a positive sense of belonging to their neighborhood and their city

	1.2.2  Youth leaders take initiatives within the neighborhood

	OTP.3 # of youth who participate in community improvement actions and youth council outreach activities implemented with/by FORSATY implementing partners in collaboration with CBOs target neighborhoods. (m/f)
	0
	NA
	NA
	150
	704
(15F;  689M)
	150
	815 
(113F; 702M)
	620
	1697
 (421F, 1276M)
	900
	3699     (817F, 2882M)
	900
	3048     (455F, 2593M)
	1820
	9963
(455F, 2593M)

	1.2.3 Youth councils maintain a dialogue with the authorities

	No separate indicator proposed. Performance achieving this output will be measured by OTC.2






Outcome 1.3 Powerholders are responsive to youth needs and proposals
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.3 # of policies created, modified or implemented taking into consideration community youth input.
	0
	NA
	NA
	0
	0
	5
	0
	8
	11
	8
	2 
	1
	0
	22
	13

	1.3.1  Powerholders communicate and consult youth

	1.3.2  Powerholders are committed to youth integration

	OTP.4 # of elected officials and local authorities who participate in project supported capacity building programs and public events
	0
	NA
	NA
	15
	0
	20
	13 
(03F, 10M)
	25
	10 (10M)
	25
	56               (17F, 39M)
	15
	26               (06F, 20M)
	100
	105 
(26F, 79M)










Sub-Purpose 2:  CSOs are stronger, more efficient, improve methods, measure, communicate, develop partnerships and increasingly mobilize local resources
Outcome 2.1 CSOs improve their organizational and technical capacities
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.4 # of FORSATY CSO implementing partners who improve their overall score in the Organizational Capacity Assessment (OCA)
	0
	NA
	NA
	6
	3
	6
	2
	2
	
2

	1
	
1

	3
	0
	18
	

	Consult report for OSSs OCA scores 
No OCA held in 2019 
For FY15 and FY16 OSSs achieved more than 50% of their OCA plans this did not necessarily reflect on their overall score. The indicator was worded different lent back in 2015-2016 

	2.1.1  CSOs improve their organizational capacities

	No separate indicator proposed. Performance achieving this output will be measured by OTC.4

	2.1.2 CSOs improve their technical capacities

	No separate indicator proposed. Performance achieving this output will be measured by OTC.4

	2.1.3 CSOs better manage information, assess their performance and communicate regularly

	No separate indicator proposed. Performance achieving this output will be measured by OTC.4



Outcome 2.2 Marginalized youth are listened to, referred and accompanied by CSOs
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.5# of FORSATY CSO implementing partners who establish effective referral and orientation services (newly added starting FY17)
	
	NA
	NA
	NA
	NA
	NA
	NA
	0
	0
	0
	0
	4
	5
	4
	5

	2.2.1 CSOs better identify, counsel, refer and accompany marginalized youth

	No separate indicator proposed. Performance achieving this output will be measured by OTC.5

	2.2.2  CSOs network to provide an efficient referral system to  youth

	No separate indicator proposed. Performance achieving this output will be measured by OTC.5

	2.2.3 Youth have access to psycho-social services in the neighborhood

	OTP.5 # of youth who receive psycho-social services offered by FORSATY implementing partners (newly added starting FY17)
	0
	NA
	NA
	NA
	NA
	NA
	NA
	1000
	998 (511F, 487M) 
	800
	1390     (762F, 628M)
	400
	664   (363F, 301M)
	2200
	3052 (1636, 1416M)



Outcome 2.3 CSOs actions are more sustainable
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.6 # of FORSATY CSO implementing partners who diversify their sources of funding for core project activities.
	0
	NA
	NA
	2
	3 
	3
	5 
	4
	
5

	4
	
4

	4
	4
	17
	21

	2.3.1 CSOs work closely with public services and private sector

	2.3.2 CSOs increasingly mobilize public and private resources

	OTP.6 # of partnerships and/or agreements formed by FORSATY CSO implementing partners with the private and public sectors to reinforce services for at-risk youth (newly added starting FY17)
	0
	NA
	NA
	NA
	NA
	NA
	NA
	4
	12
	4
	26
	2
	27
	10
	65






Sub-Purpose 3: Schools retain and prepare marginalized youth for integration 
Outcome 3.1 Marginalized youth are better integrated in school
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.7 % of at-risk in-school youth having participated in project supported after school tutoring program whose grades improve  (m/f)
	0
	NA
	NA
	75%
	64%
(Primary: 75%)
(Secondary: 52%)
	75%
	82%
(Primary: 85%)
(Secondary: 78%)
	75%
	77% 
(Primary: 75%
Secondary: 80%)
	75%
	72%
(Primary: 68%
Secondary: 75%)
	75%
	66%
(Primary: 66%
Secondary: 66%)
	75%
	72% (Primary: 74%
Secondary: 70%)

	OTP.7 # of CSO education staff, school administration and faculty and members of PTAs who receive training from the project m/f
	0
	320
	362 (98F, 264M)
 
	61
	113
(31F, 82M)

	71
	150 
(31F; 119M)

	96
	193
(73F, 120M)
	106
	273              (59F, 214M)
	30
	248             (49F, 199M)
	684
	1339 (341F, 998M)

	OTP.8 # of at-risk, in-school youth who attend  FORSATY CSO implementing partners’ after school tutoring
programs (m/f
	Primary: 5,24/10        Secondary  9,36/20
	1600
	2674 (1310F, 1364M) *

	1260
	1779 
(863F; 916M)
	1375
	1433 
(714F; 719M)

	1510
	1183 
(581F, 602M)
	1310
	2011        (1035F, 976M)
	1310
	1338 (723F, 615M)
	8365
	10 418 (5226F, 5191M)

	OTP.9 # of school initiatives organized by target schools, PTAs,  or other parent-involved school governance committees in partnership with FORSATY CSO implementing partners
	0
	NA
	NA
	29
	42
	38
	170
	55
	124
	60
	77
	20
	51
	202
	464



Outcome 3.2 Schools and CSOs promote fulfillment and personal growth
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	3.2.1 Schools and CSOs offer opportunities for students with difficulties to express themselves and exchange

	OTP.10 # of teachers in target schools trained by project on “passport to success” life skills methodology m/f
	0
	NA
	48 
(12F; 36M)
	75
	52  (18F; 34M)
	86
	32 
(12F; 20M)
	32
	21
(9F, 12M)
	0
	0
	0
	0
	193
	153
 (51F, 102M)

	3.2.2 Schools and CSOs strengthen students’ soft skills

	OTP.11 # of after school clubs that implement at least 6 life skills modules
	0
	NA
	19
	35
	30
	57
	27
	27
	31
	30
	Unavailable 
	30
	Unavailable
	179
	107

	3.2.3 Schools and CSOs build civic values 

	No separate indicator proposed. Performance achieving this output will be measured by POI 2












Sub-Purpose 4: Marginalized youth are trained and have access to decent jobs
Outcome 4.1 Vocational initiation and training are better adapted to the needs of marginalized youth
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.8 # of target youth who are employed, self-employed or undertaking an internship
	0
	400
	476 (181F;
295M)*
	690
	1 006 (379F;
627M)*
	759
	1678
(580F; 1098M)
	1130
	1418 
(447F, 971M) 
	900
	 1237    (369F, 868M)
	450
	502  (190F, 312M)
	4329
	6317
(2146F, 4171M)

	4.1.1 Youth benefit from information, counseling and referral from CSOs and public services

	OTP.12 # of target youth who participate in FORSATY supported CSO and training center vocational orientation or job placement services. (m/f)
	0
	NA
	NA
	2100
	2299 (812F; 1487M) 
	2310
	3192 
(1028F; 2164M)
	3156
	4122 
(1474F, 2648M)
	3000
	5175   (2115F, 3060M)
	1500
	3356 (1469F, 1887M)
	12066
	18144 (6898F, 11246M)

	4.1.2 Youth benefit from appropriate training methods and develop their soft skills

	OTP.13 # of target youth participate in work readiness activities, life skills development programs, or/and entrepreneurship training programs. (m/f)
	0
	NA
	NA
	425
	1333 (517F; 816M)*
	470
	2271 
(793F; 1478M) 
	820
	2011
 (693F, 1318M)
	686
	1491     (552F, 939M)
	343
	2040 (967F, 1073M)
	2744
	9146
(3522F, 5624M)

	4.1.3 Youth are accompanied through their training program and professional  integration

	OTP. 14 # of target youth who complete a project supported vocational training program. (m/f) performance indicator for PPR
	0
	320
	374 (231F; 143M)*
	704
	718 (447F; 271M)*
	774
	978 
(327F; 651M)
	1113
	932 (257F, 675M)
	800
	658      (188F, 470M)
	400
	557 (172F, 385M)
	4111
	4217
(1622F; 2595M)

	OTP. 15# of CSO personnel and other training center trainers and other personnel who participate in project supported training, forums or round table meetings.
	0
	NA
	102
	70
	200
	120
	411 
	150
	265
	200
	201
	100
	279
	640
	1458



Outcome 4.2 The private sector is engaged in favor of marginalized youth
	Indicator
	Baseline
	FY 14
	FY 15
	FY 16
	FY 17
	FY 18
	FY 19
	Global

	
	
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A
	T
	A

	OTC.9 # % of project supported training programs that form partnerships with employers (m/f)
	0
	25
	15
	03
	12
	05
	30
	12
	26
	09
	18
	02
	24
	56
	125

	4.2.1  The private sector works closely with CSOs and contributes to their programs

	4.2.2 Marginalized youth increasingly have access to decent jobs

	No separate indicator proposed. Performance achieving these outputs will be measured by OTC. 6 and OTC.9



*NB: the gender disaggregation in marked indicators (*) was calculated based on the gender ratio extracted from the gender disaggregation reported by partner OSSs concerning enrolled youth. This methods was adopted because certain associations were still struggling with reporting exact gender disaggregation for marked indicators   
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